## Update guideline
Page 1- For OPM
Page 2 - For Requesters

## Pivot Table 3
Loading
0%
100%
100%
100%
0%
0%
100%
100%
0%
0%
0%
0%
0%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
0%
100%
0%
100%
100%
100%
100%
100%
100%
100%
0%
0%
100%
100%
0%
0%
0%
0%
0%
0%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
0%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
0%
100%
100%
0%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
#DIV/0!
0%
0%
0%
0%
0%
0%
0%
100%
100%
100%
100%
100%
0%
0%
0%
0%
100%
100%
0%
0%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
0%
0%
0%
0%
100%
100%
100%
100%
100%
0%
0%
0%
100%
100%
100%
0%
100%
100%
#REF!
100%
100%

## G Project Timeline-OPM update
Rule: MVA EQ in-house date will be 2weeks earlier than each stage Date of each stage = OPM release
Update ngày construction finish
|  |  | Brand |  |  | 1st stage | 2nd stage | 3rd stage | 4th stage | 5th stage | 6th stage
|  |  | SKW | Pre-MLB | proto 0 | P1.0 | P1.1 | EVT | DVT | PVT | MP
| Project Year | Project | Phase |  |  | Date | Date | Date | Date | Date | Date | OPM DRI | Mail approved Budget
| P26 | 4CS4 | SMT |  |  | - | - | - | 2026-02-23 | 2026-04-11 | 2026-05-07 | Doris- SMT OPM
| P26 | 4CS4 | FATP |  |  | - | - | - | 2026-03-09 | 2026-04-23 | 2026-05-07 | OPM- Đức_Ryan
| P26 | CGY4 | SMT |  |  | - | - | - | 2026-02-23 | 2026-04-13 | 2026-05-07 | Judy Tran
| P26 | CGY4 | FATP |  |  | - | - | - | 2026-03-09 | 2026-04-23 | 2026-05-07 | thuy Sarah
| P26 | PKK4 | SMT |  |  | - | - | - | 2026-02-23 | 2026-04-11 | 2026-05-07 | Huong Nguyen - Clara
| P26 | PKK4 | FATP |  |  | - | - | - | 2026-03-09 | 2026-04-23 | 2026-05-07 | Luyện - Ben
| P26 Demo Line | 4CS4 | SMT |  |  |  |  | 2026-02-19 | 2026-02-19 | 2026-04-11 | 2026-05-14 | Doris- SMT OPM
| P26 Demo Line | 4CS4 | FATP |  |  |  |  | 2026-02-19 | 2026-02-19 | 2026-04-23 | 2026-05-14 | OPM- Đức_Ryan
| P26 Demo Line | CGY4 | SMT |  |  |  |  | 2026-02-19 | 2026-02-19 | 2026-04-11 | 2026-05-14 | Judy Tran
| P26 Demo Line | CGY4 | FATP |  |  |  |  | 2026-02-19 | 2026-02-19 | 2026-04-23 | 2026-05-14 | thuy Sarah
| P26 Demo Line | PKK4 | SMT |  |  |  |  | 2026-02-19 | 2026-02-19 | 2026-04-11 | 2026-05-14 | Huong Nguyen - Clara
| P26 Demo Line | PKK4 | FATP |  |  |  |  | 2026-02-19 | 2026-02-19 | 2026-04-23 | 2026-05-14 | Luyện - Ben
| P26 Zombie line | 4CS4 | Zombie | [6 empty] | 2026-05-23 | 2026-06-29 | Jenna Thanh Tam
| P26 Zombie line | CGY4 | Zombie | [6 empty] | 2026-05-23 | 2026-06-29 | OPM Hung Tom
| P26 Zombie line | PKK4 | Zombie | [6 empty] | 2026-05-23 | 2026-06-29 | Kayla Thùy Dương
| P26 Service line | 4CS4 | SMT | [6 empty] | 2026-05-02 | 2026-05-07 | Tiffany Tiên
| P26 Service line | 4CS4 | FATP | [7 empty] | 2026-05-18 | Thomas OPM Thanh
| P26 Service line | CGY4 | SMT | [6 empty] | 2026-05-02 | 2026-05-07 | Tiffany Tiên
| P26 Service line | CGY4 | FATP | [7 empty] | 2026-05-18 | Thomas OPM Thanh
| P26 Service line | PKK4 | SMT | [6 empty] | 2026-05-02 | 2026-05-07 | Tiffany Tiên
Add | P26 Service line | PKK4 | FATP | [7 empty] | 2026-05-18 | Thomas OPM Thanh
Repair-A Quan | P27 | WGO5 | SMT |  |  | 2026-05-30 | 2026-07-05 | 2026-09-20 | 2027-02-01 | 2026-04-12 |  | Tina Nguyen - OPM SMT
Packing-OPM | P27 | WGO5 | FATP |  |  | 2026-06-01 | 2026-07-13 | 2026-10-05 | 2027-02-08 | 2026-04-12 |  | Katy Nguyen Thuy Duong
| P27 | ASK5 | SMT |  |  | 2026-05-30 | 2026-07-05 | 2026-09-20 | 2027-02-01 | 2026-04-12 |  | Tina Nguyen - OPM SMT
| P27 | ASK5 | FATP |  |  | 2026-06-01 | 2026-07-13 | 2026-10-05 | 2027-02-08 | 2026-04-12 |  | Linh Nguyen G-OPM
| P27 | KSH5 | SMT |  |  | 2026-05-30 | 2026-07-05 | 2026-09-20 | 2027-02-01 | 2026-04-12 |  | Tina Nguyen - OPM SMT
| P27 | KSH5 | FATP |  |  | 2026-06-01 | 2026-07-13 | 2026-10-05 | 2027-02-08 | 2026-04-12 |  | Anh Thảo -Tiffany
| F27 | MCN5 | SMT | 2026-04-08 | 2026-05-12 | 2026-05-25 | 2026-07-21 | 2026-10-09 | 2027-02-18 | 2027-04-16 |  | Minhi Nguyen - OPM SMT
| F27 | MCN5 | FATP |  | 2026-04-28 | 2026-05-25 | 2026-07-20 | 2026-10-10 | 2027-02-19 |  |  | Jessie Nguyen OPM
| P25 Service line | MT5 | FATP
| P25 Service line | BZ5 | FATP
| P25 Service line | FL5 | FATP
| P25 Service line | MT5 | SMT
| P25 Service line | BZ5 | SMT
| P25 Service line | FL5 | SMT

## G Project MVA EQ Request
Date of Request | Department | Requester name | Requester employee ID | Email | Phone | Item | Request equipment spec | Price | Quantity | Total Cost | Purpose | Year Project | Project | Process | Stage | Required Delivery Date (update by DRI) | Given LT (days) (follow DRI update) | Required Delivery Date follow Stage date (line open date - 14 days) | Given LT (days) follow stage date | Total Leadtime | Request Deadline | LT theo ngày request of DRI | Late/ ontime | Action | Remark | Budget Status | Budget # | PR Status | PR # | PO Status | PO # | ETA (Plan) | DTA (Actual) | #PUR request No | Pending reason (If have) | Action for delivery later than time Setup line | Qty Done Budget | Qty Done PR | Qty Done PO | Qty Recieved
2026-01-12 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To | 4327 | Mini PC (Assy) | #N/A | 7800000 | 49 | 382200000 | P26 Demo Line | P26 Demo Line | 4CS4 | FATP | DVT | 2026-02-12 | 31 | 2026-02-05 | 24 |  | 2026-02-05 |  | On time | New Buy |  | Done |  | Done |  | Done | 1FSHQ10118 |  | Đã nhận 11.03.2026 | EPR2601310006 |  |  | 49 | 49 | 49 | 49
2026-01-12 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To | 4327 | Monitor (White)+ ARM | HKC MB24V7-W, 23.8 inch White, With Bracket Arm Warrior WA-MH0802 (White) | 1815000 | 49 | 88935000 | P26 Demo Line | P26 Demo Line | 4CS4 | FATP | DVT | 2026-02-12 | 31 | 2026-02-05 | 24 | 80 | 2025-11-17 |  | Late | New Buy |  | Done |  | Done |  | Done | 1FSHQ10079 |  | 2026-02-20 | EPR2601310007 |  |  | 49 | 49 | 49 | 49
2026-01-13 | QA | Ngô Thị Hoa | V1524668 | Hoa (Hana) |  | Mini PC (Assy) | #N/A | 7800000 | 23 | 179400000 | P26 Demo Line | P26 Demo Line | 4CS4 | FATP | EVT | 2026-02-12 | 30 | 2026-02-05 | 23 |  | 2026-02-05 |  | On time | New Buy |  | Done |  | Done |  | Done | 1FSHQ10118 |  | Đã nhận 11.03.2026 | EPR2602020001 |  |  | 23 | 23 | 23 | 23
2026-01-13 | QA | Ngô Thị Hoa | V1524668 | Hoa (Hana) |  | Monitor (White)+ ARM | HKC MB24V7-W, 23.8 inch White, With Bracket Arm Warrior WA-MH0802 (White) | 1815000 | 23 | 41745000 | P26 Demo Line | P26 Demo Line | 4CS4 | FATP | EVT | 2026-02-12 | 30 | 2026-02-05 | 23 | 80 | 2025-11-17 |  | Late | New Buy |  | Done |  | Done |  | Done | 1FSHQ10079 |  | 2026-02-20 | EPR2602020002 |  |  | 23 | 23 | 23 | 23
2026-01-13 | TE | Nguyen Trung Kien | V1524574 | kiennt1@fih-foxconn.com |  | Monitor (White)+ ARM | HKC MB24V7-W, 23.8 inch White, With Bracket Arm Warrior WA-MH0802 (White) | 1815000 | 6 | 10890000 | P26 Demo Line | P26 Demo Line | 4CS4 | FATP | EVT | 2026-02-23 | 41 | 2026-02-05 | 23 | 80 | 2025-11-17 |  | Late | New Buy |  | Done |  | Done |  | Done | 1FSHQ10079 |  | 2026-02-20 | EPR2602020003 |  |  | 6 | 6 | 6 | 6
2026-01-13 | TE | Nguyen Trung Kien | V1524574 | kiennt1@fih-foxconn.com |  | Mini PC (Assy) | #N/A | 7800000 | 6 | 46800000 | P26 Demo Line | P26 Demo Line | 4CS4 | FATP | EVT | 2026-02-23 | 41 | 2026-02-05 | 23 |  | 2026-02-05 |  | On time | New Buy |  | Done |  | Done |  | Done | 1FSHQ10118 |  | Đã nhận 11.03.2026 | EPR2602020004 |  |  | 6 | 6 | 6 | 6
2026-01-19 | ENG3 | Nguyen Van Huynh | V1536667 | Nguyễn Seven (Huỳnh) | 4500 | IPC+ | #N/A | 14200000 | 5 | 71000000 | PC for Auto charging machine P26 | P26 | 4CS4 | FATP | DVT | 2026-01-30 | 11 | 2026-02-23 | 35 |  | 2026-02-23 |  | On time | New Buy |  | Done | FATP-NPI-P26-MVA2601-104OM | Done | 1FSHQ10126 | Done | 1FSHQ10126 |  | 2026-02-20 | EPR2601310001: Done |  |  | 5 | 5 | 5 | 5
2026-01-19 | ENG3 | Nguyen Van Huynh | V1536667 | Nguyễn Seven (Huỳnh) | 4500 | IPC+ | #N/A | 14200000 | 5 | 71000000 | PC for Auto charging machine P26 | P26 | PKK4 | FATP | DVT | 2026-01-30 | 11 | 2026-02-23 | 35 |  | 2026-02-23 |  | On time | New Buy |  | Done | FATP-NPI-P26-MVA2601-104OM | Done | 1FSHQ10127 | Done | 1FSHQ10126 |  | 2026-02-20 | EPR2601310002: Done |  |  | 5 | 5 | 5 | 5
2026-01-19 | ENG3 | Nguyen Van Huynh | V1536667 | Nguyễn Seven (Huỳnh) | 4500 | IPC+ | #N/A | 14200000 | 5 | 71000000 | PC for Auto charging machine P26 | P26 | CGY4 | FATP | DVT | 2026-01-30 | 11 | 2026-02-23 | 35 |  | 2026-02-23 |  | On time | New Buy |  | Done | FATP-NPI-P26-MVA2601-104OM | Done | 1FSHQ10128 | Done | 1FSHQ10126 |  | 2026-02-20 | EPR2601310003: Done |  |  | 5 | 5 | 5 | 5
2026-02-05 | REL | Laymu Chen | 504000 | LaymuTHChen@fih-foxconn.com |  | IPC | #N/A | 10870000 | 2 | 21740000 | P26 | P26 | 4CS4 | SMT | DVT | 2026-02-11 | 6 | 2026-02-09 | 4 |  | 2026-02-09 |  | On time | Leverage |  | Done |  | Done |  | Done |  |  | 2026-02-11 | EPR2602060002 : Done / tầm T7 trả |  | Tháng 7 trả? | 2 | 2 | 2 | 2
2026-02-05 | REL | Laymu Chen | 504000 | LaymuTHChen@fih-foxconn.com |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 7 | 8680000 | P26 | P26 | 4CS4 | SMT | DVT | 2026-02-11 | 6 | 2026-02-09 | 4 | 50 | 2025-12-21 |  | Late | Leverage |  | Done |  | Done |  | Done |  |  | 2206-02-11 | EPR2602060003 Done / tầm T7 trả |  | Tháng 7 trả? | 7 | 7 | 7 | 7
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 31 | 38440000 | PKK4 | P26 | PKK4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 | 50 | 2026-03-04 | 2026-04-18 | On time | New Buy |  | Done | FATP-MP-PKK4-MVA2603-03OM | Done | 1FSHQ30084 | Done | 1FSHQ30084 | 2026-05-02 | 2026-05-02 | EPR2603070011 |  |  | 31 | 31 | 31 | #REF!
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Mini PC (Assy) | #N/A | 7800000 | 31 | 241800000 | PKK4 | P26 | PKK4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 |  | 2026-04-23 | 2026-02-27 | On time | New Buy |  | Done | FATP-MP-PKK4-MVA2603-03OM | Done | 1FSHQ30085 | Done | 1FSHQ30085 |  |  | EPR2603070012 |  |  | 31 | 31 | 31 | 31
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 31 | 71300000 | PKK4 | P26 | PKK4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 | 50 | 2026-03-04 | 2026-04-18 | On time | New Buy |  | Done | FATP-MP-PKK4-MVA2603-28OM | Done | VNPR202604040096 | Done | VNPO202604160162 | 2026-05-29 | 2026-05-30 | EPR2603210009 |  |  | 31 | 31 | 31 | 31
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 21 | 1024800000 | PKK4 | P26 | PKK4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 | 50 | 2026-03-04 | 2026-04-18 | On time | New Buy |  | Done | FATP-MP-PKK4-MVA2603-03OM | Done | 1FSHQ30087 | Done | 1FSHQ30087 | pending |  | EPR2603070013 |  | Lấy 16x 1FSHQ20007 => Trả hàng trước | 21 | 21 | 21 | 0
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 138 | 171120000 | 4CS4 | P26 | 4CS4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 | 50 | 2026-03-04 | 2026-04-18 | On time | New Buy |  | Done | FATP-MP-4CS4-MVA2603-04OM | Done | 1FSHQ30096 | Done | 1FSHQ30096 | EPR2603070014 request này của MFG P26 có 138x màn hình. Chị lấy đơn 1FSHQ40007 & 1FSHQ30117 : 38 + 6 =44x Trả đơn trước cho P26 MFG | 85x out ngày 10.06.2026 | EPR2603070014 |  |  | 138 | 138 | 138 | 138
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Mini PC (Assy) | #N/A | 7800000 | 163 | 1271400000 | 4CS4 | P26 | 4CS4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 |  | 2026-04-23 | 2026-02-27 | On time | New Buy |  | Done | FATP-MP-4CS4-MVA2603-04OM | Done | 100x 1FSHQ30097 63x 1FSHQ30098 | Done | 100x 1FSHQ30097 63x 1FSHQ30098 | pending |  | EPR2603070015 |  |  | 163 | 163 | 163 | 0
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 160 | 368000000 | 4CS4 | P26 | 4CS4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 | 50 | 2026-03-04 | 2026-04-18 | On time | New Buy |  | Done | FATP-MP-4CS4-MVA2603-29OM | Done | VNPR202604040091 | Done | VNPO202604160165 | 2026-05-29 | 2026-05-30 | EPR2603210010 |  |  | 160 | 160 | 160 | 160
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 6 | 19800000 | 4CS4 | P26 | 4CS4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 | 50 | 2026-03-04 | 2026-04-18 | On time | New Buy |  | Done | FATP-MP-4CS4-MVA2603-29OM | Done | VNPR202604040091 | Done | VNPO202604160165 | Dự kiến 25/05 hàng về |  | EPR2603210011 |  |  | 6 | 6 | 6 | 0
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 20 | 976000000 | 4CS4 | P26 | 4CS4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 | 50 | 2026-03-04 | 2026-04-18 | On time | New Buy |  | Done | FATP-MP-4CS4-MVA2603-04OM | Done | 1FSHQ30099 | Done | 1FSHQ30099 |  | 2026-05-20 | EPR2603070016 |  |  | 20 | 20 | 20 | 20
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Mini PC (Assy) | #N/A | 7800000 | 184 | 1435200000 | CGY4 | P26 | CGY4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 |  | 2026-04-23 | 2026-02-27 | On time | New Buy |  | Done | FATP-MP-CGY4-MVA2603-05OM | Done | 100x 1FSHQ30103 84x 1FSHQ30108 | Done | 100x 1FSHQ30103 84x 1FSHQ30108 | pending |  | EPR2603070018 |  | 120x mini PC (OR5) xuất urgent cho P26-CGY4 | 184 | 184 | 184 | 0
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 35 | 43400000 | CGY4 | P26 | CGY4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 | 50 | 2026-03-04 | 2026-04-18 | On time | New Buy |  | Done | FATP-MP-CGY4-MVA2603-05OM | Done | 1FSHQ30102 | Done | 1FSHQ30102 | 2026-05-02 | 2026-05-02 | EPR2603070017 |  |  | 35 | 35 | 35 | 35
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 180 | 414000000 | CGY4 | P26 | CGY4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 | 50 | 2026-03-04 | 2026-04-18 | On time | New Buy |  | Done | FATP-MP-CGY4-MVA2603-30OM | Done | VNPR202604040108 | Done | VNPO202604160167 | 2026-05-29 | 2026-05-30 | EPR2603210012 |  |  | 180 | 180 | 180 | 180
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 7 | 23100000 | CGY4 | P26 | CGY4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 | 50 | 2026-03-04 | 2026-04-18 | On time | New Buy |  | Done | FATP-MP-CGY4-MVA2603-30OM | Done | VNPR202604040108 | Done | VNPO202604160167 | 2026-06-20 | 2026-06-20 | EPR2603210013: Đã trả request trước PO |  |  | 7 | 7 | 7 | 7
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 31 | 1512800000 | CGY4 | P26 | CGY4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 | 50 | 2026-03-04 | 2026-04-18 | On time | New Buy |  | Done | FATP-MP-CGY4-MVA2603-05OM | Done | 20x 1FSHQ30106 11x 1FSHQ30107 | Done | 20x 1FSHQ30106 11x 1FSHQ30107 | 11x 1FSHQ30107 / 20/05 hàng về |  | EPR2603070019 |  |  | 31 | 31 | 31 | 0
2026-02-27 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Monitor (White)+ ARM | HKC MB24V7-W, 23.8 inch White, With Bracket Arm Warrior WA-MH0802 (White) | 1815000 | 149 | 270435000 | CGY4 | P26 | CGY4 | FATP | MP | 2026-04-11 | 43 | 2026-04-23 | 55 | 80 | 2026-02-02 | 2026-05-18 | Late | New Buy |  | Done | FATP-MP-CGY4-MVA2603-05OM | Done | 1FSHQ30105 | Done | 1FSHQ30105 |  | Đã nhận 20.04 | EPR2603070020 |  |  | 149 | 149 | 149 | 149
2026-03-06 | TE FATP | Nguyen Trung Kien | V1524574 | kiennt1@fih-foxconn.com | 4440 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 76 | 2033152000 | CGY4 FATP | P26 Demo Line | CGY4 | FATP | EVT | 2026-03-16 | 10 | 2026-02-05 | -29 | 70 | 2025-11-27 | 2026-05-15 | Late | New Buy |  | Done | FATP-MP-P26-MVA2603-01OM | Done | 40x 1FSHQ30073 40x 1FSHQ30075 40x 1FSHQ30076 21x 1FSHQ30078 | Done | 40x 1FSHQ30073 40x 1FSHQ30075 40x 1FSHQ30076 21x 1FSHQ30078 |  | 2026-04-14 | EPR2603210043 ( Số lượng QTY cụ thể đã chia trên file chị Q) |  |  | 76 | 76 | 76 | 76
2026-03-06 | TE SMT | Nguyen Trung Kien | V1524574 | kiennt1@fih-foxconn.com | 4440 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 36 | 963072000 | CGY4 SMT | P26 Demo Line | CGY4 | SMT | EVT | 2026-03-16 | 10 | 2026-02-05 | -29 | 70 | 2025-11-27 | 2026-05-15 | Late | New Buy |  | Done | SMT-MP-P26-MVA2603-17OM | Done | 1FSHQ30200 | Done | 1FSHQ30200 |  | 2026-04-14 | EPR2603210044 |  |  | 36 | 36 | 36 | 36
2026-03-06 | TE FATP | Nguyen Trung Kien | V1524574 | kiennt1@fih-foxconn.com | 4440 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 65 | 1738880000 | 4CS4 FATP | P26 | 4CS4 | FATP | MP | 2026-03-16 | 10 | 2026-04-23 | 48 | 70 | 2026-02-12 | 2026-05-15 | Late | New Buy |  | Done | FATP-MP-P26-MVA2603-01OM | Done | 40x 1FSHQ30073 40x 1FSHQ30075 40x 1FSHQ30076 21x 1FSHQ30078 | Done | 40x 1FSHQ30073 40x 1FSHQ30075 40x 1FSHQ30076 21x 1FSHQ30078 |  | 2026-04-14 | EPR2603210045 ( Số lượng QTY cụ thể đã chia trên file chị Q) |  |  | 65 | 65 | 65 | 65
2026-03-06 | TE SMT | Nguyen Trung Kien | V1524574 | kiennt1@fih-foxconn.com | 4440 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 38 | 1016576000 | 4CS4 SMT | P26 | 4CS4 | SMT | MP | 2026-03-16 | 10 | 2026-04-23 | 48 | 70 | 2026-02-12 | 2026-05-15 | Late | New Buy |  | Done | SMT-MP-P26-MVA2603-17OM | Done | 1FSHQ30201 | Done | 1FSHQ30201 |  | 2026-04-14 | EPR2603210046 |  |  | 38 | 38 | 38 | 38
2026-03-13 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 3 | 5940000 | 4CS4 SVR line | P26 Service line | 4CS4 | FATP | MP | 2026-04-15 | 33 | 2026-05-04 | 52 | 50 | 2026-03-15 | 2026-05-02 | On time | New Buy | G | Done | FATP-SV-4CS4-MVA2603-42OM | Done | 1FSHQ40058 | Done | 1FSHQ40058 |  | 2026-04-29 | EPR2603240015 |  |  | 3 | 3 | 3 | 3
2026-03-13 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 3 | 56151000 | 4CS4 SVR line | P26 Service line | 4CS4 | FATP | MP | 2026-04-15 | 33 | 2026-05-04 | 52 | 70 | 2026-02-23 | 2026-05-22 | Late | New Buy | G | Done | FATP-SV-4CS4-MVA2603-42OM | Done | 1FSHQ40057 |  | 1FSHQ40057 |  | Đã nhận 23/04 | EPR2603240016 |  |  | 3 | 3 | 0 | 3
2026-03-13 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 1 | 15500000 | 4CS4 SVR line | P26 | 4CS4 | FATP | MP | 2026-04-15 | 33 | 2026-04-23 | 41 | 65 | 2026-02-17 | 2026-05-17 | Late | New Buy | G | Done | FATP-MP-4CS4-MVA2603-42OM | Done | VNPR202603260169 | Done | VNPO202603310112 |  | 2026-05-07 | EPR2603240017 |  | đã out 20may tại vp OM - chị Việt | 1 | 1 | 1 | 1
2026-03-13 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | 5800000 | 1 | 5800000 | 4CS4 SVR line | P26 | 4CS4 | FATP | MP | 2026-04-15 | 33 | 2026-04-23 | 41 | 65 | 2026-02-17 | 2026-05-17 | Late | New Buy | G | Done | FATP-MP-4CS4-MVA2603-42OM | Done | VNPR202603260169 | Done | VNPO202603310112 |  | Đã nhận 25.04 | EPR2603210023 |  |  | 1 | 1 | 1 | 1
2026-03-13 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 3 | 5940000 | CGY4 SVR line | P26 Service line | CGY4 | FATP | MP | 2026-04-15 | 33 | 2026-05-04 | 52 | 50 | 2026-03-15 | 2026-05-02 | On time | New Buy | G | Done | FATP-SV-CGY4-MVA2603-43OM | Done | 1FSHQ40061 | Done | 1FSHQ40061 |  | 2026-04-29 | EPR2603240018 |  |  | 3 | 3 | 3 | 3
2026-03-13 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 3 | 56151000 | CGY4 SVR line | P26 Service line | CGY4 | FATP | MP | 2026-04-15 | 33 | 2026-05-04 | 52 | 70 | 2026-02-23 | 2026-05-22 | Late | New Buy | G | Done | FATP-SV-CGY4-MVA2603-43OM | Done | 1FSHQ40059 | Done | 1FSHQ40059 |  | Đã nhận | EPR2603240019 |  |  | 3 | 3 | 3 | 3
2026-03-13 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 1 | 15500000 | CGY4 SVR line | P26 | CGY4 | FATP | MP | 2026-04-15 | 33 | 2026-04-23 | 41 | 65 | 2026-02-17 | 2026-05-17 | Late | New Buy | G | Done | FATP-MP-CGY4-MVA2603-43OM | Done | VNPR202603260195 | Done | VNPO202603310112 |  | 2026-05-07 | EPR2603240020 |  | đã out 20may tại vp OM - chị Việt | 1 | 1 | 1 | 1
2026-03-13 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | 5800000 | 1 | 5800000 | CGY4 SVR line | P26 | CGY4 | FATP | MP | 2026-04-15 | 33 | 2026-04-23 | 41 | 65 | 2026-02-17 | 2026-05-17 | Late | New Buy | G | Done | FATP-MP-CGY4-MVA2603-43OM | Done | VNPR202603260195 | Done | VNPO202603310112 |  | Đã nhận 25.04 | EPR2603210025 |  |  | 1 | 1 | 1 | 1
2026-03-13 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 3 | 5940000 | PKK4 SVR line | P26 Service line | PKK4 | FATP | MP | 2026-04-15 | 33 | 2026-05-04 | 52 | 50 | 2026-03-15 | 2026-05-02 | On time | New Buy | G | Done | FATP-SV-PKK4-MVA2603-44OM | Done | 1FSHQ40063 | Done | 1FSHQ40063 |  | 2026-04-29 | EPR2603240021 |  |  | 3 | 3 | 3 | 3
2026-03-13 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 3 | 56151000 | PKK4 SVR line | P26 Service line | PKK4 | FATP | MP | 2026-04-15 | 33 | 2026-05-04 | 52 | 70 | 2026-02-23 | 2026-05-22 | Late | New Buy | G | Done | FATP-SV-PKK4-MVA2603-44OM | Done | 1FSHQ40062 | Done | 1FSHQ40062 |  | Đã nhận | EPR2603240022 |  |  | 3 | 3 | 3 | 3
2026-03-13 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 1 | 15500000 | PKK4 SVR line | P26 Service line | PKK4 | FATP | MP | 2026-04-15 | 33 | 2026-05-04 | 52 | 65 | 2026-02-28 | 2026-05-17 | Late | New Buy | G | Done | FATP-SV-PKK4-MVA2603-44OM | Done | VNPR202603260203 | Done | VNPO202603310112 |  | Đã nhận 25.04 | EPR2603240023 |  | đã out 20may tại vp OM - chị Việt | 1 | 1 | 1 | 1
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 33 | 40920000 | 4CS4 Service | P26 Service line | 4CS4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | G | Done | FATP-SV-4CS4-MVA2603-36OM | Done | 1FSHQ40025 | Done | 1FSHQ40025 | pending | Lấy 33x / 93x 1FSHQ40123 P27 trả hàng trước | EPR2603240024 |  | Mới add | 33 | 33 | 33 | 33
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Mini PC (Assy) | LAMITOUCH LM-30 CPU:i3-6100, RAM 16GB DDR4 3200, SSD 256G, Slot: CAT61/HDMI1/VGA1/USB8 | 7800000 | 33 | 257400000 | 4CS4 Service | P26 Service line | 4CS4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 |  | 2026-05-04 | 2026-03-16 | On time | New Buy | G | Done | FATP-SV-4CS4-MVA2603-36OM // FATP-MP-P26-MVA2605-38OM | Done | 1FSHQ40030 // 1FSHQ50347 | Done | 1FSHQ40030 ( Cancel PO ) // 1FSHQ50347 |  | Lấy 40x trong 100x MINI PC LAMITOUCH NON G / 81x trả đơn 15.06.2026 | EPR2603240025 (Cancel) // EPR2606110005 & EPR2606130001 |  |  | 33 | 33 | 33 | 33
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 51 | 117300000 | 4CS4 Service | P26 Service line | 4CS4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | G | Done | FATP-SV-4CS4-MVA2603-36OM | Done | VNPR202604030260 | Done | VNPO202604100259 | 2026-04-25 | 2026-04-25 | EPR2603210028 |  | Mới add | 51 | 51 | 51 | 51
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 9 | 29700000 | 4CS4 Service | P26 Service line | 4CS4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | G | Done | FATP-SV-4CS4-MVA2603-36OM | Done | VNPR202604030260 | Done | VNPO202604100259 | 2026-05-07 | 2026-05-09 | EPR2603210029 / May 9, 8:20 AM |  | Mới add | 9 | 9 | 9 | 9
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 14 | 683200000 | 4CS4 Service | P26 Service line | 4CS4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 |  | 2026-05-04 | 2026-03-16 | On time | New Buy | G | Done | FATP-SV-4CS4-MVA2603-36OM | Done | 1FSHQ40031 | Done | 1FSHQ40031 | 2026-06-25 | 2026-06-27 | EPR2603240026 |  | Mới add | 14 | 14 | 14 | 14
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 40 | 49600000 | CGY4 Service | P26 Service line | CGY4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | G | Done | FATP-SV-CGY4-MVA2603-37OM | Done | 1FSHQ40027 | Done | 1FSHQ40027 | pending | Lấy 40x / 93x 1FSHQ40123 P27 trả hàng trước | EPR2603240027 |  | Mới add | 40 | 40 | 40 | 40
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Mini PC (Assy) | LAMITOUCH LM-30 CPU:i3-6100, RAM 16GB DDR4 3200, SSD 256G, Slot: CAT61/HDMI1/VGA1/USB8 | 7800000 | 40 | 312000000 | CGY4 Service | P26 Service line | CGY4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 |  | 2026-05-04 | 2026-03-16 | On time | New Buy | G | Done | FATP-SV-CGY4-MVA2603-37OM // FATP-MP-P26-MVA2605-38OM | Done | 1FSHQ40028 // 1FSHQ50347 | Done | 1FSHQ40028 ( Cancel PO ) // 1FSHQ50347 |  | Lấy 40x trong 100x MINI PC LAMITOUCH NON G | EPR2603240028 (Cancel) EPR2606110005 & EPR2606130001 |  |  | 40 | 40 | 40 | 40
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 44 | 101200000 | CGY4 Service | P26 Service line | CGY4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | G | Done | FATP-SV-CGY4-MVA2603-37OM | Done | VNPR202604030258 | Done | VNPO202604150301 | 2026-05-29 | 2026-05-30 | EPR2603210030 |  | Mới add | 44 | 44 | 44 | 44
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 6 | 19800000 | CGY4 Service | P26 Service line | CGY4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | G | Done | FATP-SV-CGY4-MVA2603-37OM | Done | VNPR202604030258 | Done | VNPO202604150301 | 2026-05-25 |  | EPR2603210031 Đã trả đơn trước PO về |  | Lấy scanner ở PO: VNPO202604100231 trả đơn trước // anh Mạnh TE OR6 đồng ý | 6 | 6 | 6 | 6
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 14 | 683200000 | CGY4 Service | P26 Service line | CGY4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 |  | 2026-05-04 | 2026-03-16 | On time | New Buy | G | Done | FATP-SV-CGY4-MVA2603-37OM | Done | 1FSHQ40029 | Done | 1FSHQ40029 | 2026-05-22 | 2026-05-23 | EPR2603240029 |  | Mới add | 14 | 14 | 14 | 14
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 48 | 59520000 | PKK4 Service | P26 Service line | PKK4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | G | Done | FATP-SV-PKK4-MVA2603-38OM | Done | 1FSHQ40032 | Done | 1FSHQ40032 | 2026-06-20 | Lấy 23x / 93x 1FSHQ40123 P27 trả hàng trước ; (48x-23x= 25x / 92x 1FSHQ40126 P27 trả hàng trước) | EPR2603240030 |  | Mới add | 48 | 48 | 48 | 48
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Mini PC (Assy) | LAMITOUCH LM-30 CPU:i3-6100, RAM 16GB DDR4 3200, SSD 256G, Slot: CAT61/HDMI1/VGA1/USB8 | 7800000 | 48 | 374400000 | PKK4 Service | P26 Service line | PKK4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 |  | 2026-05-04 | 2026-03-16 | On time | New Buy | G | Done | FATP-SV-PKK4-MVA2603-38OM // FATP-MP-P26-MVA2605-38OM | Done | 1FSHQ40033 // 1FSHQ50347 | Done | 1FSHQ50347 |  | Lấy 40x trong 100x MINI PC LAMITOUCH NON G / 81x trả đơn 15.06.2026 | EPR2603240031 (Cancel) EPR2606110005 & EPR2606130001 | tạm dừng khớp giá |  | 48 | 48 | 48 | 48
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 49 | 112700000 | PKK4 Service | P26 Service line | PKK4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | G | Done | FATP-SV-PKK4-MVA2603-38OM | Done | VNPR202604030289 | Done | VNPO202604150301 | 2026-05-29 | 2026-05-30 | EPR2603210032 |  | Mới add | 49 | 49 | 49 | 49
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 5 | 16500000 | PKK4 Service | P26 Service line | PKK4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | G | Done | FATP-SV-PKK4-MVA2603-38OM | Done | VNPR202604030289 | Done | VNPO202604150301 | 2026-05-25 |  | EPR2603210033: Đã trả đơn trước PO về |  | Mới add | 5 | 5 | 5 | 5
2026-03-16 | MFG | Bui Thi Thanh Huong | V1523147 | huongbtt1@fih-foxconn.com | 4327 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 15 | 732000000 | PKK4 Service | P26 Service line | PKK4 | FATP | MP | 2026-04-15 | 30 | 2026-05-04 | 49 |  | 2026-05-04 | 2026-03-16 | On time | New Buy | G | Done | FATP-SV-PKK4-MVA2603-38OM | Done | 1FSHQ40034 | Done | 1FSHQ40034 | 2026-06-25 | 2026-06-27 | EPR2603240032 |  |  | 15 | 15 | 15 | 15
2026-03-13 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | 5800000 | 1 | 5800000 | PKK4 SVR line | P26 Service line | PKK4 | FATP | MP | 2026-04-15 | 33 | 2026-05-04 | 52 | 65 | 2026-02-28 | 2026-05-17 | Late | New Buy | G | Done | FATP-SV-PKK4-MVA2603-44OM | Done | VNPR202603260203 | Done | VNPO202603310112 |  | Đã nhận 25.04 | EPR2603210027 |  |  | 1 | 1 | 1 | 1
2026-03-16 | ENG1 | Ngo Van Duong | v1523845 | Kelvin Duong STPM | 4328 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 1 | 1240000 | NB for MP P26 | P26 | 4CS4 | FATP | MP | 2026-04-20 | 35 | 2026-04-23 | 38 | 50 | 2026-03-04 | 2026-05-05 | Late | New Buy | G | Done | FATP-MP-4CS4-MVA2603-19OM | Done | 1FSHQ30273 | Done | 1FSHQ30273 |  | 2026-05-12 | EPR2603210018 |  | Lấy OM stock trước / Mua bù sau | 1 | 1 | 1 | 1
2026-03-16 | ENG1 | Ngo Van Duong | v1523845 | Kelvin Duong STPM | 4328 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 1 | 1240000 | NB for MP P26 | P26 | PKK4 | FATP | MP | 2026-04-20 | 35 | 2026-04-23 | 38 | 50 | 2026-03-04 | 2026-05-05 | Late | New Buy | G | Done | FATP-MP-PKK4-MVA2603-20OM | Done | 1FSHQ30275 | Done | 1FSHQ30275 |  | Đã nhận 10.4 | EPR2603210019 |  | Lấy OM stock trước / Mua bù sau / 1FSHQ30275x: Đã nhận hàng | 1 | 1 | 1 | 1 | 341
2026-03-16 | ENG1 | Ngo Van Duong | v1523845 | Kelvin Duong STPM | 4328 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 1 | 1240000 | NB for MP P26 | P26 | CGY4 | FATP | MP | 2026-04-20 | 35 | 2026-04-23 | 38 | 50 | 2026-03-04 | 2026-05-05 | Late | New Buy | G | Done | FATP-MP-CGY4-MVA2603-21OM | Done | 1FSHQ30277 | Done | 1FSHQ30277 |  | Đã nhận 10.4 | EPR2603210021 |  | Lấy OM stock trước / Mua bù sau / 1FSHQ30277x: Đã nhận 1x | 1 | 1 | 1 | 1
2026-03-16 | ENG1 | Ngo Van Duong | v1523845 | Kelvin Duong STPM | 4328 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 1 | 13888000 | NB for MP P26 | P26 | 4CS4 | FATP | MP | 2026-04-20 | 35 | 2026-04-23 | 38 | 50 | 2026-03-04 | 2026-05-05 | Late | New Buy | G | Done | FATP-MP-4CS4-MVA2603-19OM | Done | 1FSHQ30274 | Done | 1FSHQ30274 |  | Đã nhận 09.4 | EPR2603210022 |  | Lấy OM stock trước / Mua bù sau / 1FSHQ30274x: Đã nhận được hàng | 1 | 1 | 1 | 1
2026-03-16 | ENG1 | Ngo Van Duong | v1523845 | Kelvin Duong STPM | 4328 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 1 | 13888000 | NB for MP P26 | P26 | PKK4 | FATP | MP | 2026-04-20 | 35 | 2026-04-23 | 38 | 50 | 2026-03-04 | 2026-05-05 | Late | New Buy | G | Done | FATP-MP-PKK4-MVA2603-20OM | Done | 1FSHQ30276 | Done | 1FSHQ30276 |  | Đã nhận 09.4 | EPR2603210024 |  | Lấy OM stock trước / Mua bù sau / 1FSHQ30276x: Đã nhận hàng | 1 | 1 | 1 | 1
2026-03-16 | ENG1 | Ngo Van Duong | v1523845 | Kelvin Duong STPM | 4328 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 1 | 13888000 | NB for MP P26 | P26 | CGY4 | FATP | MP | 2026-04-20 | 35 | 2026-04-23 | 38 | 50 | 2026-03-04 | 2026-05-05 | Late | New Buy | G | Done | FATP-MP-CGY4-MVA2603-21OM | Done | 1FSHQ30278 | Done | 1FSHQ30278 |  | Đã nhận 09.4 | EPR2603210026: Done |  | Lấy OM stock trước / Mua bù sau / 1FSHQ30278x: Đã nhận hàng | 1 | 1 | 1 | 1
2026-03-16 | GG-PQE | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 21 | 26040000 | Service MP 4CS4 | P26 Service line | 4CS4 | FATP | MP | 2026-04-20 | 35 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | Q | Done | FATP-SV-4CS4-MVA2603-39OM | Done | 1FSHQ40064 | Done | 1FSHQ40064 | 2026-06-17 | 2026-06-20 | EPR2603240006 |  |  | 21 | 21 | 21 | 21
2026-03-16 | GG-PQE | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 19 | 62700000 | Service MP 4CS4 | P26 Service line | 4CS4 | FATP | MP | 2026-04-20 | 35 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | Q | Done | FATP-SV-4CS4-MVA2603-39OM | Done | VNPR202604060057 | Done | VNPO202604150088 | 2026-06-20 | 2026-06-20 | EPR2603210036 |  |  | 19 | 19 | 19 | 19
2026-03-16 | GG-PQE | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 21 | 291648000 | Service MP 4CS4 | P26 Service line | 4CS4 | FATP | MP | 2026-04-20 | 35 | 2026-05-04 | 49 | 50 | 2026-03-15 |  | Late | New Buy | Q | Done | FATP-SV-4CS4-MVA2603-39OM | Done | 1FSHQ40065 | Done | 1FSHQ40065 |  | Đã nhận 17.04 | EPR2603240004 |  | đã out | 21 | 21 | 21 | 21
2026-03-16 | GG-PQE | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 21 | 26040000 | Service MP CGY4 | P26 Service line | CGY4 | FATP | MP | 2026-04-20 | 35 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | Q | Done | FATP-SV-CGY4-MVA2603-40OM | Done | 1FSHQ40066 | Done | 1FSHQ40066 |  | 2026-05-12 | EPR2603240005 |  | đã out | 21 | 21 | 21 | 21
2026-03-16 | GG-PQE | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 19 | 62700000 | Service MP CGY4 | P26 Service line | CGY4 | FATP | MP | 2026-04-20 | 35 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | Q | Done | FATP-SV-CGY4-MVA2603-40OM | Done | VNPR202604060058 | Done | VNPO202604150088 | 2026-06-20 | 2026-06-20 | EPR2603210037 |  |  | 19 | 19 | 19 | 19
2026-03-16 | GG-PQE | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 21 | 291648000 | Service MP CGY4 | P26 Service line | CGY4 | FATP | MP | 2026-04-20 | 35 | 2026-05-04 | 49 | 50 | 2026-03-15 |  | Late | New Buy | Q | Done | FATP-SV-CGY4-MVA2603-40OM | Done | 1FSHQ40067 | Done | 1FSHQ40067 |  | Đã nhận 17.04 | EPR2603240001 |  | đã out | 21 | 21 | 21 | 21
2026-03-16 | GG-PQE | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 21 | 26040000 | Service MP PKK4 | P26 Service line | PKK4 | FATP | MP | 2026-04-20 | 35 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | Q | Done | FATP-SV-PKK4-MVA2603-41OM | Done | 1FSHQ40069 | Done | 1FSHQ40069 | 2026-06-17 | 2026-06-20 | EPR2603240002 |  |  | 21 | 21 | 21 | 21
2026-03-16 | GG-PQE | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 20 | 66000000 | Service MP PKK4 | P26 Service line | PKK4 | FATP | MP | 2026-04-20 | 35 | 2026-05-04 | 49 | 50 | 2026-03-15 | 2026-05-05 | Late | New Buy | Q | Done | FATP-SV-PKK4-MVA2603-41OM | Done | VNPR202604060063 | Done | VNPO202604150088 | 2026-06-20 | 2026-06-20 | EPR2603210038 |  |  | 20 | 20 | 20 | 20
2026-03-16 | GG-PQE | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 21 | 291648000 | Service MP PKK4 | P26 Service line | PKK4 | FATP | MP | 2026-04-20 | 35 | 2026-05-04 | 49 | 50 | 2026-03-15 |  | Late | New Buy | Q | Done | FATP-SV-PKK4-MVA2603-41OM | Done | 1FSHQ40070 | Done | 1FSHQ40070 |  | Đã nhận 17.04 | EPR2603240003 |  | đã out | 21 | 21 | 21 | 21
2026-03-17 | TE | Nguyen Ngoc Huyen | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | Mini PC ASUS NUC 14 Essential NUC14MNK150 (TE P26 MP ONLY) | #N/A | 9680000 | 26 | 251680000 | P26 SMT MP 4CS4 | P26 | 4CS4 | SMT | MP | 2026-04-20 | 34 | 2026-04-23 | 37 |  | 2026-04-23 | 2026-03-17 | On time | New Buy |  | Done | SMT-MP-4CS4-MVA2603-34OM | Done | 1FSHQ30271 | Done | 1FSHQ30271 |  | Đã nhận 16.4 | EPR2603240038 |  |  | 26 | 26 | 26 | 26
2026-03-17 | TE | Nguyen Ngoc Huyen | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | Mini PC ASUS NUC 14 Essential NUC14MNK150 (TE P26 MP ONLY) | #N/A | 9680000 | 22 | 212960000 | P26 SMT MP CGY4 | P26 | CGY4 | SMT | MP | 2026-04-20 | 34 | 2026-04-23 | 37 |  | 2026-04-23 | 2026-03-17 | On time | New Buy |  | Done | SMT-MP-CGY4-MVA2603-35OM | Done | 1FSHQ30272 | Done | 1FSHQ30272 |  | Đã nhận 16.4 | EPR2603240039 |  |  | 22 | 22 | 22 | 22
2026-03-18 | TE | Nguyen Ngoc Huyen | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | Mini PC ASUS NUC 14 Essential NUC14MNK150 (TE P26 MP ONLY) | #N/A | 9680000 | 1 | 9680000 | P26 FATP MP 4CS4 | P26 | 4CS4 | FATP | MP | 2026-04-20 | 33 | 2026-04-23 | 36 |  | 2026-04-23 | 2026-03-18 | On time | New Buy | G | Done | FATP-MP-4CS4-MVA2603-48OM | Done | 1FSHQ30252 | Done | 1FSHQ30252 |  | Đã nhận 16.4 | EPR2603240040 |  |  | 1 | 1 | 1 | 1
2026-03-18 | TE | Nguyen Ngoc Huyen | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | Mini PC ASUS NUC 14 Essential NUC14MNK150 (TE P26 MP ONLY) | #N/A | 9680000 | 1 | 9680000 | P26 FATP MP CGY4 | P26 | CGY4 | FATP | MP | 2026-04-20 | 33 | 2026-04-23 | 36 |  | 2026-04-23 | 2026-03-18 | On time | New Buy | G | Done | FATP-MP-CGY4-MVA2603-49OM | Done | 1FSHQ30254 | Done | 1FSHQ30254 |  | Đã nhận 16.4 | EPR2603240041 |  |  | 1 | 1 | 1 | 1
2026-03-25 | ENG2 | Đỗ Thị Xuân | V1536196 | xuandt99@fih-foxconn.com | 4347 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 1 | 1240000 | P26 FATP MP 4CS4 Service line | P26 Service line | 4CS4 | FATP | MP | 2026-04-20 | 26 | 2026-05-04 | 40 | 50 | 2026-03-15 | 2026-05-14 | Late | New Buy | G | Done | FATP-SV-4CS4-MVA2603-56OM | Done | 1FSHQ40047 | Done | 1FSHQ40047 |  |  | EPR2603280003 |  |  | 1 | 1 | 1 | 0
2026-03-25 | ENG2 | Đỗ Thị Xuân | V1536196 | xuandt99@fih-foxconn.com | 4347 | Mini PC (Assy) | #N/A | 7800000 | 1 | 7800000 | P26 FATP MP 4CS4 Service line | P26 Service line | 4CS4 | FATP | MP | 2026-04-20 | 26 | 2026-05-04 | 40 |  | 2026-05-04 | 2026-03-25 | On time | New Buy | G | Done | FATP-SV-4CS4-MVA2603-56OM | Done | 1FSHQ40048 | Pending |  |  |  | EPR2603280004 (cancel) |  | Bác L bảo bỏ qua tạm thời | 1 | 1 | 0 | 0
2026-03-25 | ENG2 | Đỗ Thị Xuân | V1536196 | xuandt99@fih-foxconn.com | 4347 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 1 | 1240000 | P26 FATP MP CGY4Service line | P26 Service line | CGY4 | FATP | MP | 2026-04-20 | 26 | 2026-05-04 | 40 | 50 | 2026-03-15 | 2026-05-14 | Late | New Buy | G | Done | FATP-SV-CGY4-MVA2603-57OM | Done | 1FSHQ40049 | Done | 1FSHQ40049 |  |  | EPR2603280005 |  |  | 1 | 1 | 1 | 0
2026-03-25 | ENG2 | Đỗ Thị Xuân | V1536196 | xuandt99@fih-foxconn.com | 4347 | Mini PC (Assy) | #N/A | 7800000 | 1 | 7800000 | P26 FATP MP CGY4Service line | P26 Service line | CGY4 | FATP | MP | 2026-04-20 | 26 | 2026-05-04 | 40 |  | 2026-05-04 | 2026-03-25 | On time | New Buy | G | Done | FATP-SV-CGY4-MVA2603-57OM | Done | 1FSHQ40050 | Pending |  |  |  | EPR2603280006 (cancel) |  | Bác L bảo bỏ qua tạm thời | 1 | 1 | 0 | 0
2026-03-25 | ENG2 | Đỗ Thị Xuân | V1536196 | xuandt99@fih-foxconn.com | 4347 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 1 | 1240000 | P26 FATP MP PKK4Service line | P26 Service line | PKK4 | FATP | MP | 2026-04-20 | 26 | 2026-05-04 | 40 | 50 | 2026-03-15 | 2026-05-14 | Late | New Buy | G | Done | FATP-SV-PKK4-MVA2603-58OM | Done | 1FSHQ40052 | Done | 1FSHQ40052 |  |  | EPR2603280007 |  |  | 1 | 1 | 1 | 0
2026-03-25 | ENG2 | Đỗ Thị Xuân | V1536196 | xuandt99@fih-foxconn.com | 4347 | Mini PC (Assy) | #N/A | 7800000 | 1 | 7800000 | P26 FATP MP PKK4Service line | P26 Service line | PKK4 | FATP | MP | 2026-04-20 | 26 | 2026-05-04 | 40 |  | 2026-05-04 | 2026-03-25 | On time | New Buy | G | Done | FATP-SV-PKK4-MVA2603-58OM | Done | 1FSHQ40053 | Pending |  |  |  | EPR2603280008 (cancel) |  | Bác L bảo bỏ qua tạm thời | 1 | 1 | 0 | 0
2026-03-26 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 10 | 267520000 | P26 SMT service PKK4 | P26 Service line | PKK4 | SMT | MP | 2026-04-20 | 25 | 2026-04-23 | 28 | 70 | 2026-02-12 |  | Late | New Buy | G | Done | SMT-SV-PKK4-MVA2603-61OM | Done | 1FSHQ40073 | Done | 1FSHQ40073 |  | Đã nhận 16.4 | EPR2603280009 |  |  | 10 | 10 | 10 | 10
2026-03-26 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 10 | 267520000 | P26 SMT service CGY4 | P26 Service line | CGY4 | SMT | MP | 2026-04-20 | 25 | 2026-04-23 | 28 | 70 | 2026-02-12 |  | Late | New Buy | G | Done | SMT-SV-CGY4-MVA2603-60OM | Done | 1FSHQ40072 | Done | 1FSHQ40072 |  | Đã nhận 16.4 | EPR2603280010 |  |  | 10 | 10 | 10 | 10
2026-03-26 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | IPC++(updated) | L10-MP-OR5-MVA2601-105OM | 26752000 | 10 | 267520000 | P26 SMT service 4CS4 | P26 Service line | 4CS4 | SMT | MP | 2026-04-20 | 25 | 2026-04-23 | 28 | 70 | 2026-02-12 |  | Late | New Buy | G | Done | SMT-SV-4CS4-MVA2603-59OM | Done | 1FSHQ40071 | Done | 1FSHQ40071 |  | Đã nhận 16.4 | EPR2603280011 |  |  | 10 | 10 | 10 | 10
2026-03-26 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 2 | 6600000 | P26 SMT service PKK4 | P26 Service line | PKK4 | SMT | MP | 2026-04-20 | 25 | 2026-04-23 | 28 | 50 | 2026-03-04 | 2026-05-15 | Late | New Buy | G | Done | SMT-SV-PKK4-MVA2603-61OM | Done | VNPR202604060080 | Done | VNPO202604110046 | Dự kiến 07/05 hàng về | 2026-05-07 | EPR2603280012 |  |  | 2 | 2 | 2 | 2
2026-03-26 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 2 | 6600000 | P26 SMT service CGY4 | P26 Service line | CGY4 | SMT | MP | 2026-04-20 | 25 | 2026-04-23 | 28 | 50 | 2026-03-04 | 2026-05-15 | Late | New Buy | G | Done | SMT-SV-CGY4-MVA2603-60OM | Done | VNPR202604060079 | Done | VNPO202604110046 | Dự kiến 07/05 hàng về | 2026-05-07 | EPR2603280013 |  |  | 2 | 2 | 2 | 2
2026-03-26 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 2 | 6600000 | P26 SMT service 4CS4 | P26 Service line | 4CS4 | SMT | MP | 2026-04-20 | 25 | 2026-04-23 | 28 | 50 | 2026-03-04 | 2026-05-15 | Late | New Buy | G | Done | SMT-SV-4CS4-MVA2603-59OM | Done | VNPR202604060075 | Done | VNPO202604110046 | Dự kiến 07/05 hàng về | 2026-05-07 | EPR2603280014 |  |  | 2 | 2 | 2 | 2
2026-03-30 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 3 | 5940000 | P26 MP | P26 | PKK4 | FATP | MP | 2026-04-30 | 31 | 2026-04-23 | 24 | 50 | 2026-03-04 | 2026-05-19 |  | New Buy | L | Done | FATP-MP-PKK4-MVA2603-71OM | Done | 1FSHQ40136 | Done | 1FSHQ40136 |  | Đã nhận 29.04 | EPR2604140009 |  |  | 3 | 3 | 3 | 3
2026-03-30 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 3 | 56151000 | P26 MP | P26 | PKK4 | FATP | MP | 2026-04-30 | 31 | 2026-04-23 | 24 | 70 | 2026-02-12 | 2026-06-08 | Late | New Buy | L | Done | FATP-MP-PKK4-MVA2603-71OM | Done | 1FSHQ40137 | Done | 1FSHQ40137 |  | Đã nhận 23/04 | EPR2604140010 |  |  | 3 | 3 | 3 | 3
2026-03-30 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 4 | 7920000 | P26 MP | P26 | CGY4 | FATP | MP | 2026-04-30 | 31 | 2026-04-23 | 24 | 50 | 2026-03-04 | 2026-05-19 | Late | New Buy | L | Done | FATP-MP-CGY4-MVA2603-70OM | Done | 1FSHQ40134 | Done | 1FSHQ40134 |  | Đã nhận 29.04 | EPR2604140011 |  |  | 4 | 4 | 4 | 4
2026-03-30 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 5 | 93585000 | P26 MP | P26 | CGY4 | FATP | MP | 2026-04-30 | 31 | 2026-04-23 | 24 | 70 | 2026-02-12 | 2026-06-08 | Late | New Buy | L | Done | FATP-MP-CGY4-MVA2603-70OM | Done | 1FSHQ40135 | Done | 1FSHQ40135 |  | Đã nhận 23/04 | EPR2604140012 |  |  | 5 | 5 | 5 | 5
2026-03-30 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 5 | 9900000 | P26 MP | P26 | 4CS4 | FATP | MP | 2026-04-30 | 31 | 2026-04-23 | 24 | 50 | 2026-03-04 | 2026-05-19 | Late | New Buy | L | Done | FATP-MP-4CS4-MVA2603-69OM | Done | 1FSHQ40132 | Done | 1FSHQ40132 |  | Đã nhận 29.04 | EPR2604140013 |  |  | 5 | 5 | 5 | 5
2026-03-30 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 4 | 74868000 | P26 MP | P26 | 4CS4 | FATP | MP | 2026-04-30 | 31 | 2026-04-23 | 24 | 70 | 2026-02-12 | 2026-06-08 | Late | New Buy | L | Done | FATP-MP-4CS4-MVA2603-69OM | Done | 1FSHQ40133 | Done | 1FSHQ40133 |  | Đã nhận 23/04 | EPR2604140014 |  |  | 4 | 4 | 4 | 4
2026-03-30 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | Printer GODEX | GODEX GX4600i pro, 600dpi | 31150000 | 2 | 62300000 | P26 MP | P26 | PKK4 | FATP | MP | 2026-04-30 | 31 | 2026-04-23 | 24 | 48 | 2026-03-06 | 2026-05-17 | Late | New Buy | L | Done | L10-MP-PKK4-MVA2604-17OM | Done | 1FSHQ40297 | Done | 1FSHQ40297 | 2026-05-05 | 2026-05-05 | EPR2605060002 |  |  | 2 | 2 | 2 | 2
2026-03-30 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | Printer GODEX | GODEX GX4600i pro, 600dpi | 31150000 | 2 | 62300000 | P26 MP | P26 | CGY4 | FATP | MP | 2026-04-30 | 31 | 2026-04-23 | 24 | 48 | 2026-03-06 | 2026-05-17 | Late | New Buy | L | Done | L10-MP-CGY4-MVA2604-16OM | Done | 1FSHQ40310 | Done | 1FSHQ40310 | 2026-05-05 | 2026-05-05 | EPR2605060003 |  |  | 2 | 2 | 2 | 2
2026-03-30 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | Printer GODEX | GODEX GX4600i pro, 600dpi | 31150000 | 2 | 62300000 | P26 MP | P26 | 4CS4 | FATP | MP | 2026-04-30 | 31 | 2026-04-23 | 24 | 48 | 2026-03-06 | 2026-05-17 | Late | New Buy | L | Done | L10-MP-4CS4-MVA2604-15OM | Done | 1FSHQ40296 | Done | 1FSHQ40296 | 2026-05-05 | 2026-05-05 | EPR2605060004 |  |  | 2 | 2 | 2 | 2
2026-03-31 | ENG3 | Phạm Van Hùng | V1544999 | hungpv3@fih-foxconn.com | 4500 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 3 | 56151000 | PC for Auto charging machine P26 | P26 | 4CS4 | FATP | MP | 2026-04-14 | 14 | 2026-04-23 | 23 | 70 | 2026-02-12 | 2026-06-09 | Late | New Buy | G | Done | FATP-MP-4CS4-MVA2603-74AUTO | Done | 1FSHQ40198 | Done | 1FSHQ40198 |  | 2026-05-07 | EPR2605040001 |  |  | 3 | 3 | 3 | 3
2026-03-31 | ENG3 | Phạm Van Hùng | V1544999 | hungpv3@fih-foxconn.com | 4500 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 3 | 56151000 | PC for Auto charging machine P26 | P26 | PKK4 | FATP | MP | 2026-04-14 | 14 | 2026-04-23 | 23 | 70 | 2026-02-12 | 2026-06-09 | Late | New Buy | G | Done | FATP-MP-PKK4-MVA2603-75AUTO | Done | 1FSHQ40199 | Done | 1FSHQ40199 |  | 2026-05-07 | EPR2605040002 |  |  | 3 | 3 | 3 | 3
2026-03-31 | ENG3 | Phạm Van Hùng | V1544999 | hungpv3@fih-foxconn.com | 4500 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 3 | 56151000 | PC for Auto charging machine P26 | P26 | CGY4 | FATP | MP | 2026-04-14 | 14 | 2026-04-23 | 23 | 70 | 2026-02-12 | 2026-06-09 | Late | New Buy | G | Done | FATP-MP-CGY4-MVA2603-76AUTO | Done | 1FSHQ40200 | Done | 1FSHQ40200 |  | 2026-05-07 | EPR2605040003 |  |  | 3 | 3 | 3 | 3
2026-03-31 | ENG1 | Nguyễn Đức Hưng | V1538465 | Hung Nguyen Duc |  | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 1 | 15500000 | P26 service | P26 Service line | 4CS4 | FATP | MP | 2026-05-15 | 45 | 2026-05-04 | 34 | 65 | 2026-02-28 | 2026-06-04 | Late | New Buy | G | Done | FATP-SV-P26-MVA2604-03OM | Done | VNPR202604150121 | Done | VNPO202604200198 | 2026-05-29 | 2026-05-30 | EPR2605040004 |  |  | 1 | 1 | 1 | 1
2026-03-24 | REL | Đường Kim Quy | V1538557 | quydk@fih-foxconn.com | 4337 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 4 | 4,960,000 ₫ | P1 for P27 | P27 | KSH5 | FATP | P1.0 | 2026-03-24 | 0 | 2026-05-18 | 55 | 50 | 2026-03-29 | 2026-05-13 | On time | New Buy |  | Done | FATP-NPI-P27-MVA2603-53OM | Done | 1FSHQ40011 | Done | 1FSHQ40011 |  | 2026-05-12 | EPR2603240042 |  | ( Lấy 2x màn ở 1FSHQ30275 & 1FSHQ30277 + 2x spare trong kho OM) => Xuất trước & hàng 1FSHQ40011 làm sapre | 4 | 4 | 4 | 4
2026-03-24 | REL | Đường Kim Quy | V1538557 | quydk@fih-foxconn.com | 4337 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 2 | 37,434,000 ₫ | P1 for P27 | P27 | KSH5 | FATP | P1.0 | 2026-03-24 | 0 | 2026-05-18 | 55 | 70 | 2026-03-09 | 2026-06-02 | Late | New Buy |  | Done | FATP-NPI-P27-MVA2603-53OM | Done | 1FSHQ40197 | Pending | 1FSHQ40197 |  | 2026-05-07 | EPR2603240043 |  | đã out | 2 | 2 | 0 | 2
2026-03-24 | REL | Đường Kim Quy | V1538557 | quydk@fih-foxconn.com | 4337 | Monitor VA2432-MHD-3, 24 inch Full HD | VIEWSONIC VA2432-MHD-3, 24 inch Full HD, 3Yrs | 1970000 | 3 | 5,910,000 ₫ | P1 for P27 | P27 | KSH5 | FATP | P1.0 | 2026-03-24 | 0 | 2026-05-18 | 55 | 50 | 2026-03-29 |  | On time | New Buy |  | Done | FATP-NPI-P27-MVA2603-53OM | Done | 1FSHQ40013 | Done | 1FSHQ40013 |  | 2026-04-14 | EPR2604090002 |  | đã out | 3 | 3 | 3 | 3
2026-03-31 | ENG1 | Nguyễn Đức Hưng | V1538465 | Hung Nguyen Duc |  | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 7 | 341,600,000 ₫ | P25 service | P25 Service line | MT5 | FATP | MP | 2026-05-15 | 45 | #N/A | #N/A | 50 | #N/A | 2026-05-20 | #N/A | New Buy | G | Done | L10-MP-P25-MVA2604-02OM => FATP-SV-P25-MVA2604-02OM | Done | 1FSHQ40168 | Done | 1FSHQ40168 | pending | Lấy hàng trong kho trả request trước | EPR2605040005 |  |  | 7 | 7 | 7 | 7
2026-03-31 | ENG1 | Nguyễn Đức Hưng | V1538465 | Hung Nguyen Duc |  | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 1 | 15,500,000 ₫ | P25 service | P25 Service line | MT5 | FATP | MP | 2026-05-15 | 45 | #N/A | #N/A | 65 | #N/A | 2026-06-04 | #N/A | New Buy | G | Done | L10-MP-P25-MVA2604-02OM => FATP-SV-P25-MVA2604-02OM | Done | VNPR202604150120 | Done | VNPO202604200198 | 2026-05-29 | 2026-05-30 | EPR2605040006 |  |  | 1 | 1 | 1 | 1
2026-02-12 | ENG1 | ENG 1 - GIANG OM |  |  | 23683 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 1 | 3300000 | Mua bù 1x ENG1 | P26 | 4CS4 | FATP | DVT | 2026-03-31 | 47 | 2026-02-23 | 11 | 50 | 2026-01-04 | 2026-04-03 | Late | New Buy | G | Done | FATP-MP-4CS4-MVA2603-50OM | Done | VNPR202604060081 | Done | VNPO202604130136 | Dự kiến 07/05 hàng về | 2026-05-07 | x |  |  | 1 | 1 | 1 | 1
2026-02-12 | ENG1 | ENG 1 - GIANG OM |  |  | 23683 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 1 | 3300000 | Mua bù 1x ENG1 | P26 | PKK4 | FATP | DVT | 2026-03-31 | 47 | 2026-02-23 | 11 | 50 | 2026-01-04 | 2026-04-03 | Late | New Buy | G | Done | FATP-MP-PKK4-MVA2603-51OM | Done | VNPR202604060084 | Done | VNPO202604130136 | Dự kiến 07/05 hàng về | 2026-05-07 | x |  |  | 1 | 1 | 1 | 1
2026-03-08 | QA G -PQC | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 33 | 40920000 | MP line 3 | P26 | 4CS4 | FATP | MP | 2026-04-16 | 39 | 2026-04-23 | 46 | 50 | 2026-03-04 | 2026-04-27 | Late | New Buy | G | Done | FATP-MP-4CS4-MVA2603-26OM | Done | 1FSHQ40045 | Done | 1FSHQ40045 | 2026-06-17 | 2026-06-20 | EPR2603210047 |  |  | 33 | 33 | 33 | 33
2026-03-08 | QA G -PQC | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 26 | 85800000 | MP line 3 | P26 | 4CS4 | FATP | MP | 2026-04-16 | 39 | 2026-04-23 | 46 | 50 | 2026-03-04 | 2026-04-27 | Late | New Buy | G | Done | FATP-MP-4CS4-MVA2603-26OM | Done | VNPR202604040088 | Done | VNPO202604160163 | 2026-06-20 | 2026-06-20 | EPR2603210015 |  |  | 26 | 26 | 26 | 26
2026-03-08 | QA G -PQC | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 33 | 458304000 | MP line 3 | P26 | 4CS4 | FATP | MP | 2026-04-16 | 39 | 2026-04-23 | 46 | 50 | 2026-03-04 | 2026-04-27 | Late | New Buy | G | Done | FATP-MP-4CS4-MVA2603-26OM | Done | 1FSHQ40046 | Done | 1FSHQ40046 |  | Đã nhận | EPR2603210048 |  | ( Phát trước 9x từ : 1FSHQ30125 & 1FSHQ30127) // ( Lấy tiếp 3x từ 3 PO: 1FSHQ30274,EPR2603210048,1FSHQ30278) | 33 | 33 | 33 | 33
2026-03-08 | QA G -PQC | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 38 | 47120000 | MP line 3 | P26 | CGY4 | FATP | MP | 2026-04-16 | 39 | 2026-04-23 | 46 | 50 | 2026-03-04 | 2026-04-27 | Late | New Buy | G | Done | FATP-MP-CGY4-MVA2603-27OM | Done | 1FSHQ40007 | Done | 1FSHQ40007 | Dự kiến 29/04 |  | EPR2603210049 |  |  | 38 | 38 | 38 | 0
2026-03-08 | QA G -PQC | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 31 | 102300000 | MP line 3 | P26 | CGY4 | FATP | MP | 2026-04-16 | 39 | 2026-04-23 | 46 | 50 | 2026-03-04 | 2026-04-27 | Late | New Buy | G | Done | FATP-MP-CGY4-MVA2603-27OM | Done | VNPR202604010055 | Done | VNPO202604070280 |  | 2026-05-07 | EPR2603210016 |  |  | 31 | 31 | 31 | 31
2026-03-08 | QA G -PQC | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 38 | 527744000 | MP line 3 | P26 | CGY4 | FATP | MP | 2026-04-16 | 39 | 2026-04-23 | 46 | 50 | 2026-03-04 | 2026-04-27 | Late | New Buy | G | Done | FATP-MP-CGY4-MVA2603-27OM | Done | 1FSHQ40009 | Done | 1FSHQ40009 |  | Đã nhận | EPR2603210050 |  |  | 38 | 38 | 38 | 38
2026-03-17 | ENG2 | Đỗ Thị Xuân | V1536196 | xuandt99@fih-foxconn.com | 4347 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 12 | 14880000 | MP line 3 | P26 | 4CS4 | FATP | MP | 2026-04-20 | 34 | 2026-04-23 | 37 | 50 | 2026-03-04 | 2026-05-06 | Late | New Buy | G | Done | FATP-MP-4CS4-MVA2603-45OM | Done | 1FSHQ30255 | Done | 1FSHQ30255 |  | 2026-05-12 | EPR2603240007 |  |  | 12 | 12 | 12 | 12
2026-03-17 | ENG2 | Đỗ Thị Xuân | V1536196 | xuandt99@fih-foxconn.com | 4347 | Mini PC (Assy) | #N/A | 7800000 | 12 | 93600000 | MP line 3 | P26 | 4CS4 | FATP | MP | 2026-04-20 | 34 | 2026-04-23 | 37 |  | 2026-04-23 | 2026-03-17 | On time | New Buy | G | Done | FATP-MP-4CS4-MVA2603-45OM | Done | 1FSHQ30258 | Done | 1FSHQ30258 | pending |  | EPR2603240008 |  | Bác L bảo bỏ qua tạm thời | 12 | 12 | 12 | 0
2026-03-17 | ENG2 | Đỗ Thị Xuân | V1536196 | xuandt99@fih-foxconn.com | 4347 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 12 | 14880000 | MP line 3 | P26 | CGY4 | FATP | MP | 2026-04-20 | 34 | 2026-04-23 | 37 | 50 | 2026-03-04 | 2026-05-06 | Late | New Buy | G | Done | FATP-MP-CGY4-MVA2603-46OM | Done | 1FSHQ30253 | Done | 1FSHQ30253 |  | 2026-05-12 | EPR2603240009 |  |  | 12 | 12 | 12 | 12
2026-03-17 | ENG2 | Đỗ Thị Xuân | V1536196 | xuandt99@fih-foxconn.com | 4347 | Mini PC (Assy) | #N/A | 7800000 | 12 | 93600000 | MP line 3 | P26 | CGY4 | FATP | MP | 2026-04-20 | 34 | 2026-04-23 | 37 |  | 2026-04-23 | 2026-03-17 | On time | New Buy | G | Done | FATP-MP-CGY4-MVA2603-46OM | Done | 1FSHQ30256 | Done | 1FSHQ30256 | pending |  | EPR2603240010 |  | Bác L bảo bỏ qua tạm thời | 12 | 12 | 12 | 0
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 93 | 115320000 | Proto (KSH5) | P27 | KSH5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 | 50 | 2026-03-29 | 2026-05-14 | On time | New Buy | L | Done | FATP-NPI-KSH5-MVA2603-64OM | Done | 1FSHQ40120 | Done | 1FSHQ40120 | pending |  | EPR2603280015 |  |  | 93 | 93 | 93 | 0
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Mini PC (Assy) | #N/A | 7800000 | 93 | 725400000 | Proto (KSH5) | P27 | KSH5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 |  | 2026-05-18 | 2026-03-25 | On time | New Buy | L | Done | FATP-NPI-KSH5-MVA2603-64OM => FATP-MP-P26-MVA2605-27OM (140x) | Done | 1FSHQ40121 => 1FSHQ50258 | Done | 1FSHQ50258 |  |  | EPR2603280016 (CANCEL) // EPR2605290001 140 |  |  | 93 | 93 | 93 | 0
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 68 | 156400000 | Proto (KSH5) | P27 | KSH5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 | 50 | 2026-03-29 | 2026-05-14 | On time | New Buy | L | Done | FATP-NPI-KSH5-MVA2603-64OM | Done | VNPR202604110006 | Done | VNPO202604150030 | 2026-05-25 | 2026-05-25 | EPR2603280017 |  |  | 68 | 68 | 68 | 68
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 6 | 19800000 | Proto (KSH5) | P27 | KSH5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 | 50 | 2026-03-29 | 2026-05-14 | On time | New Buy | L | Done | FATP-NPI-KSH5-MVA2603-64OM | Done | VNPR202604110006 | Done | VNPO202604150030 |  | 2026-05-07 | EPR2603280018 | Lấy hàng kho từ chỗ 60x HDP OR out trước | chưa out | 6 | 6 | 6 | 6
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 15 | 732000000 | Proto (KSH5) | P27 | KSH5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 | 50 | 2026-03-29 | 2026-05-14 | On time | New Buy | L | Done | FATP-NPI-KSH5-MVA2603-64OM | Done | 1FSHQ40122 | Done | 1FSHQ40122 | pending |  | EPR2603280019 |  |  | 15 | 15 | 15 | 0
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 93 | 115320000 | Proto (ASK5) | P27 | ASK5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 | 50 | 2026-03-29 | 2026-05-14 | On time | New Buy | L | Done | FATP-NPI-ASK5-MVA2603-65OM | Done | 1FSHQ40123 | Done | 1FSHQ40123 |  | 2026-05-15 | EPR2603300001 |  | chưa out | 93 | 93 | 93 | 93
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Mini PC (Assy) | #N/A | 7800000 | 93 | 725400000 | Proto (ASK5) | P27 | ASK5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 |  | 2026-05-18 | 2026-03-25 | On time | New Buy | L | Done | FATP-NPI-ASK5-MVA2603-65OM => FATP-MP-P26-MVA2605-27OM (140x) | Done | 1FSHQ40124 => 1FSHQ50258 | Done | 1FSHQ50258 |  |  | EPR2603300002 (CANCEL) // EPR2605290001 140 |  |  | 93 | 93 | 93 | 0
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 75 | 172500000 | Proto (ASK5) | P27 | ASK5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 | 50 | 2026-03-29 | 2026-05-14 | On time | New Buy | L | Done | FATP-NPI-ASK5-MVA2603-65OM | Done | VNPR202604110028 | Done | VNPO202604150030 | 2026-05-25 | 2026-05-25 | EPR2604140001 |  |  | 75 | 75 | 75 | 75
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 6 | 19800000 | Proto (ASK5) | P27 | ASK5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 | 50 | 2026-03-29 | 2026-05-14 | On time | New Buy | L | Done | FATP-NPI-ASK5-MVA2603-65OM | Done | VNPR202604110028 | Done | VNPO202604150030 |  | 2026-05-07 | EPR2604140002 | Lấy hàng kho từ chỗ 60x HDP OR out trước | chưa out - đã GI GR | 6 | 6 | 6 | 6
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 18 | 878400000 | Proto (ASK5) | P27 | ASK5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 | 50 | 2026-03-29 | 2026-05-14 | On time | New Buy | L | Done | FATP-NPI-ASK5-MVA2603-65OM | Done | 1FSHQ40125 | Done | 1FSHQ40125 | pending |  | EPR2604140003 |  |  | 18 | 18 | 18 | 0
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 92 | 114080000 | Proto (WGO5)) | P27 | WGO5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 | 50 | 2026-03-29 | 2026-05-14 | On time | New Buy | L | Done | FATP-NPI-WGO5-MVA2603-66OM | Done | 1FSHQ40126 | Done | 1FSHQ40126 |  | 2026-05-15 | EPR2604140004 |  | chưa out | 92 | 92 | 92 | 92
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Mini PC (Assy) | #N/A | 7800000 | 92 | 717600000 | Proto (WGO5)) | P27 | WGO5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 |  | 2026-05-18 | 2026-03-25 | On time | New Buy | L | Done | FATP-NPI-WGO5-MVA2603-66OM => FATP-MP-P26-MVA2605-27OM (140x) | Done | 1FSHQ40127 => 1FSHQ50258 | Done | 1FSHQ50258 |  |  | EPR2604140005 (CANCEL) // EPR2605290001 140 |  |  | 92 | 92 | 92 | 0
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 72 | 165600000 | Proto (WGO5)) | P27 | WGO5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 | 50 | 2026-03-29 | 2026-05-14 | On time | New Buy | L | Done | FATP-NPI-WGO5-MVA2603-66OM | Done | VNPR202604110030 | Done | VNPO202604150030 | 2026-05-25 | 2026-05-25 | EPR2604140006 |  |  | 72 | 72 | 72 | 72
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 6 | 19800000 | Proto (WGO5)) | P27 | WGO5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 | 50 | 2026-03-29 | 2026-05-14 | On time | New Buy | L | Done | FATP-NPI-WGO5-MVA2603-66OM | Done | VNPR202604110030 | Done | VNPO202604150030 |  | 2026-05-07 | EPR2604140007 | Lấy hàng kho từ chỗ 60x HDP OR out trước | chưa out | 6 | 6 | 6 | 6
2026-03-25 | MFG | To Thi Phuong Anh | V1524505 | Phuong Anh To |  | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 18 | 878400000 | Proto (WGO5)) | P27 | WGO5 | FATP | P1.0 | 2026-05-15 | 51 | 2026-05-18 | 54 | 50 | 2026-03-29 | 2026-05-14 | On time | New Buy | L | Done | FATP-NPI-WGO5-MVA2603-66OM | Done | 1FSHQ40128 | Done | 1FSHQ40128 | pending |  | EPR2604140008 |  |  | 18 | 18 | 18 | 0
2026-04-10 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 65 | 1738880000 | WGO5 SMT P1.0 | P27 | WGO5 | SMT | P1.0 |  | -46122 | 2026-05-16 | 36 | 70 | 2026-03-07 | 2026-06-19 | Late | New Buy | L | Done | SMT-NPI-WGO5-MVA2604-09OM | Done | 40x 1FSHQ40226 25X 1FSHQ40227 | Done | 25.0x 1FSHQ40227 40.0x 1FSHQ40226 |  | 2026-05-05 | EPR2605040007 |  | đã out | 65 | 65 | 65 | 65
2026-04-10 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 67 | 1792384000 | ASK5 SMT P1.0 | P27 | ASK5 | SMT | P1.0 |  | -46122 | 2026-05-16 | 36 | 70 | 2026-03-07 | 2026-06-19 | Late | New Buy | L | Done | SMT-NPI-ASK5-MVA2604-08OM | Done | 40x 1FSHQ40223 27X 1FSHQ40224 | Done | 40x 1FSHQ40223 27X 1FSHQ40224 |  | 2026-05-07 | EPR2605040008 |  | đã out | 67 | 67 | 67 | 67
2026-04-10 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 67 | 1792384000 | KSH5 SMT P1.0 | P27 | KSH5 | SMT | P1.0 |  | -46122 | 2026-05-16 | 36 | 70 | 2026-03-07 | 2026-06-19 | Late | New Buy | L | Done | SMT-NPI-KSH5-MVA2604-07OM | Done | 40X 1FSHQ40221 27X 1FSHQ40222 | Done | 40X 1FSHQ40221 27X 1FSHQ40222 |  | 2026-05-07 | EPR2605040009 |  | đã out | 67 | 67 | 67 | 67
2026-04-10 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 7 | 23100000 | WGO5 SMT P1.0 | P27 | WGO5 | SMT | P1.0 |  | -46122 | 2026-05-16 | 36 | 50 | 2026-03-27 | 2026-05-30 | Late | New Buy | L | Done | SMT-NPI-WGO5-MVA2604-09OM | Done | VNPR202604200109 | Done | VNPO202604230205 |  | 2026-06-20 | EPR2605040010 |  |  | 7 | 7 | 7 | 7
2026-04-10 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 7 | 23100000 | ASK5 SMT P1.0 | P27 | ASK5 | SMT | P1.0 |  | -46122 | 2026-05-16 | 36 | 50 | 2026-03-27 | 2026-05-30 | Late | New Buy | L | Done | SMT-NPI-ASK5-MVA2604-08OM | Done | VNPR202604200105 | Done | VNPO202604230205 |  | 2026-06-20 | EPR2605040011 |  |  | 7 | 7 | 7 | 7
2026-04-10 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 7 | 23100000 | KSH5 SMT P1.0 | P27 | KSH5 | SMT | P1.0 |  | -46122 | 2026-05-16 | 36 | 50 | 2026-03-27 | 2026-05-30 | Late | New Buy | L | Done | SMT-NPI-KSH5-MVA2604-07OM | Done | VNPR202604200101 | Done | VNPO202604230205 |  | 2026-06-20 | EPR2605040012 |  |  | 7 | 7 | 7 | 7
2026-03-16 | GG-PQE | Nguyen Anh Thai | V1544017 | Tommy - Thai Nguyen Anh (QE) | 24422 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 5 | 93585000 | MCN5 FATP Proto1 | F27 | MCN5 | FATP | P1.0 |  | -46097 | 2026-05-11 | 56 | 70 | 2026-03-02 |  | Late | New Buy | Q | Done | FATP-NPI-F27-MVA2603-31OM | Done | 1FSHQ40076 | Done | 1FSHQ40076 |  | Đã nhận | EPR2603240036 |  | đã out | 5 | 5 | 5 | 5
2026-03-16 | GG-PQE | Nguyen Anh Thai | V1544017 | Tommy - Thai Nguyen Anh (QE) | 24422 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 5 | 9900000 | MCN5 FATP Proto1 | F27 | MCN5 | FATP | P1.0 |  | -46097 | 2026-05-11 | 56 | 50 | 2026-03-22 |  | On time | New Buy | Q | Done | FATP-NPI-F27-MVA2603-31OM | Done | 1FSHQ40077 | Done | 1FSHQ40077 |  | Đã nhận 23/04 | EPR2603240037 |  | đã out | 5 | 5 | 5 | 5
2026-03-16 | GG-PQE | Nguyen Anh Thai | V1544017 | Tommy - Thai Nguyen Anh (QE) | 24422 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 10 | 23000000 | MCN5 FATP Proto1 | F27 | MCN5 | FATP | P1.0 |  | -46097 | 2026-05-11 | 56 | 50 | 2026-03-22 | 2026-05-05 | On time | New Buy | Q | Done | FATP-NPI-F27-MVA2603-31OM | Done | VNPR202604060169 | Done | VNPO202604150301 | 2026-05-29 | 2026-05-30 | EPR2603210035 |  |  | 10 | 10 | 10 | 10
2026-03-16 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 2 | 37434000 | MCN5 FATP Proto1 | F27 | MCN5 | FATP | P1.0 |  | -46097 | 2026-05-11 | 56 | 70 | 2026-03-02 | 2026-05-25 | Late |  |  |  | FATP-NPI-F27-MVA2603-31OM | Done | 1FSHQ40076 | Done | 1FSHQ40076 |  | 2026-04-23 | EPR2603240033 |  |  | 0 | 2 | 2 | 2
2026-03-16 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 2 | 31000000 | MCN5 FATP Proto1 | F27 | MCN5 | FATP | P1.0 |  | -46097 | 2026-05-11 | 56 | 65 | 2026-03-07 | 2026-05-20 | Late |  |  |  | FATP-NPI-F27-MVA2603-31OM | Done | VNPR202604060161 | Done | VNPO202604110048 | 2026-05-25 | 2026-05-25 | EPR2603240034 |  |  | 0 | 2 | 2 | 2
2026-03-16 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | 5800000 | 3 | 17400000 | MCN5 FATP Proto1 | F27 | MCN5 | FATP | P1.0 |  |  | 2026-05-11 | 56 | 65 | 2026-03-07 | 2026-05-20 | Late |  |  |  | FATP-NPI-F27-MVA2603-31OM | Done | VNPR202604060161 | Done | VNPO202604110048 |  | 2026-05-07 | EPR2603210034
2026-03-16 | GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 2020000 | 2 | 4040000 | MCN5 FATP Proto1 | F27 | MCN5 | FATP | P1.0 |  | -46097 | 2026-05-11 | 56 | 50 | 2026-03-22 | 2026-05-05 | On time |  |  |  | FATP-NPI-F27-MVA2603-31OM | Done | 1FSHQ40077 | Done | 1FSHQ40077 |  | 2026-04-29 | EPR2603240035 |  |  | 0 | 2 | 2 | 2
2026-03-16 | TE | Lê Phi Yến | V1542548 | yenlp@fih-foxconn.com |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 6 | 39600000 | MCN5 FATP Proto | F27 | MCN5 | FATP | P1.0 |  |  | 2026-05-11 | 56 | 50 | 2026-03-22 | 2026-05-05 | On time | New Buy |  | Done | FATP-NPI-F27-MVA2603-33OM | Done | VNPR202604010061 | Done | VNPO202604070280 |  | 2026-05-07 | EPR2605090012 |  |  | 6 | 6 | 6 | 6
2026-03-17 | TE | Lê Phi Yến | V1542549 | yenlp@fih-foxconn.com |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 6 | 39600000 | MCN5 SMT Proto | F27 | MCN5 | SMT | P1.0 |  | -46098 | 2026-05-11 | 55 | 50 | 2026-03-22 | 2026-05-06 | On time | New Buy |  | Done | SMT-NPI-F27-MVA2605-18OM | Done | VNPR202605180025 | Done | VNPO202605210256 | 2026-05-29 | 2026-05-30 | EPR2605090001 (4x - về sau) / EPR2603210039 (2x lấy từ spare part) |  |  | 6 | 6 | 6 | 6
2026-03-17 | IQC | Nguyễn Văn Ngọc | V1540332 | ngocnv5@fih-foxconn.com |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 2 | 6600000 | MCN5 Proto | F27 | MCN5 | FATP | P1.0 |  |  | 2026-05-11 | 55 | 50 | 2026-03-22 | 2026-05-06 | On time | New Buy |  | Done | FATP-NPI-F27-MVA2603-33OM | Done | VNPR202604010061 | Done | VNPO202604070280 |  | 2026-05-07 | EPR2603210040 |  |  | 2 | 2 | 2 | 2
2026-03-17 | FAE | Trần Ngọc Tiến | V1524847 | tientn@fih-foxconn.com | 4457 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 3 | 9900000 | MCN5 FATP Proto | F27 | MCN5 | FATP | P1.0 |  | -46098 | 2026-05-11 | 55 | 50 | 2026-03-22 | 2026-05-06 | On time | New Buy | L | Done | L10-NPI-F27-MVA2604-04OM => FATP-NPI-F27-MVA2604-04OM | Done | VNPR202604200019 | Done | VNPO202604230205 | 2026-05-29 | 2026-05-30 | EPR2603210041 |  |  | 3 | 3 | 3 | 3
2026-03-24 | TE | Ngô Thị Anh | V1550422 | anhnt40@fih-foxconn.com |  | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 10 | 267520000 | P1 for F27 / FATP | F27 | MCN5 | FATP | P1.0 |  | -46105 | 2026-05-11 | 48 | 70 | 2026-03-02 |  | Late | New Buy | L | Done | FATP-NPI-F27-MVA2603-54OM | Done | 1FSHQ40014 | Done | 1FSHQ40014 |  | Đã nhận | EPR2603280001: Done |  |  | 10 | 10 | 10 | 10
2026-03-24 | TE | Ngô Thị Anh | V1550422 | anhnt40@fih-foxconn.com |  | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 2 | 53504000 | P1 for F27 / SMT | F27 | MCN5 | SMT | P1.0 |  | -46105 | 2026-05-11 | 48 | 70 | 2026-03-02 |  | Late | New Buy | L | Done | SMT-NPI-F27-MVA2603-55OM | Done | 1FSHQ40078 | Done | 1FSHQ40078 |  | Đã nhận | EPR2603280002: Done |  |  | 2 | 2 | 2 | 2
[6 empty] | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 1 | 18717000 |  | P27 | WGO5 | SMT | P1.1 |  | 0 | 2026-06-21 | 2026-06-21 | 70 | 2026-04-12 | 70 | On time | [13 empty] | 0 | 0 | 0 | 0
2026-04-23 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 54 | 1444608000 | WGO5 FATP P1.0 | P27 | WGO5 | FATP | P1.0 |  | -46135 | 2026-05-18 | 25 | 70 | 2026-03-09 | 2026-07-02 | Late | New Buy | L | Done | FATP-NPI-WGO5-MVA2604-20OM | Done | 30x 1FSHQ50057 24x 1FSHQ50058 | Done | 30x 1FSHQ50057 24x 1FSHQ50058 |  | 2026-05-14 | EPR2605040013 |  | đã out | 54 | 54 | 54 | 54
2026-04-23 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 58 | 1551616000 | ASK5 FATP P1.0 | P27 | ASK5 | FATP | P1.0 |  | -46135 | 2026-05-18 | 25 | 70 | 2026-03-09 | 2026-07-02 | Late | New Buy | L | Done | FATP-NPI-ASK5-MVA2604-19OM | Done | 30x 1FSHQ50054 28x 1FSHQ50056 | Done | 30x 1FSHQ50054 28x 1FSHQ50056 |  | 2026-05-14 | EPR2605040014 |  | đã out | 58 | 58 | 58 | 58
2026-04-23 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 58 | 1551616000 | KSH5 FATP P1.0 | P27 | KSH5 | FATP | P1.0 |  | -46135 | 2026-05-18 | 25 | 70 | 2026-03-09 | 2026-07-02 | Late | New Buy | L | Done | FATP-NPI-KSH5-MVA2604-18OM | Done | 30x 1FSHQ50052 28x 1FSHQ50053 | Done | 30x 1FSHQ50052 28x 1FSHQ50053 |  | 2026-05-14 | EPR2605040015 |  | đã out | 58 | 58 | 58 | 58
2026-04-24 | TE | Nguyễn Ngọc Huyền | V1549412 | Nguyen Ngoc Huyen (Evelyn) | 4440 | Monitor MB24V7-W, 23.8 inch White, With Bracket Arm Warrior | MB24V7-W, 23.8 inch White, With Bracket Arm Warrior WA-MH0802 (White) | 1815000 | 53 | 96195000 | CGY4 P26 demo line | P26 Demo Line | CGY4 | FATP | MP |  | -46136 | 2026-04-30 | 6 | 80 | 2026-02-09 | 2026-07-13 | Late | New Buy | L | Done | FATP-MP-CGY4-MVA2604-21OM | Done | 1FSHQ50011 | Done | 1FSHQ50011 | 22May26 (về trước 49x màn+ 74x arm) 25x màn còn lại plan tháng 6/2026 | Đã nhận 22.5(49x màn-74 arn) | EPR2605040016 |  |  | 53 | 53 | 53 | 53
2026-04-24 | QA G -PQC | Đặng Duy Linh | V1527806 | Linh Dang Duy (Cole) | 3040 | Monitor MB24V7-W, 23.8 inch White, With Bracket Arm Warrior | MB24V7-W, 23.8 inch White, With Bracket Arm Warrior WA-MH0802 (White) | 1815000 | 21 | 38115000 | CGY4 P26 demo line | P26 Demo Line | CGY4 | FATP | MP |  | -46136 | 2026-04-30 | 6 | 80 | 2026-02-09 | 2026-07-13 | Late | New Buy | L | Done | FATP-MP-CGY4-MVA2604-21OM | Done | 1FSHQ50011 | Done | 1FSHQ50011 |  | 2026-05-23 | EPR2605040017 |  |  | 21 | 21 | 21 | 21
2026-04-24 | QA G -PQC | Đặng Duy Linh | V1527806 | Linh Dang Duy (Cole) | 3040 | Mini PC ASUS NUC 14 Essential NUC14MNK150 | NUC 14 Essential NUC14MNK150 Intel N150, Ram 16 GB DDR5,SSD 256GB, Wi-Fi and Bluetooth, NoOS, 3Yrs Wty | 9680000 | 21 | 203280000 | CGY4 P26 demo line | P26 Demo Line | CGY4 | FATP | MP |  | -46136 | 2026-04-30 | 6 | 50 | 2026-03-11 | 2026-06-13 | Late | New Buy | G | Done | FATP-MP-CGY4-MVA2605-40OM | Done | 1FSHQ50334 | Done | 1FSHQ50334 | [5 empty] | 21 | 21 | 21 | 0
2026-05-02 | ENG2 | Đỗ Văn Toàn |  |  |  | Monitor MB24V7-W, 23.8 inch White, With Bracket Arm Warrior | MB24V7-W, 23.8 inch White, With Bracket Arm Warrior WA-MH0802 (White) | 1815000 | 12 | 21780000 | CGY4 P26 demo line | P26 Demo Line | CGY4 | FATP | MP |  | -46144 | 2026-04-30 | -2 | 80 | 2026-02-09 | 2026-07-21 | Late | [13 empty] | 0 | 0 | 0 | 0
2026-05-06 | ENG3 | Phạm Van Hùng |  |  |  | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 5 | 93585000 | PC for Auto charging machine P26 | P26 | 4CS4 | FATP | MP | 2026-06-06 | 31 | 2026-04-23 | -13 | 70 | 2026-02-12 | 2026-07-15 | Late | RE: 关于手机充电站项目（CGY4, 4CS4, PKK4）电脑设备的申领需求) | G | Done | FATP-MP-4CS4-MVA2605-09AUTO | Done | 1FSHQ50177 | Done | 1FSHQ50177 | 2026-06-02 | 2026-06-02 | EPR2605110012 |  | Đã out nhưng nợ tem chính thức (PO này chưa đẩy được nên chưa có số MVA, các em in tạm tem theo SN trước nhé ) | 5 | 5 | 5 | 5
2026-05-06 | ENG3 | Phạm Van Hùng |  |  |  | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 5 | 93585000 | PC for Auto charging machine P26 | P26 | CGY4 | FATP | MP | 2026-06-06 | 31 | 2026-04-23 | -13 | 70 | 2026-02-12 | 2026-07-15 | Late | RE: 关于手机充电站项目（CGY4, 4CS4, PKK4）电脑设备的申领需求) | G | Done | FATP-MP-CGY4-MVA2605-11AUTO | Done | 1FSHQ50179 | Done | 1FSHQ50179 |  | 2026-05-23 | EPR2605110011 |  | đã out | 5 | 5 | 5 | 5
2026-05-06 | ENG3 | Phạm Van Hùng |  |  |  | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 5 | 93585000 | PC for Auto charging machine P26 | P26 | PKK4 | FATP | MP | 2026-06-06 | 31 | 2026-04-23 | -13 | 70 | 2026-02-12 | 2026-07-15 | Late | RE: 关于手机充电站项目（CGY4, 4CS4, PKK4）电脑设备的申领需求) | G | Done | FATP-MP-PKK4-MVA2605-10AUTO | Done | 1FSHQ50178 | Done | 1FSHQ50178 |  | 2026-05-23 | EPR2605110010 |  | đã out | 5 | 5 | 5 | 5
2026-05-07 | QA G -PQC | Phạm Thị Bích |  |  |  | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 14 | 262038000 | P27 P1.0 | P27 | KSH5 | FATP | P1.0 | 2026-05-25 | 18 | 2026-05-18 | 11 | 70 | 2026-03-09 | 2026-07-16 | Late |  | L | Done | FATP-NPI-KSH5-MVA2605-13OM | Done | 1FSHQ50181 | Done | 1FSHQ50181 |  | 2026-05-23 | EPR2605110009 |  |  | 14 | 14 | 14 | 14
2026-05-07 | QA G -PQC | Phạm Thị Bích |  |  |  | Monitor 2 (old) | #N/A | #N/A | 14 | #N/A | P27 P1.0 | P27 | KSH5 | FATP | P1.0 | 2026-05-25 | 18 | 2026-05-18 | 11 |  | 2026-05-18 | 2026-05-07 | On time |  | L | Done | FATP-NPI-KSH5-MVA2605-13OM | Done | 1FSHQ50183 | Done | 1FSHQ50183 |  |  | EPR2605110008 |  |  | 14 | 14 | 14 | 0
2026-05-07 | QA G -PQC | Phạm Thị Bích |  |  |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 11 | 36300000 | P27 P1.0 | P27 | KSH5 | FATP | P1.0 | 2026-05-25 | 18 | 2026-05-18 | 11 | 50 | 2026-03-29 | 2026-06-26 | Late |  | L | Done | FATP-NPI-KSH5-MVA2605-13OM | In Progress | VNPR202605160018 | Done | VNPO202606010194 |  |  | EPR2605110007 |  |  | 11 | 0 | 11 | 0
2026-05-07 | QA G -PQC | Phạm Thị Bích |  |  |  | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 14 | 262038000 | P27 P1.0 | P27 | WGO5 | FATP | P1.0 | 2026-05-25 | 18 | 2026-05-18 | 11 | 70 | 2026-03-09 | 2026-07-16 | Late |  | L | Done | FATP-NPI-WGO5-MVA2605-15OM | Done | 1FSHQ50186 | Done | 1FSHQ50186 |  |  | EPR2605110006 |  |  | 14 | 14 | 14 | 0
2026-05-07 | QA G -PQC | Phạm Thị Bích |  |  |  | Monitor 2 (old) | #N/A | #N/A | 14 | #N/A | P27 P1.0 | P27 | WGO5 | FATP | P1.0 | 2026-05-25 | 18 | 2026-05-18 | 11 |  | 2026-05-18 | 2026-05-07 | On time |  | L | Done | FATP-NPI-WGO5-MVA2605-15OM | Done | 1FSHQ50187 | Done | 1FSHQ50187 |  |  | EPR2605110005 |  |  | 14 | 14 | 14 | 0
2026-05-07 | QA G -PQC | Phạm Thị Bích |  |  |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 11 | 36300000 | P27 P1.0 | P27 | WGO5 | FATP | P1.0 | 2026-05-25 | 18 | 2026-05-18 | 11 | 50 | 2026-03-29 | 2026-06-26 | Late |  | L | Done | FATP-NPI-WGO5-MVA2605-15OM | Done | VNPR202605160022 | Done | VNPO202606010194 |  |  | EPR2605110004 |  |  | 11 | 11 | 11 | 0
2026-05-07 | QA G -PQC | Phạm Thị Bích |  |  |  | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 14 | 262038000 | P27 P1.0 | P27 | ASK5 | FATP | P1.0 | 2026-05-25 | 18 | 2026-05-18 | 11 | 70 | 2026-03-09 | 2026-07-16 | Late |  | L | Done | FATP-NPI-ASK5-MVA2605-14OM | Done | 1FSHQ50184 | Done | 1FSHQ50184 |  | 2026-05-23 | EPR2605110003 |  |  | 14 | 14 | 14 | 14
2026-05-07 | QA G -PQC | Phạm Thị Bích |  |  |  | Monitor 2 (old) | #N/A | #N/A | 14 | #N/A | P27 P1.0 | P27 | ASK5 | FATP | P1.0 | 2026-05-25 | 18 | 2026-05-18 | 11 |  | 2026-05-18 | 2026-05-07 | On time |  | L | Done | FATP-NPI-ASK5-MVA2605-14OM | Done | 1FSHQ50185 | Done | 1FSHQ50185 |  |  | EPR2605110002 |  |  | 14 | 14 | 14 | 0
2026-05-07 | QA G -PQC | Phạm Thị Bích |  |  |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 11 | 36300000 | P27 P1.0 | P27 | ASK5 | FATP | P1.0 | 2026-05-25 | 18 | 2026-05-18 | 11 | 50 | 2026-03-29 | 2026-06-26 | Late |  | L | Done | FATP-NPI-ASK5-MVA2605-14OM | Done | VNPR202605160021 | Done | VNPO202606010194 |  |  | EPR2605110001 |  |  | 11 | 11 | 11 | 0
2026-05-12 | QA G - SMT QC | Tống Văn Tuyến |  |  |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 2 | 4600000 | P27 P1.0 | P27 | ASK5 | SMT | P1.0 | 2026-05-25 | 13 | 2026-05-16 | 4 | 50 | 2026-03-27 | 2026-07-01 | Late |  | L | Done | SMT-NPI-ASK5-MVA2605-23OM | Done | VNPR202605220183 | Done | VNPO202606120168 |  | Lấy stock OM WH trả đơn trước | EPR2605260006 |  |  | 2 | 2 | 2 | 2
2026-05-12 | QA G - SMT QC | Tống Văn Tuyến |  |  |  | Monitor 2 (old) | #N/A | #N/A | 2 | #N/A | P27 P1.0 | P27 | ASK5 | SMT | P1.0 | 2026-05-25 | 13 | 2026-05-16 | 4 |  | 2026-05-16 | 2026-05-12 | On time |  | L | Done | SMT-NPI-ASK5-MVA2605-23OM | Done | 1FSHQ50257 | Done | 1FSHQ50257 |  |  | EPR2605260007 |  |  | 2 | 2 | 2 | 0
2026-05-12 | QA G - SMT QC | Tống Văn Tuyến |  |  |  | Monitor 1 (old) | #N/A | #N/A | 4 | #N/A | P27 P1.0 | P27 | ASK5 | SMT | P1.0 | 2026-05-25 | 13 | 2026-05-16 | 4 |  | 2026-05-16 | 2026-05-12 | On time |  | L | Done | SMT-NPI-ASK5-MVA2605-23OM | Done | 1FSHQ50259 | Done | 1FSHQ50259 |  |  | EPR2605260008 |  |  | 4 | 4 | 4 | 0
2026-05-12 | QA G - SMT QC | Tống Văn Tuyến |  |  |  | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 1 | 15500000 | P27 P1.0 | P27 | ASK5 | SMT | P1.0 | 2026-05-25 | 13 | 2026-05-16 | 4 | 65 | 2026-03-12 | 2026-07-16 | Late |  | L | Done | SMT-NPI-ASK5-MVA2605-23OM | Done | VNPR202605220190 | Done | VNPO202606120163 |  |  | EPR2605260009 |  |  | 1 | 1 | 1 | 0
2026-05-13 | QA G - SMT QC | Tống Văn Tuyến |  |  |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 2 | 6600000 | P27 P1.0 | P27 | KSH5 | SMT | P1.0 | 2026-05-25 | 12 | 2026-05-16 | 3 | 50 | 2026-03-27 | 2026-07-02 | Late |  | L | Done | SMT-NPI-KSH5-MVA2605-22OM | Done | VNPR202605220174 | Done | VNPO202606010194 |  |  | EPR2605260010 |  |  | 2 | 2 | 2 | 0
2026-05-13 | QA G - SMT QC | Tống Văn Tuyến |  |  |  | Monitor 2 (old) | #N/A | #N/A | 2 | #N/A | P27 P1.0 | P27 | KSH5 | SMT | P1.0 | 2026-05-25 | 12 | 2026-05-16 | 3 |  | 2026-05-16 | 2026-05-13 | On time |  | L | Done | SMT-NPI-KSH5-MVA2605-22OM | Done | 1FSHQ50260 | Done | 1FSHQ50260 |  |  | EPR2605260011 |  |  | 2 | 2 | 2 | 0
2026-05-13 | QA G - SMT QC | Tống Văn Tuyến |  |  |  | Monitor 1 (old) | #N/A | #N/A | 4 | #N/A | P27 P1.0 | P27 | KSH5 | SMT | P1.0 | 2026-05-25 | 12 | 2026-05-16 | 3 |  | 2026-05-16 | 2026-05-13 | On time |  | L | Done | SMT-NPI-KSH5-MVA2605-22OM | Done | 1FSHQ50261 | Done | 1FSHQ50261 |  |  | EPR2605260012 |  |  | 4 | 4 | 4 | 0
2026-05-13 | QA G - SMT QC | Tống Văn Tuyến |  |  |  | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 1 | 15500000 | P27 P1.0 | P27 | KSH5 | SMT | P1.0 | 2026-05-25 | 12 | 2026-05-16 | 3 | 65 | 2026-03-12 | 2026-07-17 | Late |  | L | Done | SMT-NPI-KSH5-MVA2605-22OM | Done | VNPR202605220176 | Done | VNPO202606120169 |  |  | EPR2605260013 |  |  | 1 | 1 | 1 | 0
2026-05-13 | QA G - SMT QC | Tống Văn Tuyến |  |  |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 2 | 4600000 | P27 P1.0 | P27 | WGO5 | SMT | P1.0 | 2026-05-25 | 12 | 2026-05-16 | 3 | 50 | 2026-03-27 | 2026-07-02 | Late |  | L | Done | SMT-NPI-WGO5-MVA2605-24OM | Done | VNPR202605220259 | Done | VNPO202606080275 |  | Lấy stock OM WH trả đơn trước | EPR2605260014 |  |  | 2 | 2 | 2 | 2
2026-05-13 | QA G - SMT QC | Tống Văn Tuyến |  |  |  | Monitor 2 (old) | #N/A | #N/A | 2 | #N/A | P27 P1.0 | P27 | WGO5 | SMT | P1.0 | 2026-05-25 | 12 | 2026-05-16 | 3 |  | 2026-05-16 | 2026-05-13 | On time |  | L | Done | SMT-NPI-WGO5-MVA2605-24OM | Done | 1FSHQ50268 | Done | 1FSHQ50268 |  |  | EPR2605260015 |  |  | 2 | 2 | 2 | 0
2026-05-13 | QA G - SMT QC | Tống Văn Tuyến |  |  |  | Monitor 1 (old) | #N/A | #N/A | 4 | #N/A | P27 P1.0 | P27 | WGO5 | SMT | P1.0 | 2026-05-25 | 12 | 2026-05-16 | 3 |  | 2026-05-16 | 2026-05-13 | On time |  | L | Done | SMT-NPI-WGO5-MVA2605-24OM | Done | 1FSHQ50269 | Done | 1FSHQ50269 |  |  | EPR2605260016 |  |  | 4 | 4 | 4 | 0
2026-05-13 | QA G - SMT QC | Tống Văn Tuyến |  |  |  | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 1 | 15500000 | P27 P1.0 | P27 | WGO5 | SMT | P1.0 | 2026-05-25 | 12 | 2026-05-16 | 3 | 65 | 2026-03-12 | 2026-07-17 | Late |  | L | Done | SMT-NPI-WGO5-MVA2605-24OM | Done | VNPR202605220261 | Done | VNPO202606080274 |  |  | EPR2605260017 |  |  | 1 | 1 | 1 | 0
2026-05-19 | FAE | Phạm Hữu Tính |  |  |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 1 | 3300000 | P27 P1.0 | P27 | WGO5 | FATP | P1.0 | 2026-05-25 | 6 | 2026-05-18 | -1 | 50 | 2026-03-29 | 2026-07-08 | Late |  | L | Done | FATP-NPI-WGO5-MVA2605-34OM | Done | VNPR202605270042 | Done | VNPO202606010093 |  | Lấy stock OM WH trả đơn trước | EPR2605260018 |  |  | 1 | 1 | 1 | 1
2026-05-19 | FAE | Phạm Hữu Tính |  |  |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 6 | 13800000 | P27 P1.0 | P27 | WGO5 | FATP | P1.0 | 2026-05-25 | 6 | 2026-05-18 | -1 | 50 | 2026-03-29 | 2026-07-08 | Late |  | L | Done | FATP-NPI-WGO5-MVA2605-34OM | Done | VNPR202605270042 | Done | VNPO202606010093 |  | Lấy stock OM WH trả đơn trước | EPR2605260019 |  |  | 6 | 6 | 6 | 6
2026-05-19 | FAE | Lê Đình Nhật |  |  |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 1 | 3300000 | P27 P1.0 | P27 | ASK5 | FATP | P1.0 | 2026-05-25 | 6 | 2026-05-18 | -1 | 50 | 2026-03-29 | 2026-07-08 | Late |  | L | Done | FATP-NPI-ASK5-MVA2605-33OM | Done | VNPR202605270035 | Done | VNPO202606010093 |  | Lấy stock OM WH trả đơn trước | EPR2605260020 |  |  | 1 | 1 | 1 | 1
2026-05-19 | FAE | Lê Đình Nhật |  |  |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 6 | 13800000 | P27 P1.0 | P27 | ASK5 | FATP | P1.0 | 2026-05-25 | 6 | 2026-05-18 | -1 | 50 | 2026-03-29 | 2026-07-08 | Late |  | L | Done | FATP-NPI-ASK5-MVA2605-33OM | Done | VNPR202605270035 | Done | VNPO202606010093 |  | Lấy stock OM WH trả đơn trước | EPR2605260021 |  |  | 6 | 6 | 6 | 6
2026-05-19 | FAE | Nguyễn Văn Tiếp |  |  |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 1 | 3300000 | P27 P1.0 | P27 | KSH5 | FATP | P1.0 | 2026-05-25 | 6 | 2026-05-18 | -1 | 50 | 2026-03-29 | 2026-07-08 | Late |  | L | Done | FATP-NPI-KSH5-MVA2605-32OM | Done | VNPR202605270029 | Done | VNPO202606010093 |  | Lấy stock OM WH trả đơn trước | EPR2605260022 |  |  | 1 | 1 | 1 | 1
2026-05-19 | FAE | Nguyễn Văn Tiếp |  |  |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 6 | 13800000 | P27 P1.0 | P27 | KSH5 | FATP | P1.0 | 2026-05-25 | 6 | 2026-05-18 | -1 | 50 | 2026-03-29 | 2026-07-08 | Late |  | L | Done | FATP-NPI-KSH5-MVA2605-32OM | Done | VNPR202605270029 | Done | VNPO202606010093 |  | Lấy stock OM WH trả đơn trước | EPR2605260023 |  |  | 6 | 6 | 6 | 6
2026-05-30 | TE | Ngô Thị Anh |  |  |  | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 10 | 267520000 | F27 P1.1 | F27 | MCN5 | SMT | P1.1 |  | -46172 | 2026-07-07 | 38 | 70 | 2026-04-28 | 2026-08-08 | Late |  | L | Done | SMT-NPI-F27-MVA2605-42OM | Done | 1FSHQ60053 | Done | 1FSHQ60053 |  |  | EPR2606120001 |  |  | 10 | 10 | 10 | 0
2026-06-08 | MFG-GTW | Nguyễn Thị Trang |  |  |  | Mini PC (Assy) |  | #N/A | 50 | #N/A | F27 P1.1 | F27 | MCN5 | FATP | P1.1 |  | -46181 | 2026-07-06 | 28 |  | 2026-07-06 | 2026-06-08 | On time |  |  |  |  | Done | [8 empty] | 0 | 50 | 0 | 0
2026-06-08 | MFG-GTW | Nguyễn Thị Trang |  |  |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1265000 | 50 | 63250000 | F27 P1.1 | F27 | MCN5 | FATP | P1.1 |  | -46181 | 2026-07-06 | 28 | 50 | 2026-05-17 | 2026-07-28 | Late |  |  | Pending | FATP-NPI-F27-MVA2606-02OM | Done | 1FSHQ60129 | Done | 1FSHQ60129 |  |  | EPR2606120003 |  |  | 0 | 50 | 50 | 0
2026-06-08 | MFG-GTW | Nguyễn Thị Trang |  |  |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 50 | 165000000 | F27 P1.1 | F27 | MCN5 | FATP | P1.1 |  | -46181 | 2026-07-06 | 28 | 50 | 2026-05-17 | 2026-07-28 | Late |  |  | Done | FATP-NPI-F27-MVA2606-02OM | Done | VNPR202606150114 |  |  |  |  | EPR2606120004 |  |  | 50 | 50 | 0 | 0
2026-06-08 | FAE | Trần Ngọc Tiến |  |  |  | All-in-One SingPC M22Vi512H8M2-W | M22Vi512H8M2-W, i5-12450H, Ram 8GB, SSD 256GB, 21.5inch Key-Mouse, WiFi, Bluetooth | 16280000 | 2 | 32560000 | F27 P1.1 | F27 | MCN5 | FATP | P1.1 |  | -46181 | 2026-07-06 | 28 | 20 | 2026-06-16 | 2026-06-28 | On time |  |  | Done | FATP-NPI-F27-MVA2606-03OM | Done | 1FSHQ60128 | Done | 1FSHQ60128 |  |  | EPR2606220001 |  |  | 2 | 2 | 2 | 0
2026-06-10 | GTW-PQE | Nguyễn Anh Thái |  |  |  | All-in-One SingPC M22Vi512H8M2-W | SingPC M22Vi512H8M2-W , i5-12450H, Ram 8GB, SSD 256GB, 21.5inch Key-Mouse, WiFi, Bluetooth | 16280000 | 3 | 48840000 | F27 P1.1 | F27 | MCN5 | FATP | P1.1 | 2026-07-15 | 35 | 2026-07-06 | 26 | 20 | 2026-06-16 | 2026-06-30 | On time |  |  | Done | FATP-NPI-F27-MVA2606-05OM | Pending | 1FSHQ60153 | [7 empty] | 3 | 0 | 0 | 0
2026-06-10 | GTW-PQE | Nguyễn Anh Thái |  |  |  | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 2020000 | 5 | 10100000 | F27 P1.1 | F27 | MCN5 | FATP | P1.1 | 2026-07-15 | 35 | 2026-07-06 | 26 | 50 | 2026-05-17 | 2026-07-30 | Late |  |  | Done | FATP-NPI-F27-MVA2606-05OM | Pending | 1FSHQ60154 |  |  |  |  | EPR2606120005 |  |  | 5 | 0 | 0 | 0
2026-06-10 | GTW-PQE | Nguyễn Anh Thái |  |  |  | Mini PC ASUS NUC 14 Essential NUC14MNK150 | NUC 14 Essential NUC14MNK150 Intel N150, Ram 16 GB DDR5,SSD 256GB, Wi-Fi and Bluetooth, NoOS, 3Yrs Wty | 9680000 | 2 | 19360000 | F27 P1.1 | F27 | MCN5 | FATP | P1.1 | 2026-07-15 | 35 | 2026-07-06 | 26 | 50 | 2026-05-17 | 2026-07-30 | Late | [13 empty] | 0 | 0 | 0 | 0
2026-06-14 | GTW-IQC | Nguyễn Văn Ngọc |  |  |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 10 | 33000000 | F27 P1.1 | F27 | MCN5 | FATP | P1.1 | 2026-06-21 | 7 | 2026-07-06 | 22 | 50 | 2026-05-17 | 2026-08-03 | Late |  |  | Done | FATP-NPI-F27-MVA2606-10OM | Done | VNPR202606180125 | Done | VNPO202606230081 |  |  | EPR2606240011 |  |  | 10 | 10 | 10 | 0
2026-06-15 | GTW-IQC | Nguyễn Văn Ngọc |  |  |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1265000 | 3 | 3795000 | F27 P1.1 | F27 | MCN5 | FATP | P1.1 | 2026-07-15 | 30 | 2026-07-06 | 21 | 50 | 2026-05-17 | 2026-08-04 | Late |  |  | Done | FATP-NPI-F27-MVA2606-10OM | Pending | 1FSHQ60147 |  |  |  |  | EPR2606240012
2026-06-19 | QA G-IQC | Nguyễn Thị Huyền Trang |  |  |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 2 | 6600000 | P27 P1.0 | P27 | WGO5 | SMT | P1.0 |  | -46192 | 2026-05-16 | -34 | 50 | 2026-03-27 | 2026-08-08 | Late |  |  | Done | SMT-NPI-WGO5-MVA2606-37OM | Done | VNPR202606250158 | Done | VNPO202606270391 |  |  | EPR2606240010 |  |  | 2 | 2 | 2 | 0
2026-06-19 | QA G-IQC | Nguyễn Thị Huyền Trang |  |  |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 1 | 3300000 | P27 P1.0 | P27 | ASK5 | SMT | P1.0 |  | -46192 | 2026-05-16 | -34 | 50 | 2026-03-27 | 2026-08-08 | Late |  |  | Done | SMT-NPI-ASK5-MVA2606-36OM | Done | VNPR202606250155 | Done | VNPO202606270391 |  |  | EPR2606240009 |  |  | 1 | 1 | 1 | 0
2026-06-19 | QA G-IQC | Nguyễn Thị Huyền Trang |  |  |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 2 | 6600000 | P27 P1.0 | P27 | KSH5 | SMT | P1.0 |  | -46192 | 2026-05-16 | -34 | 50 | 2026-03-27 | 2026-08-08 | Late |  |  | Done | SMT-NPI-KSH5-MVA2606-35OM | Done | VNPR202606250153 | Done | VNPO202606270391 |  |  | EPR2606240008 |  |  | 2 | 2 | 2 | 0
[6 empty] | Mini PC (Assy NUC series) | Mini PC ASUS RNUC14MNK9700000, Intel N100, Ram 16 GB DDR5 4800MHz , SSD 256GB, Wi-Fi and Bluetooth, 3Yrs Wty |  |  | 0 | [6 empty] | 0 | #N/A | #N/A | 20 | #N/A | 20 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | 0 | #N/A | [13 empty] | 0 | 0 | 0 | 0
Formulas:
Request Deadline = S2-[Total Leadtime]
LT theo ngày request of DRI = [Date of Request]+[Total Leadtime]
Given LT (days) (follow DRI update) = [Required Delivery Date (update by DRI)]-[Date of Request]

## Check mini PC issue
Mini PC Lamitouch Issue
Project | Dept | Qty request | Yubo Supplied Qty | Pending Qty | PO release Qty | Actual Backup | Detail back up | Pending Supply Qty
P26 MP | MFG | 378 | 0 | 378 | 378 | 262 | +12x-newbuy from P26 zombie line -DL return: +40x- PC Assy at OM WH +120x - newbuy from OR5 - DL return: -14x-NG line return +5x- borrow OR5 wisetech-DL return: +7x-OM stock-lev for P26 +8x PC Assy (8x MFG return NG, OM check OK- re-supplied) +4x PC Assy-borrow PQE-DL return: | 116
| ENG | 24 | 0 | 24 | 24 | 0 |  | 24 | Cancel PO, change to order from Banico Mini PC Asus
P26 service | MFG | 121 | 0 | 121 | 73 | 80 | Đang mượn 80x from p26 zombie line-DL ruturn: | 41
| ENG | 3 | 0 | 3 | 0 | 0 |  | 3
P27 P1.0 | MFG | 140 | 0 | 140 | 0 | 140 | Order 140x- Mini PC asus Banico- Received | 0
Total |  | 666 | 0 | 666 | 475 | 482 |  | 184
[5 empty] | Cancel 475x, change order to NUC asus Banico |  |  | 92 | Trả P26 zombie line
[5 empty] | Remain Qty not yet released PO | 329 |  | 276
now Total order request mini Lamitouch 780x for P26-378x, P26 service: 124x (Line open date 5/18), P27: 278x ( line open date 6/1). Current we temporary use pending pickup mini PC of P26 zombie line 92x and PC assy 40x supplied for P26 MP, total Qty lack ~ 780x-132x= 648x

## NON G MVA EQ request
Date of Request | Department | Requester name | Requester employee ID | Email | Phone | Item | Request equipment spec | Price | Quantity | Total Cost | Purpose | Year Project | Project | Phase | Stage | Required Delivery Date (update by DRI) | Given LT (days) (follow DRI update) | Required Delivery Date follow Stage date (line open date - 14 days) | Given LT (days) follow stage date | Total Leadtime | Request Deadline | Late/ ontime | Action | Remark | Budget Status | Budget # | PR Status | PR # | PO Status | PO # | ETA (Plan) | DTA (Actual) | #PUR request No | Action for delivery later than time Setup line |  | Qty Done Budget | Qty Done PQ | Qty Done PO | Qty Recieved
2026-01-13 | FAE | Vu Xuan Bach | V1521896 | bachvx@fih-foxconn.com | 3546/3435 | IPC | #N/A | 10870000 | 2 | 21740000 | OR6 EVT |  | OR6 | FATP | EVT | 2026-01-30 | 17 | 2026-02-21 | 39 |  | 2026-02-21 | On time | New Buy |  | Done |  | Done |  | Done |  |  | 2026-02-20 | EPR2602020005 : Done |  | FAEIPC2OR6New Buy | 2 | 2 | 2 | 2
2026-01-13 | FAE | Vu Xuan Bach | V1521896 | bachvx@fih-foxconn.com |  | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 2 | 3960000 | OR6 EVT |  | OR6 | FATP | EVT | 2026-01-30 | 17 | 2026-02-21 | 39 |  | 2026-02-21 | On time | New Buy |  | Done | FATP-NPI-OR6-MVA2601-101OM | Done | 1FSHQ10134 | Done | 1FSHQ10134 |  | 2026-02-20 | EPR2602020006 |  | FAEMonitor 12OR6New BuyFATP-NPI-OR6-MVA2601-101OM | 2 | 2 | 2 | 2
2026-01-15 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | IPC+ | #N/A | 14200000 | 2 | 28400000 | OR6 EVT |  | OR6 | FATP | EVT | 2026-01-30 | 15 | 2026-02-21 | 37 |  | 2026-02-21 | On time | New Buy |  | Done | FATP-NPI-OR6-MVA2601-101OM | Done | 1FSHQ10132 | Done | 1FSHQ10132 |  | 2026-02-13 | EPR2602020007 : Done |  | WHIPC+2OR6New BuyFATP-NPI-OR6-MVA2601-101OM | 2 | 2 | 2 | 2
2026-01-15 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 2 | 3960000 | OR6 EVT |  | OR6 | FATP | EVT | 2026-01-30 | 15 | 2026-02-21 | 37 |  | 2026-02-21 | On time | New Buy |  | Done |  | Done |  | Done |  |  | 2026-02-20 | EPR2602020008 ( cũ ) |  | WHMonitor 12OR6New Buy | 2 | 2 | 2 | 2
2026-01-15 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 1 | 15500000 | OR6 EVT |  | OR6 | FATP | EVT | 2026-03-03 | 47 | 2026-02-21 | 37 | 65 | 2025-12-18 | Late | New Buy |  | Done | FATP-NPI-OR6-MVA2602-112OM | Done | VNPR202602090065 | Done | VNPO202602130022 |  | 2026-03-31 | EPR2603100002 |  | WHPDA CHAINWAY C61-48501OR6New BuyFATP-NPI-OR6-MVA2602-112OM | 1 | 1 | 1 | 1
2026-01-19 | ME | Nguyen Thi Hai | V1516000 | haint2@fih-foxconn.com | 4493 | Mini PC (Assy) | #N/A | 7800000 | 440 | 3432000000 | OR5 DVT |  | OR5 | FATP | DVT | 2026-02-23 | 35 | -14 | -46055 |  | -14 | Late | New Buy |  | Done | L10-MP-OR5-MVA2601-103OM / L10-MP-OR5-MVA2601-105OM | Done | 3 PR: 120 / 120 / 120 => check total AMT 120x 1FSHQ20008 120x 1FSHQ20009 120x 1FSHQ20010 80x 1FSHQ10131 | Done | 3 PR: 120 / 120 / 120 => check total AMT 120x 1FSHQ20008 120x 1FSHQ20009 120x 1FSHQ20010 8x + 40x 1FSHQ10131 | pending | 30-03-2026 | EPR2602020009 | Lấy 120x-1FSHQ20008, cấp trước cho P26-MP CGY4 / lấy 40x 1FSHQ10131 cấp cho MFG G trong đống 100x | MEMini PC (Assy)440OR5New BuyL10-MP-OR5-MVA2601-103OM / L10-MP-OR5-MVA2601-105OM | 440 | 440 | 440 | 440
2026-01-19 | ME | Nguyen Thi Hai | V1516000 | haint2@fih-foxconn.com | 4493 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 360 | 446400000 | OR5 DVT |  | OR5 | FATP | DVT | 2026-02-23 | 35 | -14 | -46055 |  | -14 | Late | New Buy |  | Done | L10-MP-OR5-MVA2601-103OM | Done | 90x 1FSHQ20011 90x 1FSHQ20012 90x 1FSHQ20013 90x 1FSHQ20015 | Done | 1FSHQ20012 (PO) 1FSHQ20011 (PO) 1FSHQ20015 (PO) 1FSHQ20013 (PO) |  | 20-03-2026 | EPR2602020010: Done 1 phần |  | MEMonitor 2360OR5New BuyL10-MP-OR5-MVA2601-103OM | 360 | 360 | 360 | 360
2026-01-19 | ME | Nguyen Thi Hai | V1516000 | haint2@fih-foxconn.com | 4493 | Barcode Scanner NEWLAND HH220-HD, USB cable | NEWLAND HH220-HD, USB cable | 2400000 | 330 | 792000000 | OR5 DVT |  | OR5 | FATP | DVT | 2026-02-23 | 35 | -14 | -46055 | 35 | -49 | Late | New Buy |  | Done | L10-MP-OR5-MVA2601-103OM | Done | VNPR202602040113 | Done | VNPO202602090105 |  | 28-03-2026 | EPR2602020011 |  | MEBarcode Scanner NEWLAND HH220-HD, USB cable330OR5New BuyL10-MP-OR5-MVA2601-103OM | 330 | 330 | 330 | 330
2026-01-19 | ME | Nguyen Thi Hai | V1516000 | haint2@fih-foxconn.com | 4493 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 16 | 780800000 | OR5 DVT |  | OR5 | FATP | DVT | 2026-02-23 | 35 | -14 | -46055 | 50 | -64 | Late | New Buy |  | Done | L10-MP-OR5-MVA2601-103OM | Done | 1FSHQ20007 | Done | 1FSHQ20007 |  | 30-03-2026 | EPR2602020012: đã out hết r ( PO: 1FSHQ20007 về làm spare ) |  | MEBarcode Printer ZEBRA16OR5New BuyL10-MP-OR5-MVA2601-103OM | 16 | 16 | 16 | 16
2026-01-26 | FAE | Vu Xuan Bach | V1521896 | bachvx@fih-foxconn.com |  | IPC++ | #N/A | 19280000 | 4 | 77120000 | OR6 EVT |  | OR6 | FATP | EVT | 2026-03-01 | 34 | 2026-02-21 | 26 |  | 2026-02-21 | On time | New Buy |  | Done | FATP-NPI-OR6-MVA2601-106OM | Done | 1FSHQ20004 | Done | 1FSHQ20004 |  | 2026-02-28 | EPR2601310004 |  | FAEIPC++4OR6New BuyFATP-NPI-OR6-MVA2601-106OM | 4 | 4 | 4 | 4
2026-01-26 | FAE | Vu Xuan Bach | V1521896 | bachvx@fih-foxconn.com |  | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 4 | 7920000 | OR6 EVT |  | OR6 | FATP | EVT | 2026-03-01 | 34 | 2026-02-21 | 26 |  | 2026-02-21 | On time | New Buy |  | Done | FATP-NPI-OR6-MVA2601-106OM | Done | 1FSHQ20006 | Done | 1FSHQ20006 |  | 2026-02-28 | EPR2601310005 |  | FAEMonitor 14OR6New BuyFATP-NPI-OR6-MVA2601-106OM | 4 | 4 | 4 | 4
2026-01-29 | PQE | Nguyen Thi Phuong | V1544473 | phuongnt18@fih-foxconn.com | 3802 | IPC | #N/A | 10870000 | 4 | 43480000 | Order for Q station on Line LD8-NPI |  | LD8 |  |  | 2026-03-01 | 31 | #N/A | #N/A |  | #N/A | #N/A | New Buy |  | Done | FATP-NPI-LD8-MVA2601-111OM | Done | 1FSHQ20029 | Done | 1FSHQ20029 |  | 2026-02-27 | EPR2602130001: Done |  | PQEIPC4LD8New BuyFATP-NPI-LD8-MVA2601-111OM | 4 | 4 | 4 | 4
2026-01-29 | PQE | Nguyen Thi Phuong | V1544473 | phuongnt18@fih-foxconn.com | 3802 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 4 | 4960000 | Order for Q station on Line LD8-NPI |  | LD8 |  |  | 2026-03-01 | 31 | #N/A | #N/A |  | #N/A | #N/A | New Buy |  | Done |  | Done |  | Done |  |  | 2026-02-27 | EPR2602130002: Done |  | PQEMonitor 24LD8New Buy | 4 | 4 | 4 | 4
2026-01-29 | PQE | Nguyen Thi Phuong | V1544473 | phuongnt18@fih-foxconn.com | 3802 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 3 | 9900000 | Order for Q station on Line LD8-NPI |  | LD8 |  |  | 2026-03-01 | 31 | #N/A | #N/A | 50 | #N/A | #N/A | New Buy |  | Done | FATP-NPI-LD8-MVA2601-110OM | Done | VNPR202602060073 | Done | VNPO202602110021 |  | 2026-03-16 | EPR2602130003 |  | PQEBarcode Scanner SEUIC HS505HDP-2530 ,USB cable3LD8New BuyFATP-NPI-LD8-MVA2601-110OM | 3 | 3 | 3 | 3
2026-01-30 | TE | Nguyen Hai Yen | V1549748 | yennh@fih-foxconn.com | 4179 | IPC++ | #N/A | 19280000 | 8 | 154240000 | Order for test station on Line LD8-NPI |  | LD8 | FATP | PVT | 2026-03-01 | 30 | 2026-05-18 | 108 |  | 2026-05-18 | On time | New Buy |  | Done | FATP-NPI-LD8-MVA2601-110OM | Done | 1FSHQ20039 | Done | 1FSHQ20039 |  | 2026-02-27 | EPR2602130004 |  | TEIPC++8LD8New BuyFATP-NPI-LD8-MVA2601-110OM | 8 | 8 | 8 | 8
2026-01-30 | TE | Nguyen Hai Yen | V1549748 | yennh@fih-foxconn.com | 4179 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 8 | 9920000 | Order for test station on Line LD8-NPI |  | LD8 | FATP | PVT | 2026-03-01 | 30 | 2026-05-18 | 108 |  | 2026-05-18 | On time | New Buy |  | Done |  | Done |  | Done |  |  | 2026-02-27 | EPR2602130005 : Done |  | TEMonitor 28LD8New Buy | 8 | 8 | 8 | 8
2026-01-30 | TE | Nguyen Hai Yen | V1549748 | yennh@fih-foxconn.com | 4179 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 8 | 18400000 | Order for test station on Line LD8-NPI |  | LD8 | FATP | PVT | 2026-03-01 | 30 | 2026-05-18 | 108 | 50 | 2026-03-29 | On time | New Buy |  | Done | FATP-NPI-LD8-MVA2601-110OM | Done | VNPO202602110021 | Done | VNPO202602110021 |  | 2026-03-16 | EPR2602130006 | 2026-03-17 13:24 | TEBarcode Scanner SEUIC HS505DP, USB cable8LD8New BuyFATP-NPI-LD8-MVA2601-110OM | 8 | 8 | 8 | 8
2026-01-30 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | IPC | #N/A | 10870000 | 3 | 32610000 | LD8 |  | LD8 | FATP | PVT | 2026-02-23 | 24 | 2026-05-18 | 108 |  | 2026-05-18 | On time | Leverage |  | Done | FATP-NPI-LD8-MVA2601-111OM | Done | 1FSHQ20029 | Done | 1FSHQ20029 |  | 2026-02-27 | EPR2602060001: Done |  | WHIPC3LD8LeverageFATP-NPI-LD8-MVA2601-111OM | 3 | 3 | 3 | 3
2026-01-30 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 3 | 5940000 | LD8 |  | LD8 | FATP | PVT | 2026-02-23 | 24 | 2026-05-18 | 108 |  | 2026-05-18 | On time | New Buy |  | Done | FATP-NPI-LD8-MVA2601-110OM | Done | 1FSHQ20037 | Done | 1FSHQ20037 |  | 2026-02-27 | EPR2602070002 |  | WHMonitor 13LD8New BuyFATP-NPI-LD8-MVA2601-110OM | 3 | 3 | 3 | 3
2026-01-30 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 1 | 48800000 | LD8 |  | LD8 | FATP | PVT | 2026-02-23 | 24 | 2026-05-18 | 108 | 50 | 2026-03-29 | On time | New Buy |  | Done | FATP-NPI-LD8-MVA2601-110OM | Done | 1FSHQ20036 | Done | 1FSHQ20036 |  | 2026-03-23 | EPR2602070003: Done |  | WHBarcode Printer ZEBRA1LD8New BuyFATP-NPI-LD8-MVA2601-110OM | 1 | 1 | 1 | 1
2026-01-30 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 3 | 46500000 | LD8 |  | LD8 | FATP | PVT | 2026-02-23 | 24 | 2026-05-18 | 108 | 65 | 2026-03-14 | On time | New Buy |  | Done | FATP-NPI-LD8-MVA2602-113OM | Done | VNPR202602050240 | Done | VNPO202602110021 |  | 2026-05-07 | EPR2602070004 | đã out chị Lịch tại OM Office 30May | WHPDA CHAINWAY C61-48503LD8New BuyFATP-NPI-LD8-MVA2602-113OM | 3 | 3 | 3 | 3
2026-01-30 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 10 | 12400000 | LD8 |  | LD8 | FATP | PVT | 2026-02-23 | 24 | 2026-05-18 | 108 |  | 2026-05-18 | On time | New Buy |  | Done |  | Done |  | Done |  |  | 2026-02-27 | EPR2602070005 |  | MFG Monitor 210LD8New Buy | 10 | 10 | 10 | 10
2026-01-30 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | IPC+ | #N/A | 14200000 | 1 | 14200000 | LD8 |  | LD8 | FATP | PVT | 2026-02-23 | 24 | 2026-05-18 | 108 |  | 2026-05-18 | On time | New Buy |  | Done | FATP-NPI-LD8-MVA2601-110OM | Done | 1FSHQ20040 | Done | 1FSHQ20040 |  | 2026-02-27 | EPR2602070006 |  | MFG IPC+1LD8New BuyFATP-NPI-LD8-MVA2601-110OM | 1 | 1 | 1 | 1
2026-01-30 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 9 | 20700000 | LD8 |  | LD8 | FATP | PVT | 2026-02-23 | 24 | 2026-05-18 | 108 | 50 | 2026-03-29 | On time | New Buy |  | Done | FATP-NPI-LD8-MVA2601-110OM | Done | VNPO202602110021 | Done | VNPO202602110021 |  | 2026-03-31 | EPR2602070007 | 2026-03-21 10:51 | MFG Barcode Scanner SEUIC HS505DP, USB cable9LD8New BuyFATP-NPI-LD8-MVA2601-110OM | 9 | 9 | 9 | 9
2026-01-30 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 3 | 146400000 | LD8 |  | LD8 | FATP | PVT | 2026-02-23 | 24 | 2026-05-18 | 108 | 50 | 2026-03-29 | On time | New Buy |  | Done | FATP-NPI-LD8-MVA2601-110OM | Done | 1FSHQ20036 | Done | 1FSHQ20036 |  | 2026-02-27 | EPR2602070008: Done |  | MFG Barcode Printer ZEBRA3LD8New BuyFATP-NPI-LD8-MVA2601-110OM | 3 | 3 | 3 | 3
2026-01-30 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | IPC | #N/A | 10870000 | 10 | 108700000 | LD8 |  | LD8 | FATP | PVT | 2026-02-23 | 24 | 2026-05-18 | 108 |  | 2026-05-18 | On time | New Buy |  | Done | FATP-NPI-LD8-MVA2601-111OM | Done | 1FSHQ20029 | Done | 1FSHQ20029 |  | 2026-02-27 | EPR2602070009: Done |  | MFG IPC10LD8New BuyFATP-NPI-LD8-MVA2601-111OM | 10 | 10 | 10 | 10
2026-01-30 | IQC | Nguyễn Thị Hiền | V1524357 | hiennt3@fih-foxconn.com | 4160 | IPC | #N/A | 10870000 | 10 | 108700000 | LD8 |  | LD8 |  |  | 2026-02-23 | 24 | #N/A | #N/A |  | #N/A | #N/A | New Buy |  | Done | FATP-NPI-LD8-MVA2601-111OM | Done | 1FSHQ20029 | Done | 1FSHQ20029 |  | 2026-02-27 | EPR2602070010: Done |  | IQCIPC10LD8New BuyFATP-NPI-LD8-MVA2601-111OM | 10 | 10 | 10 | 10
2026-01-30 | IQC | Nguyễn Thị Hiền | V1524357 | hiennt3@fih-foxconn.com | 4160 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 10 | 12400000 | LD8 |  | LD8 |  |  | 2026-02-23 | 24 | #N/A | #N/A |  | #N/A | #N/A | New Buy |  | Done |  | Done |  | Done |  |  | 2026-02-27 | EPR2602070011: Done |  | IQCMonitor 210LD8New Buy | 10 | 10 | 10 | 10
2026-01-30 | IQC | Nguyễn Thị Hiền | V1524357 | hiennt3@fih-foxconn.com | 4160 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 10 | 23000000 | LD8 |  | LD8 |  |  | 2026-02-23 | 24 | #N/A | #N/A | 50 | #N/A | #N/A | New Buy |  | Done | FATP-NPI-LD8-MVA2601-110OM | Done | VNPO202602110021 | Done | VNPO202602110021 |  | 2026-03-31 | EPR2602070012 | 2026-03-17 13:24 | IQCBarcode Scanner SEUIC HS505DP, USB cable10LD8New BuyFATP-NPI-LD8-MVA2601-110OM | 10 | 10 | 10 | 10
2026-02-09 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 18 | 22320000 | MH2 |  | MH2 | FATP | PVT |  | -46062 | 2026-06-05 | 116 |  | 2026-06-05 | On time | New Buy |  | Done | FATP-NPI-MH2-MVA2602-114OM | Done | 1FSHQ20106 | Done | 1FSHQ20106 |  | 2026-03-16 | EPR2603070001 |  | MFGMonitor 218MH2New BuyFATP-NPI-MH2-MVA2602-114OM | 18 | 18 | 18 | 18
2026-02-09 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Mini PC (Assy) | #N/A | 7800000 | 18 | 140400000 | MH2 |  | MH2 | FATP | PVT |  | -46062 | 2026-06-05 | 116 |  | 2026-06-05 | On time | New Buy |  | Done | FATP-NPI-MH2-MVA2602-114OM | Done | 1FSHQ20104 | Done | 1FSHQ20104 | pending | Lấy hết PO 1FSHQ20104 trả cho MFG G // trả đơn Ban MFG thực tế 18x MINI PC ASUS | EPR2603070002: đã cancel // EPR2606240002 |  | MFGMini PC (Assy)18MH2New BuyFATP-NPI-MH2-MVA2602-114OM | 18 | 18 | 18 | 18
2026-02-09 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 18 | 59400000 | MH2 |  | MH2 | FATP | PVT |  | -46062 | 2026-06-05 | 116 | 50 | 2026-04-16 | On time | New Buy |  | Done | FATP-NPI-MH2-MVA2603-22OM | Done | VNPR202603230176 | Done | VNPO202603280076 |  | 2026-04-25 | EPR2603210001 |  | MFGBarcode Scanner SEUIC HS505HDP-2530 ,USB cable18MH2New BuyFATP-NPI-MH2-MVA2603-22OM | 18 | 18 | 18 | 18
2026-02-23 | TE | Nguyen Hai Yen | V1549748 | yennh@fih-foxconn.com | 4179 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 3 | 56151000 | MH2 |  | MH2 | FATP | PVT | 2026-03-09 | 14 | 2026-06-05 | 102 | 70 | 2026-03-27 | On time | New Buy | G | Done | FATP-NPI-MH2-MVA2603-09OM | Done | 1FSHQ30126 | Done | 1FSHQ30126 |  | 2026-04-23 | EPR2603210002 |  | TEIPC+(updated)3MH2New BuyFATP-NPI-MH2-MVA2603-09OM | 3 | 3 | 3 | 3
2026-02-23 | TE | Nguyen Hai Yen | V1549748 | yennh@fih-foxconn.com | 4179 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 3 | 3720000 | MH2 |  | MH2 | FATP | PVT | 2026-03-09 | 14 | 2026-06-05 | 102 |  | 2026-06-05 | On time | New Buy |  | Done | FATP-NPI-MH2-MVA2602-116OM | Done | 1FSHQ30023 | Done | 1FSHQ30023 |  | 2026-03-16 | EPR2603070003 |  | TEMonitor 23MH2New BuyFATP-NPI-MH2-MVA2602-116OM | 3 | 3 | 3 | 3
2026-02-23 | TE | Nguyen Hai Yen | V1549748 | yennh@fih-foxconn.com | 4179 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 3 | 6900000 | MH2 |  | MH2 | FATP | PVT | 2026-03-09 | 14 | 2026-06-05 | 102 | 50 | 2026-04-16 | On time | New Buy |  | Done | FATP-NPI-MH2-MVA2603-22OM | Done | VNPR202603230176 | Done | VNPO202603280076 | 2026-04-25 | Lấy 3x từ 35 con VNPO202604150030 MFG G (180/215) trả đơn trước | EPR2603210004 |  | TEBarcode Scanner SEUIC HS505DP, USB cable3MH2New BuyFATP-NPI-MH2-MVA2603-22OM | 3 | 3 | 3 | 3
2026-02-24 | PQE | Vũ Đăng Hoạch | V1546253 | hoachvd@fih-foxconn.com | 4006 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 4 | 4960000 | BM2 |  | BM2 | FATP | PVT | 2026-03-09 | 13 | -14 | -46091 |  | -14 | Late | New Buy |  | Done | FATP-NPI-BM2-MVA2602-118OM | Done | 1FSHQ30070 | Done | 1FSHQ30070 |  | 2026-04-29 | EPR2603070004 |  | PQEMonitor 24BM2New BuyFATP-NPI-BM2-MVA2602-118OM | 4 | 4 | 4 | 4
2026-02-24 | PQE | Vũ Đăng Hoạch | V1546253 | hoachvd@fih-foxconn.com | 4006 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 3 | 80256000 | BM2 |  | BM2 | FATP | PVT | 2026-03-09 | 13 | -14 | -46091 | 70 | -84 | Late | New Buy | G | Done | FATP-NPI-BM2-MVA2603-10OM | Done | 1FSHQ30119 | Done | 1FSHQ30119 |  | 2026-04-13 | EPR2604090001 |  | PQEIPC++(updated)3BM2New BuyFATP-NPI-BM2-MVA2603-10OM | 3 | 3 | 3 | 3
2026-02-24 | PQE | Vũ Đăng Hoạch | V1546253 | hoachvd@fih-foxconn.com | 4006 | Mini PC (Assy) | #N/A | 7800000 | 14 | 109200000 | BM2 |  | BM2 | FATP | PVT | 2026-03-09 | 13 | -14 | -46091 |  | -14 | Late | New Buy |  | Done | FATP-NPI-BM2-MVA2602-118OM | Done | 1FSHQ30071 | Done | 1FSHQ30071 | pending | Trả 3 PC(ASSY) từ OM-WH trước / lấy hết PO : 1FSHQ30071 cho MFG G | EPR2603070005 ( 11x Mini PC Lami mua mới + 3x PC(ASSY) Lev ) // EPR2603070005 : 11x Lamitouch : đã cancel // EPR2606240003 |  | PQEMini PC (Assy)14BM2New BuyFATP-NPI-BM2-MVA2602-118OM | 14 | 14 | 14 | 14
2026-02-24 | PQE | Vũ Đăng Hoạch | V1546253 | hoachvd@fih-foxconn.com | 4006 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 16 | 36800000 | BM2 |  | BM2 | FATP | PVT | 2026-03-09 | 13 | -14 | -46091 | 50 | -64 | Late | New Buy |  | Done | FATP-NPI-BM2-MVA2603-23OM | Done | VNPR202603230171 | Done | VNPO202603280076 | 2026-04-25 | Lấy 2x từ 35 con VNPO202604150030 MFG G (180/215) trả đơn trước | EPR2603210007 |  | PQEBarcode Scanner SEUIC HS505DP, USB cable16BM2New BuyFATP-NPI-BM2-MVA2603-23OM | 16 | 16 | 16 | 16
2026-02-24 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 11 | 13640000 | BM2 |  | BM2 | FATP | PVT | 2026-03-09 | 13 | -14 | -46091 |  | -14 | Late | New Buy |  | Done | FATP-NPI-BM2-MVA2602-118OM | Done | 1FSHQ30070 | Done | 1FSHQ30070 |  | 2026-04-29 | EPR2603070006 |  | MFGMonitor 211BM2New BuyFATP-NPI-BM2-MVA2602-118OM | 11 | 11 | 11 | 11
2026-02-24 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Mini PC (Assy) | #N/A | 7800000 | 11 | 85800000 | BM2 |  | BM2 | FATP | PVT | 2026-03-09 | 13 | -14 | -46091 |  | -14 | Late | New Buy |  | Done | FATP-NPI-BM2-MVA2602-118OM | Done | 1FSHQ30071 | Done | 1FSHQ30071 | pending | Lấy hết PO: 1FSHQ30071 cho MFG G // Trả đơn Ban MFG MINI PC ASUS | EPR2603070007: đã cancel // EPR2606240004 |  | MFGMini PC (Assy)11BM2New BuyFATP-NPI-BM2-MVA2602-118OM | 11 | 11 | 11 | 11
2026-02-24 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 10 | 23000000 | BM2 |  | BM2 | FATP | PVT | 2026-03-09 | 13 | -14 | -46091 | 50 | -64 | Late | New Buy |  | Done | FATP-NPI-BM2-MVA2603-23OM | Done | VNPR202603230171 | Done | VNPO202603280076 |  | 2026-05-25 | EPR2603210008 | Wed 3:09 PM | MFGBarcode Scanner SEUIC HS505DP, USB cable10BM2New BuyFATP-NPI-BM2-MVA2603-23OM | 10 | 10 | 10 | 10
2026-02-24 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 4 | 195200000 | BM2 |  | BM2 | FATP | PVT | 2026-03-09 | 13 | -14 | -46091 | 50 | -64 | Late | New Buy |  | Done | FATP-NPI-BM2-MVA2602-118OM | Done | 1FSHQ30072 | Done | 1FSHQ30072 |  | 2026-04-02 | EPR2603070008: Đã out | ( Đã out trước đó / 1FSHQ30072x: PO này về làm spare) | MFGBarcode Printer ZEBRA4BM2New BuyFATP-NPI-BM2-MVA2602-118OM | 4 | 4 | 4 | 4
2026-02-25 | PQE | Nguyen Van Than | V1550929 | thannv@fih-foxconn.com | 3802 | IPC | #N/A | 10870000 | 6 | 65220000 | MH2 |  | MH2 | FATP | PVT | 2026-04-01 | 35 | 2026-06-05 | 100 |  | 2026-06-05 | On time | New Buy | G | Done | FATP-NPI-MH2-MVA2603-09OM | Done | 1FSHQ30125 | Done | 1FSHQ30125 : Lấy hàng trong kho trước ( Hàng trong kho: 1FSHQ10101) / Hàng về làm spare sau |  | 2026-03-26 | EPR2603070009 |  | PQEIPC6MH2New BuyFATP-NPI-MH2-MVA2603-09OM | 6 | 6 | 6 | 6
2026-02-25 | PQE | Nguyen Van Than | V1550929 | thannv@fih-foxconn.com | 3802 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 6 | 7440000 | MH2 |  | MH2 | FATP | PVT | 2026-04-01 | 35 | 2026-06-05 | 100 |  | 2026-06-05 | On time | New Buy |  | Done | FATP-NPI-MH2-MVA2602-119OM | Done | 1FSHQ30029 | Done | 1FSHQ30029 |  | Đã nhận 16.03.2026 | EPR2603070010 |  | PQEMonitor 26MH2New BuyFATP-NPI-MH2-MVA2602-119OM | 6 | 6 | 6 | 6
2026-02-25 | PQE | Nguyen Van Than | V1550929 | thannv@fih-foxconn.com | 3802 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 5 | 11500000 | MH2 |  | MH2 | FATP | PVT | 2026-04-01 | 35 | 2026-06-05 | 100 | 50 | 2026-04-16 | On time | New Buy |  | Done | FATP-NPI-MH2-MVA2603-22OM | Done | VNPR202603230176 | Done | VNPO202603280076 |  | 2026-04-25 | EPR2603210005 | 2026-05-15 14:44 | PQEBarcode Scanner SEUIC HS505DP, USB cable5MH2New BuyFATP-NPI-MH2-MVA2603-22OM | 5 | 5 | 5 | 5
2026-03-02 | TE | Nguyễn Đức Mạnh | V1536673 | manhnd6@fih-foxconn.com |  | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 13 | 243321000 | OR6 EVT |  | OR6 | FATP | EVT | 2026-04-01 | 30 | 2026-02-21 | -9 | 70 | 2025-12-13 | Late | New Buy |  | Done | FATP-NPI-OR6-MVA2603-02OM / SMT-NPI-OR6-MVA2603-15OM | Done | 1FSHQ30093 & 1FSHQ30116 | Done | 1FSHQ30093 & 1FSHQ30116 |  | 2026-04-23 | EPR2603210042 |  | TEIPC+(updated)13OR6New BuyFATP-NPI-OR6-MVA2603-02OM / SMT-NPI-OR6-MVA2603-15OM | 13 | 13 | 13 | 13
2026-03-02 | TE | Nguyen Duc Manh | V1536673 | manhnd6@fih-foxconn.com |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 14 | 17360000 | OR6 EVT |  | OR6 | FATP | EVT | 2026-04-01 | 30 | 2026-02-21 | -9 |  | 2026-02-21 | Late | New Buy |  | Done | FATP-NPI-OR6-MVA2603-02OM / SMT-NPI-OR6-MVA2603-15OM | Done | 1FSHQ30094 / 1FSHQ30117 | Done | 1FSHQ30094 / 1FSHQ30117 |  | 2026-05-12 | EPR2603070021 | 1FSHQ30094 / 1FSHQ30117 ( Lấy hàng trong kho trước 2 PO về làm spare part) | TEMonitor 214OR6New BuyFATP-NPI-OR6-MVA2603-02OM / SMT-NPI-OR6-MVA2603-15OM | 14 | 14 | 14 | 14
2026-03-02 | TE | Nguyen Duc Manh | V1536673 | manhnd6@fih-foxconn.com |  | Mini PC ASUS NUC 15 (TE only) | NUC 15 PRO Tall/ U7-255H/16GB DDR5/512GB NVMe SSD, 3Yrs Wty | 20870000 | 1 | 20870000 | OR6 EVT |  | OR6 | FATP | EVT | 2026-04-01 | 30 | 2026-02-21 | -9 | 50 | 2026-01-02 | Late | New Buy |  | Done | FATP-NPI-OR6-MVA2603-02OM | Done | 1FSHQ30095 | Done | 1FSHQ30095 |  | 2026-03-25 | EPR2603210003 |  | TEMini PC ASUS NUC 15 (TE only)1OR6New BuyFATP-NPI-OR6-MVA2603-02OM | 1 | 1 | 1 | 1
2026-03-02 | TE | Nguyễn Đức Mạnh | V1536673 | manhnd6@fih-foxconn.com |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 13 | 29900000 | OR6 EVT |  | OR6 | FATP | EVT | 2026-04-01 | 30 | 2026-02-21 | -9 | 50 | 2026-01-02 | Late | New Buy |  | Done | FATP-NPI-OR6-MVA2603-24OM | Done | VNPR202604040090 | Done | VNPO202604100231 | 2026-04-25 | 2026-05-04 | EPR2603210014 | 2026-05-04 10:15 | TEBarcode Scanner SEUIC HS505DP, USB cable13OR6New BuyFATP-NPI-OR6-MVA2603-24OM | 13 | 13 | 13 | 13
2026-03-02 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 3 | 41664000 | MH2 |  | MH2 | FATP | PVT |  | -46083 | 2026-06-05 | 95 | 50 | 2026-04-16 | On time | New Buy |  | Done | FATP-NPI-MH2-MVA2603-06OM | Done | 1FSHQ30127 | Done | 1FSHQ30127: Lấy hàng trong kho trước ( Hàng trong kho: 1FSHQ10101) / Hàng về làm spare sau |  | 2026-03-26 | EPR2603070022: Done |  | WHIPC(updated)3MH2New BuyFATP-NPI-MH2-MVA2603-06OM | 3 | 3 | 3 | 3
2026-03-02 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 3 | 5940000 | MH2 |  | MH2 | FATP | PVT |  | -46083 | 2026-06-05 | 95 |  | 2026-06-05 | On time | New Buy |  | Done | FATP-NPI-MH2-MVA2603-06OM | Done | 1FSHQ30124 | Done | 1FSHQ30124 |  | 2026-08-20 | EPR2603070023 |  | WHMonitor 13MH2New BuyFATP-NPI-MH2-MVA2603-06OM | 3 | 3 | 3 | 3
2026-03-02 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | 5800000 | 2 | 11600000 | MH2 |  | MH2 | FATP | PVT |  | -46083 | 2026-06-05 | 95 | 65 | 2026-04-01 | On time | New Buy |  | Done | FATP-NPI-MH2-MVA2603-11OM | Done | VNPR202603130176 | Done | VNPO202603190072 |  | 2026-08-25 | EPR2603070024 |  | WH Barcode Scanner ZEBRA DS8178,USB cable2MH2New BuyFATP-NPI-MH2-MVA2603-11OM | 2 | 2 | 2 | 2
2026-03-02 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 1 | 48800000 | MH2 |  | MH2 | FATP | PVT |  | -46083 | 2026-06-05 | 95 | 50 | 2026-04-16 | On time | New Buy |  | Done | FATP-NPI-MH2-MVA2603-06OM | Done | 1FSHQ30128 | Done | 1FSHQ30128 |  | 2026-05-20 | EPR2603070025 | ( Lây 1x máy ở 1FSHPC0092 trước / hàng về làm spare ) | WHBarcode Printer ZEBRA1MH2New BuyFATP-NPI-MH2-MVA2603-06OM | 1 | 1 | 1 | 1
2026-03-02 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 5 | 77500000 | MH2 |  | MH2 | FATP | PVT |  | -46083 | 2026-06-05 | 95 | 65 | 2026-04-01 | On time | New Buy |  | Done | FATP-NPI-MH2-MVA2603-06OM | Done | VNPR202603130196 | Done | VNPO202603200118 |  | 2026-05-07 | EPR2603070026 | đã out 20may tại vp OM - chị Việt | WHPDA CHAINWAY C61-48505MH2New BuyFATP-NPI-MH2-MVA2603-06OM | 5 | 5 | 5 | 5
2026-03-02 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 3 | 41664000 | AS3 |  | AS3 | FATP | MP |  | -46083 | -14 | -46097 | 50 | -64 | Late | New Buy |  | Done | FATP-MP-AS3-MVA2603-07OM | Done | 1FSHQ30074 | Done | 1FSHQ30074 |  | 26/03/2026 | EPR2603070027: Done |  | WHIPC(updated)3AS3New BuyFATP-MP-AS3-MVA2603-07OM | 3 | 3 | 3 | 3
2026-03-02 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 3 | 5940000 | AS3 |  | AS3 | FATP | MP |  | -46083 | -14 | -46097 |  | -14 | Late | New Buy |  | Done | FATP-MP-AS3-MVA2603-07OM | Done | 1FSHQ30077 | Done | 1FSHQ30077 |  | Đã nhận 20.04 | EPR2603070028 |  | WHMonitor 13AS3New BuyFATP-MP-AS3-MVA2603-07OM | 3 | 3 | 3 | 3
2026-03-02 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | 5800000 | 2 | 11600000 | AS3 |  | AS3 | FATP | MP |  | -46083 | -14 | -46097 | 65 | -79 | Late | New Buy |  | Done | FATP-MP-AS3-MVA2603-12OM | Done | VNPR202603130186 | Done | VNPO202603230130 |  | 2026-04-25 | EPR2603070029 |  | WH Barcode Scanner ZEBRA DS8178,USB cable2AS3New BuyFATP-MP-AS3-MVA2603-12OM | 2 | 2 | 2 | 2
2026-03-02 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 2 | 31000000 | AS3 |  | AS3 | FATP | MP |  | -46083 | -14 | -46097 | 65 | -79 | Late | New Buy |  | Done | FATP-MP-AS3-MVA2603-07OM | Done | VNPR202603110208 | Done | VNPO202603160180 |  | 2026-05-07 | EPR2603070030 | đã out tại OM office 30 May | WHPDA CHAINWAY C61-48502AS3New BuyFATP-MP-AS3-MVA2603-07OM | 2 | 2 | 2 | 2
2026-03-02 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 3 | 41664000 | BM2 |  | BM2 | FATP | PVT |  | -46083 | -14 | -46097 | 50 | -64 | Late | New Buy |  | Done | FATP-NPI-BM2-MVA2602-08OM | Done | 1FSHQ30080 | Done | 1FSHQ30080 |  | Đã nhận 26.03 | EPR2603070031: Done | Lấy hàng spare | WHIPC(updated)3BM2New BuyFATP-NPI-BM2-MVA2602-08OM | 3 | 3 | 3 | 3
2026-03-02 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 3 | 5940000 | BM2 |  | BM2 | FATP | PVT |  | -46083 | -14 | -46097 |  | -14 | Late | New Buy |  | Done | FATP-NPI-BM2-MVA2602-08OM | Done | 1FSHQ30100 | Done | 1FSHQ30100 |  | 2026-04-11 | EPR2603070032 |  | WHMonitor 13BM2New BuyFATP-NPI-BM2-MVA2602-08OM | 3 | 3 | 3 | 3
2026-03-02 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | 5800000 | 3 | 17400000 | BM2 |  | BM2 | FATP | PVT |  | -46083 | -14 | -46097 | 65 | -79 | Late | New Buy |  | Done | FATP-NPI-BM2-MVA2602-13OM | Done | VNPR202603130193 | Done | VNPO202603230130 |  | 2026-04-25 | EPR2603070033 |  | WH Barcode Scanner ZEBRA DS8178,USB cable3BM2New BuyFATP-NPI-BM2-MVA2602-13OM | 3 | 3 | 3 | 3
2026-03-02 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 1 | 48800000 | BM2 |  | BM2 | FATP | PVT |  | -46083 | -14 | -46097 | 50 | -64 | Late | New Buy |  | Done | FATP-NPI-BM2-MVA2602-08OM | Done | 1FSHQ30101 | Done | 1FSHQ30101 |  | 2026-05-20 | EPR2603070034 | ( Lây 1x máy ở 1FSHPC0092 trước / hàng về làm spare ) | WHBarcode Printer ZEBRA1BM2New BuyFATP-NPI-BM2-MVA2602-08OM | 1 | 1 | 1 | 1
2026-03-02 | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | 4478 | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 2 | 31000000 | BM2 |  | BM2 | FATP | PVT |  | -46083 | -14 | -46097 | 65 | -79 | Late | New Buy |  | Done | FATP-NPI-BM2-MVA2602-08OM | Done | VNPR202603110206 | Done | VNPO202603160180 |  | 2026-05-07 | EPR2603070035 | đã out tại OM office 30 May | WHPDA CHAINWAY C61-48502BM2New BuyFATP-NPI-BM2-MVA2602-08OM | 2 | 2 | 2 | 2
2026-03-08 | TE | Nguyen Duc Manh | V1536673 | manhnd6@fih-foxconn.com |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 5 | 6200000 | OR6 EVT |  | OR6 |  | EVT | 2026-04-01 | 24 | #N/A | #N/A |  | #N/A | #N/A | New Buy |  | Done | FATP-NPI-OR6-MVA2603-14OM | Done | 1FSHQ30118 | Done | 1FSHQ30118 |  | 1FSHQ30118 | EPR2603210051 |  | TEMonitor 25OR6New BuyFATP-NPI-OR6-MVA2603-14OM | 5 | 5 | 5 | 5
2026-03-10 | TE | Le Thi Hong Nhung | V1552445 | nhunglth2@fih-foxconn.com | 4179 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 6 | 112302000 | BM2 |  | BM2 | FATP | MP | 2026-04-24 | 45 | 2026-05-07 | 58 | 70 | 2026-02-26 | Late | New Buy |  | Done | FATP-NPI-BM2-MVA2603-16OM | Done | 1FSHQ30133 | Done | 1FSHQ30133 |  | 2026-04-23 | EPR2603210052 |  | TEIPC+(updated)6BM2New BuyFATP-NPI-BM2-MVA2603-16OM | 6 | 6 | 6 | 6
2026-03-10 | TE | Le Thi Hong Nhung | V1552445 | nhunglth2@fih-foxconn.com | 4179 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 6 | 11880000 | BM2 |  | BM2 | FATP | MP | 2026-04-24 | 45 | 2026-05-07 | 58 |  | 2026-05-07 | On time | New Buy |  | Done | FATP-NPI-BM2-MVA2603-16OM | Done | 1FSHQ30134 | Done | 1FSHQ30134 |  | 2026-04-29 | EPR2603240011 |  | TEMonitor 16BM2New BuyFATP-NPI-BM2-MVA2603-16OM | 6 | 6 | 6 | 6
2026-03-10 | TE | Le Thi Hong Nhung | V1552445 | nhunglth2@fih-foxconn.com | 4179 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 6 | 13800000 | BM2 |  | BM2 | FATP | MP | 2026-04-24 | 45 | 2026-05-07 | 58 | 50 | 2026-03-18 | On time | New Buy |  | Done | FATP-NPI-BM2-MVA2603-23OM | Done | VNPR202603230171 | Done | VNPO202603280076 | 2026-04-25 | Lấy 6x từ 35 con VNPO202604150030 MFG G (180/215) trả đơn bù | EPR2603210017 |  | TEBarcode Scanner SEUIC HS505DP, USB cable6BM2New BuyFATP-NPI-BM2-MVA2603-23OM | 6 | 6 | 6 | 6
2026-03-13 | ME | Nguyen Thi Hai | V1516000 | haint2@fih-foxconn.com | 4493 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 100 | 124000000 | OR5 UPH 230 to 300 |  | OR5 | FATP | MP | 2026-03-27 | 14 | -14 | -46108 |  | -14 | Late | New Buy | G | Done | L10-MP-OR5-MVA2603-18OM | Done | 1FSHQ40038 | Done | 1FSHQ40038 | pending |  | EPR2603240012 |  | MEMonitor 2100OR5New BuyL10-MP-OR5-MVA2603-18OM | 100 | 100 | 100 | 0
2026-03-13 | ME | Nguyen Thi Hai | V1516000 | haint2@fih-foxconn.com | 4493 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 16 | 780800000 | OR5 UPH 230 to 300 |  | OR5 | FATP | MP | 2026-03-27 | 14 | -14 | -46108 | 50 | -64 | Late | New Buy | G | Done | L10-MP-OR5-MVA2603-18OM | Done | 1FSHQ40039 | Done | 1FSHQ40039 | 2026-05-12 | Lấy 7x spare out hàng cho ME OR5 trước // out thêm 6x spare đợt 2 ngày 11.05 // lấy 2x 1FSHQ30128 & 1FSHQ30101 // Lấy 1x ở MFG G | EPR2603240013 ( đã trả hết ) |  | MEBarcode Printer ZEBRA16OR5New BuyL10-MP-OR5-MVA2603-18OM | 16 | 16 | 16 | 16
2026-03-13 | ME | Nguyen Thi Hai | V1516000 | haint2@fih-foxconn.com | 4493 | Mini PC (Assy) | #N/A | 7800000 | 99 | 772200000 | OR5 UPH 230 to 300 |  | OR5 | FATP | MP | 2026-03-27 | 14 | -14 | -46108 |  | -14 | Late | New Buy | G | Done | L10-MP-OR5-MVA2603-25OM | Done | 1FSHQ40023 | Done | 1FSHQ40023 | pending | 17x 1FSHQ40023 lấy cho MFG G | EPR2603240014 Cancelled // EPR2606190001 : Lấy hàng ở PO 1FSHQ50347 |  | MEMini PC (Assy)99OR5New BuyL10-MP-OR5-MVA2603-25OM | 99 | 99 | 99 | 99
2026-03-13 | ME | Nguyen Thi Hai | V1516000 | haint2@fih-foxconn.com | 4493 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 160 | 528000000 | OR5 UPH 230 to 300 |  | OR5 | FATP | MP | 2026-03-27 | 14 | -14 | -46108 | 50 | -64 | Late | New Buy | G | Done | L10-MP-OR5-MVA2603-25OM | Done | VNPR202604030189 | Done | VNPO202604070280 | 2026-05-07 | 2026-05-07 | EPR2603210020 | Trả 2 lần : 100 / 60 | MEBarcode Scanner SEUIC HS505HDP-2530 ,USB cable160OR5New BuyL10-MP-OR5-MVA2603-25OM | 160 | 160 | 160 | 160
2026-03-21 | ORT | Nguyen Van Thai | V1552266 | thainv3@fih-foxconn.com | 4141 | Mini PC (Assy) | #N/A | 7800000 | 1 | 7800000 | OR6 EVT |  | OR6 |  | EVT | 2026-03-21 | 0 | #N/A | #N/A |  | #N/A | #N/A | Leverage |  | Done |  | Done |  | Done |  |  | 2026-03-21 | EPR2603210006 |  | ORTMini PC (Assy)1OR6Leverage | 1 | 1 | 1 | 1
2026-03-21 | ORT | Nguyen Van Thai | V1552266 | thainv3@fih-foxconn.com | 4141 | Mini PC (Assy) | #N/A | 7800000 | 1 | 7800000 | OR6 EVT |  | OR6 |  | EVT | 2026-03-21 | 0 | #N/A | #N/A |  | #N/A | #N/A | Leverage |  | Done |  | Done |  | Done |  |  | 2026-03-21 | EPR2603210006 |  | ORTMini PC (Assy)1OR6Leverage | 1 | 1 | 1 | 1
2026-03-21 | ORT | Nguyen Van Thai | V1552266 | thainv3@fih-foxconn.com | 4141 | Mini PC (Assy) | #N/A | 7800000 | 1 | 7800000 | OR6 EVT |  | OR6 |  | EVT | 2026-03-21 | 0 | #N/A | #N/A |  | #N/A | #N/A | Leverage |  | Done |  | Done |  | Done |  |  | 2026-03-21 | EPR2603210006 |  | ORTMini PC (Assy)1OR6Leverage | 1 | 1 | 1 | 1
2026-03-30 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1265000 | 5 | 6325000 | SSF EVT |  | SSF | FATP | EVT |  | -46111 | 2026-04-08 | 9 |  | 2026-04-08 | On time | New Buy | L | Done | FATP-NPI-SSF-MVA2604-73OM | Done | 1FSHQ40303 | Done | 1FSHQ40303 | 2026-06-17 | 2026-06-20 | EPR2604140015 |  | MFG NONG Monitor 25SSFNew BuyFATP-NPI-SSF-MVA2604-73OM | 5 | 5 | 5 | 5
2026-03-30 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 2 | 53504000 | SSF EVT |  | SSF | FATP | EVT |  | -46111 | 2026-04-08 | 9 | 70 | 2026-01-28 | Late | New Buy | L | Done | FATP-NPI-SSF-MVA2604-73OM | Done | 1FSHQ40322 | Done | 1FSHQ40322 |  | 2026-05-14 | EPR2604140016 |  | MFG NONG IPC++(updated)2SSFNew BuyFATP-NPI-SSF-MVA2604-73OM | 2 | 2 | 2 | 2
2026-03-30 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 5 | 11500000 | SSF EVT |  | SSF | FATP | EVT |  | -46111 | 2026-04-08 | 9 | 50 | 2026-02-17 | Late | New Buy | L | Done | FATP-NPI-SSF-MVA2604-73OM | Done | VNPR202604290084 | Done | VNPO202605040213 | 2026-05-25 | 2026-05-30 | EPR2604140017 |  | MFG NONG Barcode Scanner SEUIC HS505DP, USB cable5SSFNew BuyFATP-NPI-SSF-MVA2604-73OM | 5 | 5 | 5 | 5
2026-03-30 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 2 | 97600000 | SSF EVT |  | SSF | FATP | EVT |  | -46111 | 2026-04-08 | 9 | 50 | 2026-02-17 | Late | New Buy | L | Done | FATP-NPI-SSF-MVA2604-73OM | Done | 1FSHQ40323 | Done | 1FSHQ40323 | pending | Lấy hàng trong kho trả trước | EPR2604140018 |  | MFG NONG Barcode Printer ZEBRA2SSFNew BuyFATP-NPI-SSF-MVA2604-73OM | 2 | 2 | 2 | 2
2026-03-30 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 3 | 56151000 | SSF EVT |  | SSF | FATP | EVT |  | -46111 | 2026-04-08 | 9 | 70 | 2026-01-28 | Late | New Buy | L | Done | FATP-NPI-SSF-MVA2604-73OM | Done | 1FSHQ40324 | Done | 1FSHQ40324 |  | 2026-05-14 | EPR2604140019 |  | MFG NONG IPC+(updated)3SSFNew BuyFATP-NPI-SSF-MVA2604-73OM | 3 | 3 | 3 | 3
2026-03-25 | TE | Trần Thị Thanh Thanh | V1558423 | thanhttt@fih-foxconn.com |  | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 1 | 18717000 | SSF EVT |  | SSF | FATP | EVT |  | -46106 | 2026-04-08 | 14 | 70 | 2026-01-28 | Late | New Buy | L | Done | FATP-NPI-SSF-MVA2604-73OM | Done | 1FSHQ40324 | Done | 1FSHQ40324 |  | 2026-05-14 | EPR2604140020 |  | TEIPC+(updated)1SSFNew BuyFATP-NPI-SSF-MVA2604-73OM | 1 | 1 | 1 | 1
2026-03-25 | TE | Trần Thị Thanh Thanh | V1558423 | thanhttt@fih-foxconn.com |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 1 | 2300000 | SSF EVT |  | SSF | FATP | EVT |  | -46106 | 2026-04-08 | 14 | 50 | 2026-02-17 | Late | New Buy | L | Done | FATP-NPI-SSF-MVA2604-73OM | Done | VNPR202604290084 | Done | VNPO202605040213 | 2026-05-25 | 2026-05-30 | EPR2604140021 |  | TEBarcode Scanner SEUIC HS505DP, USB cable1SSFNew BuyFATP-NPI-SSF-MVA2604-73OM | 1 | 1 | 1 | 1
2026-03-25 | TE | Trần Thị Thanh Thanh | V1558423 | thanhttt@fih-foxconn.com |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1265000 | 1 | 1265000 | SSF EVT |  | SSF | FATP | EVT |  | -46106 | 2026-04-08 | 14 |  | 2026-04-08 | On time | New Buy | L | Done | FATP-NPI-SSF-MVA2604-73OM | Done | 1FSHQ40303 | Done | 1FSHQ40303 | 2026-06-17 | 2026-06-20 | EPR2604140022 |  | TEMonitor 21SSFNew BuyFATP-NPI-SSF-MVA2604-73OM | 1 | 1 | 1 | 1
2026-03-31 | IQC | Nguyễn Thị Hiên | V1550665 | hiennt78@fih-foxconn.com | 3321 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 3 | 9900000 | ML2 PVT |  | ML2 | SMT | PVT | 2026-04-30 | 30 | -14 | -46126 | 50 | -64 | Late | New Buy | G | Done | L10-NPI-ML2-MVA2604-01OM | Done | VNPR202604110061 | Done | VNPO202604150301 | 2026-06-20 | 2026-06-20 | EPR2604180004 |  | IQCBarcode Scanner SEUIC HS505HDP-2530 ,USB cable3ML2New BuyL10-NPI-ML2-MVA2604-01OM | 3 | 3 | 3 | 3
2026-03-31 | IQC | Nguyễn Thị Hiên | V1550665 | hiennt78@fih-foxconn.com | 3321 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 1 | 48800000 | ML2 PVT |  | ML2 | SMT | PVT | 2026-04-30 | 30 | -14 | -46126 | 50 | -64 | Late | New Buy | G | Done | L10-NPI-ML2-MVA2604-01OM | Done | 1FSHQ40140 | Done | 1FSHQ40140 | pending | Lấy hàng trong kho trả trước | EPR2604180005 |  | IQCBarcode Printer ZEBRA1ML2New BuyL10-NPI-ML2-MVA2604-01OM | 1 | 1 | 1 | 1
2026-03-31 | IQC | Nguyễn Thị Hiên | V1550665 | hiennt78@fih-foxconn.com | 3321 | Monitor 1 (old) | #N/A | 1980000 | 5 | 9900000 | ML2 PVT |  | ML2 | SMT | PVT | 2026-04-30 | 30 | -14 | -46126 |  | -14 | Late | New Buy | G | Done | L10-NPI-ML2-MVA2604-01OM | Done | 1FSHQ40139 | Done | 1FSHQ40139 | 2026-05-22 | 2026-05-23 | EPR2604180006 |  | IQCMonitor 1 (old)5ML2New BuyL10-NPI-ML2-MVA2604-01OM | 5 | 5 | 5 | 5
2026-03-31 | IQC | Nguyễn Thị Hiên | V1550665 | hiennt78@fih-foxconn.com | 3321 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 5 | 133760000 | ML2 PVT |  | ML2 | SMT | PVT | 2026-04-30 | 30 | -14 | -46126 | 70 | -84 | Late | New Buy | G | Done | L10-NPI-ML2-MVA2604-01OM | Done | 1FSHQ40138 | Done | 1FSHQ40138 |  | 2026-04-29 | EPR2604180007 |  | IQCIPC++(updated)5ML2New BuyL10-NPI-ML2-MVA2604-01OM | 5 | 5 | 5 | 5
2026-04-05 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 10 | 12400000 | ML2 |  | ML2 | FATP | PVT | 2026-04-30 | 25 | 2026-05-05 | 30 |  | 2026-05-05 | On time | New Buy | G | Done | L10-NPI-ML2-MVA2604-05OM | Done | 1FSHQ40166 | Done | 1FSHQ40166 | 2026-06-17 | 2026-06-20 | EPR2604180008 |  | MFG NONG Monitor 210ML2New BuyL10-NPI-ML2-MVA2604-05OM | 10 | 10 | 10 | 10
2026-04-05 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 3 | 146400000 | ML2 |  | ML2 | FATP | PVT |  | -46117 | 2026-05-05 | 30 | 50 | 2026-03-16 | Late | New Buy | G | Done | L10-NPI-ML2-MVA2604-05OM | Done | 1FSHQ40167 | Done | 1FSHQ40167 | pending | Lấy hàng trong kho trả trước | EPR2604180009 |  | MFG NONG Barcode Printer ZEBRA3ML2New BuyL10-NPI-ML2-MVA2604-05OM | 3 | 3 | 3 | 3
2026-04-08 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 2 | 3960000 | OR5 bổ sung 2 line |  | OR5 | FATP | MP |  | -46120 | -14 | -46134 |  | -14 | Late | New Buy |  | Done | L10-MP-OR5-MVA2604-12OM | Done | 1FSHQ40308 | Done | 1FSHQ40308 | 2026-05-22 | 2026-05-23 | EPR2604180010 |  | WHMonitor 12OR5New BuyL10-MP-OR5-MVA2604-12OM | 2 | 2 | 2 | 2
2026-04-08 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | IPC+ | #N/A | 14200000 | 1 | 14200000 | OR5 bổ sung 2 line |  | OR5 | FATP | MP |  | -46120 | -14 | -46134 |  | -14 | Late | New Buy |  | Done | L10-MP-OR5-MVA2604-10OM | Done | 1FSHQ40219 | Done | 1FSHQ40219 |  | 2026-05-14 | EPR2605050001 |  | WHIPC+1OR5New BuyL10-MP-OR5-MVA2604-10OM | 1 | 1 | 1 | 1
2026-04-08 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | 5800000 | 1 | 5800000 | OR5 bổ sung 2 line |  | OR5 | FATP | MP |  | -46120 | -14 | -46134 | 65 | -79 | Late | New Buy |  | Done | L10-MP-OR5-MVA2604-10OM | Done | VNPR202604200082 | Done | VNPO202604240250 | 2026-05-29 | 2026-05-30 | EPR2605050002 |  | WH Barcode Scanner ZEBRA DS8178,USB cable1OR5New BuyL10-MP-OR5-MVA2604-10OM | 1 | 1 | 1 | 1
2026-04-08 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 2 | 97600000 | OR5 bổ sung 2 line |  | OR5 | FATP | MP |  | -46120 | -14 | -46134 | 50 | -64 | Late | New Buy |  | Done | L10-MP-OR5-MVA2604-10OM | Done | 1FSHQ40220 | Done | 1FSHQ40220 | pending | Lấy hàng trong kho trả trước | EPR2605050003 |  | WHBarcode Printer ZEBRA2OR5New BuyL10-MP-OR5-MVA2604-10OM | 2 | 2 | 2 | 2
2026-04-08 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 2 | 3960000 | SSF |  | SSF | FATP | PVT |  | -46120 | -14 | -46134 |  | -14 | Late | New Buy |  | Done | L10-NPI-SSF-MVA2604-13OM | Done | 1FSHQ40309 | Done | 1FSHQ40309 | 2026-05-22 | 2026-05-23 | EPR2605060005 |  | WHMonitor 12SSFNew BuyL10-NPI-SSF-MVA2604-13OM | 2 | 2 | 2 | 2
2026-04-08 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | IPC+ | #N/A | 14200000 | 1 | 14200000 | SSF |  | SSF | FATP | EVT |  | -46120 | 2026-04-08 | 0 |  | 2026-04-08 | On time | New Buy |  | Done | L10-NPI-SSF-MVA2604-11OM | Done | 1FSHQ40218 | Done | 1FSHQ40218 |  | 2026-05-14 | EPR2605050004 | Re-mind pick up | WHIPC+1SSFNew BuyL10-NPI-SSF-MVA2604-11OM | 1 | 1 | 1 | 1
2026-04-08 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | 5800000 | 2 | 11600000 | SSF |  | SSF | FATP | EVT |  | -46120 | 2026-04-08 | 0 | 65 | 2026-02-02 | Late | New Buy |  | Done | L10-NPI-SSF-MVA2604-11OM | Done | VNPR202604200054 | Done | VNPO202604240250 | 2026-05-29 | 2026-05-30 | EPR2605090002 |  | WH Barcode Scanner ZEBRA DS8178,USB cable2SSFNew BuyL10-NPI-SSF-MVA2604-11OM | 2 | 2 | 2 | 2
2026-04-08 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 1 | 15500000 | SSF |  | SSF | FATP | EVT |  | -46120 | 2026-04-08 | 0 | 65 | 2026-02-02 | Late | New Buy |  | Done | L10-NPI-SSF-MVA2604-11OM | Done | VNPR202604200054 | Done | VNPO202604240250 | 2026-05-29 | 2026-05-30 | EPR2605090003 |  | WHPDA CHAINWAY C61-48501SSFNew BuyL10-NPI-SSF-MVA2604-11OM | 1 | 1 | 1 | 1
2026-04-19 | TE | Nguyễn Đức Mạnh | V1536673 | manhnd6@fih-foxconn.com | 4469 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 110 | 2942720000 | FAPT OR6 MP 4 line |  | OR6 | FATP | DVT | 2026-06-01 | 43 | 2026-06-01 | 43 | 70 | 2026-03-23 | Late | New Buy | G | In Progress | FATP-MP-OR6-MVA2605-04OM | Done | 1FSHQ50322 40x 1FSHQ50323 40x 1FSHQ50324 30x | Done | 1FSHQ50322 40x 1FSHQ50323 40x 1FSHQ50324 30x | 2026-06-17 | 2026-05-20 | EPR2605090004 |  | TEIPC++(updated)110OR6New BuyFATP-MP-OR6-MVA2605-04OM | 0 | 110 | 110 | 110
2026-04-19 | TE | Nguyễn Đức Mạnh | V1536673 | manhnd6@fih-foxconn.com | 4469 | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 58 | 1551616000 | SMT OR6 MP 4 line |  | OR6 | SMT | DVT | [7 empty] | New Buy | L | Done | SMT-MP-OR6-MVA2605-36OM | Done | 40x 1FSHQ60008 18x 1FSHQ60010 | Done | 40x 1FSHQ60008 18x 1FSHQ60010 |  |  | EPR2606120012 | Pending Budget + Approval
2026-04-19 | TE | Nguyễn Đức Mạnh | V1536673 | manhnd6@fih-foxconn.com | 4469 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 2020000 | 128 | 258560000 | FAPT OR6 MP 4 line |  | OR6 | FATP | DVT | 2026-06-01 | 43 | 2026-06-01 | 43 |  | 2026-06-01 | On time | New Buy | G | Done | FATP-MP-OR6-MVA2606-07OM | Done | 1FSHQ60151 | Done | 1FSHQ60151 |  |  | EPR2605090005 | Pending Budget + Approval | TEMonitor 1128OR6New BuyFATP-MP-OR6-MVA2606-07OM | 128 | 128 | 128 | 0
2026-04-19 | TE | Nguyễn Đức Mạnh | V1536673 | manhnd6@fih-foxconn.com | 4469 | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 2020000 | 58 | 117160000 | SMT OR6 MP 4 line |  | OR6 | SMT | DVT | [7 empty] | New Buy | G | In Progress | SMT-MP-OR6-MVA2606-08OM | [6 empty] | EPR2606120013 | Pending Budget + Approval
2026-04-19 | TE | Nguyễn Đức Mạnh | V1536673 | manhnd6@fih-foxconn.com | 4469 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 128 | 422400000 | FAPT OR6 MP 4 line |  | OR6 | FATP | DVT | 2026-06-01 | 43 | 2026-06-01 | 43 | 50 | 2026-04-12 | Late | New Buy | G | In Progress | FATP-MP-OR6-MVA2605-04OM | Done | VNPR202605270256 | Done | VNPO202606120173 |  |  | EPR2605090006 | Pending Budget + Approval | TEBarcode Scanner SEUIC HS505HDP-2530 ,USB cable128OR6New BuyFATP-MP-OR6-MVA2605-04OM | 0 | 128 | 128 | 0
2026-04-19 | TE | Nguyễn Đức Mạnh | V1536673 | manhnd6@fih-foxconn.com | 4469 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 58 | 191400000 | SMT OR6 MP 4 line |  | OR6 | SMT | DVT | [7 empty] | New Buy | L | Done | SMT-MP-OR6-MVA2605-36OM | Done | VNPR202606010059 | Done | VNPO202606040129 |  |  | EPR2606110002 | Pending Budget + Approval
2026-04-19 | TE | Nguyễn Đức Mạnh | V1536673 | manhnd6@fih-foxconn.com | 4469 | Mini PC ASUS NUC 15 PRO Tall - APR 2026 | NUC 15 PRO Tall, U7- 255H, 16GB DDR5, 512GB NVMe SSD, 3Yrs Ｗty | 22750000 | 18 | 409500000 | FAPT OR6 MP 4 line |  | OR6 | FATP | DVT | 2026-06-01 | 43 | 2026-06-01 | 43 |  | 2026-06-01 | On time | New Buy | G | Done | FATP-MP-OR6-MVA2605-04OM | Done | 1FSHQ50325 | Done | 1FSHQ50325 | 2026-06-22 | 2026-06-24 | EPR2605090007 |  |  | 18 | 18 | 18 | 18
2026-04-09 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com |  | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 3 | 56151000 | OR6 MP 4 line |  | OR6 | FATP | MP |  | -46121 | 2026-08-10 | 123 | 70 | 2026-06-01 | On time | New Buy | L | In Progress | L10-MP-OR6-MVA2605-06OM | [6 empty] | EPR2605090008 |  | WHIPC+(updated)3OR6New BuyL10-MP-OR6-MVA2605-06OM | 0 | 0 | 0 | 0
2026-04-09 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com |  | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 1980000 | 3 | 5940000 | OR6 MP 4 line |  | OR6 | FATP | MP |  | -46121 | 2026-08-10 | 123 |  | 2026-08-10 | On time | New Buy | L | Done | L10-MP-OR6-MVA2605-06OM | Done | 1FSHQ50150 | Done | 1FSHQ50150 | 2026-05-22 | 2026-05-23 | EPR2605090009 |  | WHMonitor 13OR6New BuyL10-MP-OR6-MVA2605-06OM | 3 | 3 | 3 | 3
2026-04-09 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com |  | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 3 | 46500000 | OR6 MP 4 line |  | OR6 | FATP | MP |  | -46121 | 2026-08-10 | 123 | 65 | 2026-06-06 | On time | New Buy | L | In Progress | L10-MP-OR6-MVA2605-06OM | [6 empty] | EPR2605090010 |  | WHPDA CHAINWAY C61-48503OR6New BuyL10-MP-OR6-MVA2605-06OM | 0 | 0 | 0 | 0
2026-04-09 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com |  | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | 5800000 | 3 | 17400000 | OR6 MP 4 line |  | OR6 | FATP | MP |  | -46121 | 2026-08-10 | 123 | 65 | 2026-06-06 | On time | New Buy | L | In Progress | L10-MP-OR6-MVA2605-06OM | [6 empty] | EPR2605090011 |  | WH Barcode Scanner ZEBRA DS8178,USB cable3OR6New BuyL10-MP-OR6-MVA2605-06OM | 0 | 0 | 0 | 0
2026-04-09 | ME | Nguyễn Thành Luân | V1546250 | luan_nguyen_thanh1@fih-foxconn.com | 3105 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty |  | 40 | 0 | OR6 MP 4 line --> 2 line |  | OR6 | FATP | DVT | 2026-06-01 | 53 | 2026-06-01 | 53 | 70 | 2026-03-23 | Late | New Buy | G | Done | FATP-MP-OR6-MVA2605-37OM | Done | 1FSHQ50333 | Done | 1FSHQ50333 | 2026-06-17 | 2026-06-20 | EPR2606110003 |  | MEIPC+(updated)40OR6New BuyFATP-MP-OR6-MVA2605-37OM | 40 | 40 | 40 | 40
2026-04-09 | ME | Nguyễn Thành Luân | V1546250 | luan_nguyen_thanh1@fih-foxconn.com | 3105 | Mini PC ASUS NUC 14 Essential NUC14MNK150 | NUC 14 Essential NUC14MNK150 Intel N150, Ram 16 GB DDR5,SSD 256GB, Wi-Fi and Bluetooth, NoOS, 3Yrs Wty | 7800000 | 235 | 1833000000 | OR6 MP 4 line --> 2 line |  | OR6 | FATP | DVT | 2026-06-01 | 53 | 2026-06-01 | 53 | 50 | 2026-04-12 | On time | New Buy | G | Done | FATP-MP-OR6-MVA2605-39OM | Done | 1FSHQ50348 | Done | 1FSHQ50348 |  | lấy 500x PO MINI PC bên ASUS trả đơn trước bên MFG G | EPR2606240005 |  | MEMini PC ASUS NUC 14 Essential NUC14MNK150235OR6New BuyFATP-MP-OR6-MVA2605-39OM | 235 | 235 | 235 | 235
2026-04-09 | ME | Nguyễn Thành Luân | V1546250 | luan_nguyen_thanh1@fih-foxconn.com | 3105 | Monitor 2 (old) | #N/A |  | 185 | 0 | OR6 MP 4 line --> 2 line |  | OR6 | FATP | DVT | 2026-06-01 | 53 | 2026-06-01 | 53 |  | 2026-06-01 | On time | New Buy | G | In Progress | FATP-MP-OR6-MVA2606-01OM | Done | 1FSHQ60063 | Done | 1FSHQ60063 |  |  | EPR2606120010 | Pending Budget + Approval | MEMonitor 2 (old)185OR6New BuyFATP-MP-OR6-MVA2606-01OM | 0 | 185 | 185 | 0
2026-04-09 | ME | Nguyễn Thành Luân | V1546250 | luan_nguyen_thanh1@fih-foxconn.com | 3105 | Monitor 1 (old) | #N/A |  | 90 | 0 | OR6 MP 4 line --> 2 line |  | OR6 | FATP | DVT | 2026-06-01 | 53 | 2026-06-01 | 53 |  | 2026-06-01 | On time | New Buy | G | Done | FATP-MP-OR6-MVA2606-07OM | Done | 1FSHQ60151 | Done | 1FSHQ60151 |  |  | EPR2606120011 | Pending Budget + Approval | MEMonitor 1 (old)90OR6New BuyFATP-MP-OR6-MVA2606-07OM | 90 | 90 | 90 | 0
2026-04-09 | ME | Nguyễn Thành Luân | V1546250 | luan_nguyen_thanh1@fih-foxconn.com | 3105 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable |  | 293 | 0 | OR6 MP 4 line --> 2 line |  | OR6 | FATP | DVT | 2026-06-01 | 53 | 2026-06-01 | 53 | 50 | 2026-04-12 | On time | New Buy | G | Done | FATP-MP-OR6-MVA2605-07OM | Done | VNPR202606010079 | Done | VNPO202606040129 |  |  | EPR2606110001 |  | MEBarcode Scanner SEUIC HS505HDP-2530 ,USB cable293OR6New BuyFATP-MP-OR6-MVA2605-07OM | 293 | 293 | 293 | 0
2026-04-09 | ME | Nguyễn Thành Luân | V1546250 | luan_nguyen_thanh1@fih-foxconn.com | 3105 | Barcode Printer ZEBRA | ZT610, 600dpi |  | 26 | 0 | OR6 MP 4 line --> 2 line |  | OR6 | FATP | DVT | 2026-06-01 | 53 | 2026-06-01 | 53 | 50 | 2026-04-12 | On time | New Buy | G | Done | FATP-MP-OR6-MVA2605-07OM | Done | 20x 1FSHQ60017 6x 1FSHQ60019 | Done | 20x 1FSHQ60017 6x 1FSHQ60019 |  |  | EPR2606110007 | Pending Budget + Approval | MEBarcode Printer ZEBRA26OR6New BuyFATP-MP-OR6-MVA2605-07OM | 26 | 26 | 26 | 0
2026-04-17 | FAE | Vu Xuan Bach | V1521896 | bachvx@fih-foxconn.com | 4144 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 11 | 13640000 | OR6 MP 4 lineSetup fixture test for FA area |  | OR6 | FATP | DVT |  | -46129 | 2026-06-01 | 45 |  | 2026-06-01 | On time | New Buy | G | Done | FATP-MP-OR6-MVA2605-03OM | Done | 1FSHQ50227 | Done | 1FSHQ50227 |  | Trả đơn trước từ 92x 1FSHQ50211 | EPR2605220001 |  |  | 11 | 11 | 11 | 11
2026-04-17 | FAE | Vu Xuan Bach | V1521896 | bachvx@fih-foxconn.com | 4144 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 11 | 205887000 | OR6 MP 4 lineSetup fixture test for FA area |  | OR6 | FATP | DVT |  | -46129 | 2026-06-01 | 45 | 70 | 2026-03-23 | Late | New Buy | G | Done | FATP-MP-OR6-MVA2605-03OM | Done | 1FSHQ50226 | Done | 1FSHQ50226 | 2026-06-02 | 2026-06-05 | EPR2605220003 |  |  | 11 | 11 | 11 | 11
2026-04-17 | FAE | Vu Xuan Bach | V1521896 | bachvx@fih-foxconn.com | 4144 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 11 | 36300000 | OR6 MP 4 line Setup fixture test for FA area |  | OR6 | FATP | DVT |  | -46129 | 2026-06-01 | 45 | 50 | 2026-04-12 | Late | New Buy | G | Done | FATP-MP-OR6-MVA2605-03OM | Done | VNPR202605190217 | Done | VNPO202606010194 |  |  | EPR2605250002 |  |  | 11 | 11 | 11 | 0
2026-04-09 | ORT | Nguyễn Văn Thái | V1552266 | thainv3@fih-foxconn.com |  | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty |  | 7 |  | OR6 MP 4 line Setup fixture test for FA area | [13 empty] | Done | L10-MP-OR6-MVA2605-05OM | Done | 1FSHQ50147 | Done | 1FSHQ50147 | 2026-05-22 | 2026-05-23 | EPR2605200002
2026-04-09 | ORT | Nguyễn Văn Thái | V1552266 | thainv3@fih-foxconn.com |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC |  | 9 |  | OR6 MP 4 line Setup fixture test for FA area | [13 empty] | Done | L10-MP-OR6-MVA2605-05OM | Done | 1FSHQ50154 | Done | 1FSHQ50154 |  | Trả đơn trước từ 92x 1FSHQ50211 | EPR2605200001: Done
2026-04-09 | ORT | Nguyễn Văn Thái | V1552266 | thainv3@fih-foxconn.com |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | #N/A | 5 | #N/A | OR6 MP 4 line Setup fixture test for FA area | [5 empty] | -46121 | #N/A | #N/A | 50 | #N/A | #N/A |  |  | Done | L10-MP-OR6-MVA2605-05OM | In Progress | VNPR202605150159 | Done | VNPO202606120173 |  | Lấy stock OM WH trả đơn trước | EPR2605250006 |  |  | 5 | 0 | 5 | 5
2026-04-18 | TE | Nguyen Hai Yen | V1549748 | yennh@fih-foxconn.com |  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 3 | 9900000 |  |  | ML2 | FATP | PVT |  | -46130 | 2026-05-05 | 17 | 50 | 2026-03-16 | Late |  |  | Done | FATP-NPI-ML2-MVA2604-14OM | Done | VNPR202604280015 | Done | VNPO202605040209 |  |  | EPR2605060001 |  |  | 3 | 3 | 3 | 0
2026-04-18 | TE | Nguyen Hai Yen | V1549748 | yennh@fih-foxconn.com |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1265000 | 3 | 3795000 |  |  | ML2 | FATP | PVT |  | -46130 | 2026-05-05 | 17 |  | 2026-05-05 | On time |  | L | Done | FATP-NPI-ML2-MVA2604-14OM | Done | 1FSHQ40300 | Done | 1FSHQ40300 |  | Trả đơn trước từ 92x 1FSHQ50211 | EPR2605250003 |  |  | 3 | 3 | 3 | 3
2026-04-18 | TE | Nguyen Hai Yen | V1549748 | yennh@fih-foxconn.com |  | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 3 | 80256000 |  |  | ML2 | FATP | PVT |  | -46130 | 2026-05-05 | 17 | 70 | 2026-02-24 | Late |  | L | Done | FATP-NPI-ML2-MVA2604-14OM | Done | 1FSHQ40301 | Done | 1FSHQ40301 |  | 2026-05-14 | EPR2605130001 |  |  | 3 | 3 | 3 | 3
2026-04-25 | ME | Nguyen Que Hung | V1542733 | hungnq4@fih-foxconn.com | 3542 | Mini PC ASUS NUC 15 PRO Tall - APR 2026 | NUC 15 PRO Tall, U7- 255H, 16GB DDR5, 512GB NVMe SSD, 3Yrs Ｗty | 22750000 | 18 | 409500000 | Set up OR5 MP 4 line |  | OR5 | FATP | MP |  | -46137 | -14 | -46151 |  | -14 | Late |  | L | Done | FATP-MP-OR5-MVA2605-19OM | Done | 1FSHQ50213 | Done | 1FSHQ50213 | 2026-05-27 | 2026-05-27 | EPR2605230001 |  |  | 18 | 18 | 18 | #REF!
2026-05-04 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1265000 | 9 | 11385000 | Use for MA4 |  | MA4 | FATP | DVT |  | -46146 | #VALUE! | #VALUE! |  | #VALUE! | #VALUE! |  | L | In Progress | FATP-NPI-MA4-MVA2605-01OM | Done | 1FSHQ50218 | Done | 1FSHQ50218 |  | Trả đơn trước từ 92x 1FSHQ50211 | EPR2605250004: Done |  |  | 0 | 9 | 9 | 9
2026-05-04 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 9 | 124992000 | Use for MA4 |  | MA4 | FATP | DVT | [9 empty] | Done | FATP-NPI-MA4-MVA2605-01OM | Done | 1FSHQ50219 | Done | 1FSHQ50219 | 2026-06-02 | 2026-06-05 | EPR2605250005
2026-05-04 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 9 | 20700000 | Use for MA4 |  | MA4 | FATP | DVT | [9 empty] | Done | FATP-NPI-MA4-MVA2605-01OM | Done | VNPR202605190171 | Done | VNPO202605210256 |  | Lấy 9x từ 35 con VNPO202604150030 MFG G (180/215) trả đơn trước | EPR2605250007
2026-05-04 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 2 | 97600000 | Use for MA4 |  | MA4 | FATP | DVT | [9 empty] | Done | FATP-NPI-MA4-MVA2605-01OM | Done | 1FSHQ50220 | Done | 1FSHQ50220 |  |  | EPR2605250008
2026-05-04 | PQE | Vũ Đăng Hoạch | V1546253 | hoachvd@fih-foxconn.com |  | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1265000 | 5 | 6325000 | Use for MA4 PVT |  | MA4 | FATP | DVT | [9 empty] | Done | L10-NPI-MA4-MVA2605-02OM | Done | 1FSHQ50222 | Done | 1FSHQ50222 |  | Trả đơn trước từ 92x 1FSHQ50211 | EPR2605250009
2026-05-04 | PQE | Vũ Đăng Hoạch | V1546253 | hoachvd@fih-foxconn.com |  | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 3 | 41664000 | Use for MA4 PVT |  | MA4 | FATP | DVT | [9 empty] | Done | L10-NPI-MA4-MVA2605-02OM | Done | 1FSHQ50221 | Done | 1FSHQ50221 | 2026-06-02 | 2026-06-05 | EPR2605250010
2026-05-04 | PQE | Vũ Đăng Hoạch | V1546253 | hoachvd@fih-foxconn.com |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 5 | 11500000 | Use for MA4 PVT |  | MA4 | FATP | DVT | [9 empty] | Done | L10-NPI-MA4-MVA2605-02OM | Done | VNPR202605190177 | Done | VNPO202605210256 |  | Lấy 5x từ 35 con VNPO202604150030 MFG G (180/215) trả đơn trước | EPR2605250011
[7 empty] | #N/A | #N/A |  | #N/A | [6 empty] | 0 | #N/A | #N/A |  | #N/A | #N/A | [13 empty] | 0 | 0 | 0 | 0
2026-05-02 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | Monitor 1 (old) | #N/A | #N/A | 3 | #N/A | MA4 |  | MA4 | FATP | PVT | [7 empty] | New Buy |  | Done | L10-NPI-MA4-MVA2605-12OM | Done | 1FSHQ50214 | Done | 1FSHQ50214 |  |  | EPR2605250001 |  |  | 3 | 3 | 3 | 0
2026-05-02 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 3 | 41664000 | MA4 |  | MA4 | FATP | PVT | [7 empty] | New Buy |  | Done | L10-NPI-MA4-MVA2605-12OM | Done | 1FSHQ50215 | Done | 1FSHQ50215 | 2026-06-02 | 2026-06-05 | EPR2605250012 |  |  | 3 | 3 | 3 | 3
2026-05-02 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | 5800000 | 2 | 11600000 | MA4 |  | MA4 | FATP | PVT | [7 empty] | New Buy |  | Done | L10-NPI-MA4-MVA2605-12OM | Done | VNPR202605190111 | Done | VNPO202605210251 |  |  | EPR2605250013 |  |  | 2 | 2 | 2 | 0
2026-05-02 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 2 | 97600000 | MA4 |  | MA4 | FATP | PVT | [7 empty] | New Buy |  | Done | L10-NPI-MA4-MVA2605-12OM | Done | 1FSHQ50216 | Done | 1FSHQ50216 |  |  | EPR2605250014 |  |  | 2 | 2 | 2 | 0
2026-05-02 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | Monitor 1 (old) | #N/A | #N/A | 3 | #N/A | OR6 MP 4 line Setup fixture test for FA area |  | OR6 | FATP | MP | [7 empty] | New Buy |  | Done | L10-MP-OR6-MVA2605-06OM | Done | 1FSHQ50150 | Done | 1FSHQ50150 |  | 2026-05-22 | EPR2605250015
2026-05-02 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 3 | 41664000 | OR6 MP 4 line Setup fixture test for FA area |  | OR6 | FATP | MP | [7 empty] | New Buy |  | Done | L10-MP-OR6-MVA2605-06OM | Done | 1FSHQ50146 | Done | 1FSHQ50146 |  | 2026-05-23 | EPR2605200003 - cancel? / EPR2605230009
2026-05-02 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | 5800000 | 3 | 17400000 | OR6 MP 4 line Setup fixture test for FA area |  | OR6 | FATP | MP | [7 empty] | New Buy |  | Done | L10-MP-OR6-MVA2605-06OM | Done | VNPR202605150167 | Done | VNPO202605190337 | 2026-05-26 | 2026-05-30 | EPR2605250016
2026-05-02 | WH | Lê Thị Lịch | V1525678 | lichlt@fih-foxconn.com | 4478 | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | 15500000 | 3 | 46500000 | OR6 MP 4 line Setup fixture test for FA area |  | OR6 | FATP | MP | [7 empty] | New Buy |  | Done | L10-MP-OR6-MVA2605-06OM | Done | VNPR202605150166 | Done | VNPO202606120174 |  |  | EPR2605260001
2026-05-06 | IQC | Nguyễn Thị Hiên | V1550665 | hiennt78@fih-foxconn.com | 3321 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 1 | 48800000 |  |  | OR6 | FATP | MP | [7 empty] | New Buy |  | Done | L10-MP-OR6-MVA2605-06OM | Done | 1FSHQ50141 | In Progress | 1FSHQ50141 |  |  | EPR2605260002 |  |  | 1 | 1 | 0 | 0
2026-05-06 | ME | Nguyễn Anh Thư | V1525145 | thuna@fih-foxconn.com | 3605 | Monitor (White)+ ARM | HKC MB24V7-W, 23.8 inch White, With Bracket Arm Warrior WA-MH0802 (White) | 1815000 | 15 | 27225000 | Set up OR5 MP 4 line |  | OR5 | FATP | MP | [7 empty] | New Buy | G | Done | FATP-MP-OR5-MVA2605-08OM | Done | 1FSHQ50166 | Done | 1FSHQ50166 |  |  | EPR2605060006 ( Mua mới ) / EPR2606030001: Lấy 2x trả trước 4CS4 Demo line |  |  | 15 | 15 | 15 | 0
2026-05-06 | ME | Nguyễn Anh Thư | V1525145 | thuna@fih-foxconn.com | 3605 | Mini PC ASUS NUC 15 PRO Tall - APR 2026 | NUC 15 PRO Tall, U7- 255H, 16GB DDR5, 512GB NVMe SSD, 3Yrs Ｗty | 22750000 | 15 | 341250000 | Set up OR5 MP 4 line |  | OR5 | FATP | MP | [7 empty] | New Buy | G | Done | FATP-MP-OR5-MVA2605-08OM | Done | 1FSHQ50167 | Done | 1FSHQ50167 | 2026-05-19 |  | EPR2605190001: Done |  |  | 15 | 15 | 15 | 0
2026-05-06 | IQC | Nguyễn Thị Hiên | V1550665 | hiennt78@fih-foxconn.com | 3321 | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | 5800000 | 5 | 29000000 | BM2 MP |  | BM2 | FATP | MP | 2026-05-25 | [6 empty] | New Buy | G | Done | FATP-MP-BM2-MVA2605-16OM | Done | VNPR202605190110 | Done | VNPO202605210251 |  |  | EPR2605110019 |  |  | 5 | 5 | 5 | 0
2026-05-06 | PQE | Vũ Đăng Hoạch | V1546253 | hoachvd@fih-foxconn.com | 24006 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1265000 | 12 | 15180000 | BM2 MP |  | BM2 | FATP | MP | [7 empty] | New Buy | G | Done | FATP-MP-BM2-MVA2605-16OM | Done | 1FSHQ50211 | Done | 1FSHQ50211 |  | Trả đơn trước từ 92x 1FSHQ50211 | EPR2605110018 |  |  | 12 | 12 | 12 | 12
2026-05-06 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1265000 | 17 | 21505000 | BM2 MP |  | BM2 | FATP | MP | [7 empty] | New Buy | G | Done | FATP-MP-BM2-MVA2605-16OM | Done | 1FSHQ50211 | Done | 1FSHQ50211 |  | Trả đơn trước từ 92x 1FSHQ50211 | EPR2605110017 |  |  | 17 | 17 | 17 | 17
2026-05-06 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | IPC(updated) | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 13888000 | 17 | 236096000 | BM2 MP |  | BM2 | FATP | MP | [7 empty] | New Buy | G | Done | FATP-MP-BM2-MVA2605-16OM | Done | 1FSHQ50210 | Done | 1FSHQ50210 | 2026-06-02 | 2026-06-05 | EPR2605110016 |  |  | 17 | 17 | 17 | 17
2026-05-06 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 18 | 41400000 | BM2 MP |  | BM2 | FATP | MP | [7 empty] | New Buy | G | Done | FATP-MP-BM2-MVA2605-16OM | Done | VNPR202605190112 | Done | VNPO202605210256 |  | Lấy stock OM WH trả đơn trước | EPR2605110015 |  |  | 18 | 18 | 18 | 18
2026-05-06 | MFG NONG | Đặng thị Ban | V1547168 | bandt1@fih-foxconn.com | 4324 | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 4 | 195200000 | BM2 MP |  | BM2 | FATP | MP | [7 empty] | New Buy | G | Done | FATP-MP-BM2-MVA2605-16OM | Done | 1FSHQ50212 | Done | 1FSHQ50212 | 2026-06-12 | 2026-06-13 | EPR2605110014 |  |  | 4 | 4 | 4 | 4
2026-05-09 | ME | Nguyễn Quế Hưng | V1542733 | hungnq4@fih-foxconn.com | 3542 | Mini PC ASUS NUC 15 PRO Tall - APR 2026 | NUC 15 PRO Tall, U7- 255H, 16GB DDR5, 512GB NVMe SSD, 3Yrs Ｗty | 22750000 | 30 | 682500000 | Set up OR5 MP 4 line |  | OR5 | FATP | MP | [7 empty] | New Buy | L | Done | FATP-MP-OR5-MVA2605-19OM | Done | 1FSHQ50213 | Done | 1FSHQ50213 | 2026-05-27 | 2026-05-27 | EPR2605110013 |  |  | 30 | 30 | 30 | 30
2026-05-12 | IQC | Nguyễn Thị Hiên | V1550665 | hiennt78@fih-foxconn.com | 3321 | Monitor 1 (old) | #N/A | #N/A | 3 | #N/A | SSF EVT1.1 |  | SSF | FATP | EVT | [7 empty] | New Buy | G | Done | L10-NPI-SSF-MVA2605-21OM | Done | 1FSHQ50256 | Done | 1FSHQ50256 |  |  | EPR2605230002 |  |  | 3 | 3 | 3 | 0
2026-05-12 | IQC | Nguyễn Thị Hiên | V1550665 | hiennt78@fih-foxconn.com | 3321 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 3 | 56151000 | SSF EVT1.1 |  | SSF | FATP | EVT | [7 empty] | New Buy | G | Done | L10-NPI-SSF-MVA2605-21OM | Done | 1FSHQ50255 | Done | 1FSHQ50255 | 2026-06-02 | 2026-06-05 | EPR2605230003 |  |  | 3 | 3 | 3 | 3
2026-05-12 | IQC | Nguyễn Thị Hiên | V1550665 | hiennt78@fih-foxconn.com | 3321 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 3 | 9900000 | SSF EVT1.1 |  | SSF | FATP | EVT | [7 empty] | New Buy | G | Done | L10-NPI-SSF-MVA2605-21OM | Done | VNPR202605220119 | Done | VNPO202606120157 |  |  | EPR2605230004 |  |  | 3 | 3 | 3 | 0
2026-05-16 | IQC | Nguyễn Thị Hiên | V1550665 | hiennt78@fih-foxconn.com | 3321 | Monitor 1 (old) | #N/A | #N/A | 10 | #N/A | OR6 DVT |  | OR6 | FATP | DVT | 2026-05-31 | 15 | [5 empty] | New Buy | L | Done | L10-MP-OR6-MVA2605-29OM | Done | 1FSHQ50299 | Done | 1FSHQ50299 |  |  | EPR2605260003 |  |  | 10 | 10 | 10 | 10
2026-05-16 | IQC | Nguyễn Thị Hiên | V1550665 | hiennt78@fih-foxconn.com | 3321 | IPC+(updated) | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 18717000 | 10 | 187170000 | OR6 DVT |  | OR6 | FATP | DVT | 2026-05-31 | 15 | [5 empty] | New Buy | L | Done | L10-MP-OR6-MVA2605-29OM | Done | 1FSHQ50300 | Done | 1FSHQ50300 | 2026-06-17 | 2026-06-20 | EPR2605260004 |  |  | 10 | 10 | 10 | #REF!
2026-05-16 | IQC | Nguyễn Thị Hiên | V1550665 | hiennt78@fih-foxconn.com | 3321 | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | 5800000 | 6 | 34800000 | OR6 DVT |  | OR6 | FATP | DVT | 2026-05-31 | 15 | [5 empty] | New Buy | L | Done | L10-MP-OR6-MVA2605-29OM | Done | VNPR202605260105 | Done | VNPO202606120169 |  |  | EPR2605260005 |  |  | 6 | 6 | 6 | 0
2026-05-18 | ME | Trịnh Hồng Đức | V1520599 | ducthfih-foxconn.com | 23382 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 12 | 39600000 | OR5 MP |  | OR5 | FATP | MP | 2026-05-23 | 5 | [5 empty] | New Buy | G | Done | FATP-MP-OR5-MVA2605-30OM | Done | VNPR202605250211 | Done | VNPO202606120168 |  |  | EPR2605230005 |  |  | 12 | 12 | 12 | 0
2026-05-18 | ME | Trịnh Hồng Đức | V1520599 | ducthfih-foxconn.com | 23382 | Barcode Printer ZEBRA | Barcode Printer ZEBRA ZT610, 600dpi | 48800000 | 12 | 585600000 | OR5 MP |  | OR5 | FATP | MP | 2026-05-23 | 5 | [5 empty] | New Buy | G | Done | FATP-MP-OR5-MVA2605-30OM | Done | 1FSHQ50291 | Done | 1FSHQ50291 |  |  | EPR2605230006 |  |  | 12 | 12 | 12 | 0
2026-05-18 | ME | Trịnh Hồng Đức | V1520599 | ducthfih-foxconn.com | 23382 | Monitor 1 (old) | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1265000 | 12 | 15180000 | OR5 MP |  | OR5 | FATP | MP | 2026-05-23 | 5 | [5 empty] | New Buy | G | Done | FATP-MP-OR5-MVA2605-30OM | Done | 1FSHQ50290 | Done | 1FSHQ50290 / Trả đơn trước |  | Lấy hàng ở RQ trả đơn trước: 12x 1FSHQ30255 ( PO chị Xuân ENG2) | EPR2605230007 |  |  | 12 | 12 | 12 | 12
2026-05-18 | ME | Trịnh Hồng Đức | V1520599 | ducthfih-foxconn.com | 23382 | Mini PC ASUS NUC 15 PRO Tall - APR 2026 | NUC 15 PRO Tall, U7- 255H, 16GB DDR5, 512GB NVMe SSD, 3Yrs Ｗty | 22750000 | 12 | 273000000 | OR5 MP |  | OR5 | FATP | MP | 2026-05-23 | 5 | [5 empty] | New Buy | G | Done | FATP-MP-OR5-MVA2605-30OM | Done | 1FSHQ50292 | Done | 1FSHQ50292 | 2026-06-03 | 2026-06-06 | EPR2605230008 |  |  | 12 | 12 | 12 | 12
2026-05-25 | PQE | Phạm Văn Hiệp | V1524537 | hieppv@fih-foxconn.com | 24461 | Mini PC ASUS NUC 14 Essential NUC14MNK150 | NUC 14 Essential NUC14MNK150 Intel N150, Ram 16 GB DDR5,SSD 256GB, Wi-Fi and Bluetooth, NoOS, 3Yrs Wty | 9680000 | 6 | 58080000 | OR6 MP |  | OR6 | FATP | MP | [7 empty] | New Buy | G | Done | FATP-MP-OR6-MVA2605-39OM | Done | 1FSHQ50348 | Done | 1FSHQ50348 |  | 2026-06-26 | EPR2606110009 : lấy PO 500x MINI PC trả đơn trước |  |  | 6 | 6 | 6 | 6
2026-05-25 | PQE | Phạm Văn Hiệp | V1524537 | hieppv@fih-foxconn.com | 24461 | Monitor 2 (old) | #N/A | #N/A | 6 | #N/A | OR6 MP |  | OR6 | FATP | MP | [7 empty] | New Buy | G | Done | L10-MP-OR6-MVA2605-35OM | Done | 1FSHQ60042 | Done | 1FSHQ60042 |  | Lấy stock OM WH trả đơn trước | EPR2606100001 |  |  | 6 | 6 | 6 | 6
2026-05-25 | PQE | Phạm Văn Hiệp | V1524537 | hieppv@fih-foxconn.com | 24461 | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | 3300000 | 2 | 6600000 | OR6 MP |  | OR6 | FATP | MP | [7 empty] | New Buy | G | Done | L10-MP-OR6-MVA2605-35OM | Done | VNPR202606040073 | Done | VNPO202606100088 |  | Lấy stock OM WH trả đơn trước | EPR2606110008 |  |  | 2 | 2 | 2 | 2
2026-06-01 | TE | Lê Thị Hồng Nhung | V1552445 | nhunglth2@fih-foxconn.com |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 3 | 6900000 | BM2 MP | P26 | BM2 | SMT | MP | [7 empty] | New Buy | L | Done | SMT-MP-BM2-MVA2605-43OM | Done | VNPR202606090270 | Done | VNPO202606120145 |  | Lấy stock OM WH trả đơn trước | EPR2606120006 |  |  | 3 | 3 | 3 | 3
2026-06-11 | TE | Trần Thị Thanh Thanh | V1558423 | thanhttt@fih-foxconn.com |  | IPC+(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 13 | 347776000 | SSF DVT | P26 | SSF | FATP | DVT | [7 empty] | New Buy | L | In Progress | FATP-NPI-SSF-MVA2606-06OM | Done | 1FSHQ60131 | Done | 1FSHQ60131 |  |  | EPR2606120007 |  |  | 0 | 13 | 13 | 0
2026-06-11 | TE | Trần Thị Thanh Thanh | V1558423 | thanhttt@fih-foxconn.com |  | Monitor 2 (old) | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | 1240000 | 14 | 17360000 | SSF DVT | P26 | SSF | FATP | DVT | [7 empty] | New Buy | L | In Progress | FATP-NPI-SSF-MVA2606-06OM | Done | 1FSHQ60132 | Done | 1FSHQ60132 |  | Lấy 21x / 48x 1FSHQ40032 trả đơn truoc | EPR2606120008 |  |  | 0 | 14 | 14 | 14
2026-06-11 | TE | Trần Thị Thanh Thanh | V1558423 | thanhttt@fih-foxconn.com |  | Barcode Scanner SEUIC HS505DP, USB cable | SEUIC, HS505DP-2530, USB cable | 2500000 | 21 | 52500000 | SSF DVT | P26 | SSF | FATP | DVT | [7 empty] | New Buy | L | In Progress | FATP-NPI-SSF-MVA2606-06OM | Done | VNPR202606160065 | Done | VNPO202606230081 |  |  | EPR2606120009 |  |  | 0 | 21 | 21 | 0
2026-06-15 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com |  | All-in-One AOC (SSF) | All-in-One Desktop PC AOC A24A33-2FN2N8F/74 // CPU N95 ¦ Ram 8G ¦ SSD 256G ¦ IPS 23.8 inch FHD ¦ Color: Black Warranty: 03 Years | 13088000 | 13 | 170144000 | SSF DVT | P26 | SSF | FATP | DVT | [7 empty] | New Buy | G | Done | FATP-NPI-SSF-MVA2606-11OM | [9 empty] | 13 | 0 | 0 | 0
2026-06-15 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 13 | 29900000 | SSF DVT | P26 | SSF | FATP | DVT | [7 empty] | New Buy | G | Done | FATP-NPI-SSF-MVA2606-11OM | Done | VNPR202606220290 | Done | VNPO202606240089 | [5 empty] | 13 | 13 | 13 | 0
2026-06-15 | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com |  | Barcode Printer ZEBRA | ZT610, 600dpi | 48800000 | 2 | 97600000 | SSF DVT | P26 | SSF | FATP | DVT | [7 empty] | New Buy | G | Done | FATP-NPI-SSF-MVA2606-11OM | Pending | Hold PR | [7 empty] | 2 | 0 | 0 | 0
2026-06-20 | MFG | Nguyễn Văn Doanh | V1501972 | doanh.nguyen-van@fih-foxconn.com | 23222 | All-in-One SingPC M22Vi512H8M2-W | SingPC M22Vi512H8M2-W , i5-12450H, Ram 8GB, SSD 256GB, 21.5inch Key-Mouse, WiFi, Bluetooth | 16280000 | 3 | 48840000 |  |  | OR5 | FATP | MP | [7 empty] | New Buy | G | In Progress | FATP-MP-OR5-MVA2606-38OM | [9 empty] | 0 | 0 | 0 | 0
2026-06-24 | TE | Lê Thị Hồng Nhung | V1552445 | nhunglth2@fih-foxconn.com |  | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | 26752000 | 18 | 481536000 | BM2-MP |  | BM2 | SMT | MP | [7 empty] | New Buy | G | In Progress | SMT-MP-BM2-MVA2606-41OM | [9 empty] | 0 | 0 | 0 | 0
2026-06-24 | TE | Lê Thị Hồng Nhung | V1552445 | nhunglth2@fih-foxconn.com |  | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | 2020000 | 12 | 24240000 | BM2-MP |  | BM2 | SMT | MP | [7 empty] | New Buy | G | In Progress | SMT-MP-BM2-MVA2606-41OM | [9 empty] | 0 | 0 | 0 | 0
2026-06-24 | TE | Lê Thị Hồng Nhung | V1552445 | nhunglth2@fih-foxconn.com |  | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | 2300000 | 20 | 46000000 | BM2-MP |  | BM2 | SMT | MP | [7 empty] | New Buy | G | In Progress | SMT-MP-BM2-MVA2606-41OM | [9 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
#N/A
576
Formulas:
Request Deadline = S2-[Total Leadtime]

## NONG Project Timeline-OPM updat
Rule: MVA EQ in-house date will be 2weeks earlier than each stage Date of each stage = OPM release
| Brand | 1st stage | 2nd stage | 3rd stage | 4th stage | 5th stage | 6th stage
|  | P1.0 | P1.1 | EVT | DVT | PVT | MP
Project | Phase | Date | Date | Date | Date | Date | Date | OPM DRI | Mail approved Budget
MH2 | SMT |  |  |  |  | 2026-06-18 |  | Sơn Ngô OPM
MH2 | FATP |  |  |  |  | 2026-06-19 |  | Nguyễn Hạnh Donna-OPM
OR5 | SMT | [6 empty] | Phung_Thi_Anh@fih-foxconn.com
OR5 | FATP | [6 empty] | Mary Hạnh Nguyễn - OPM
OR6 | SMT |  |  | 2026-03-10 | 2026-06-08 | 2026-07-20 | 2026-08-17 | Trung Hoàng (Howard - OPM FATP)
OR6 | FATP |  |  | 2026-03-07 | 2026-06-15 | 2026-07-27 | 2026-08-24 | Trung Hoàng (Howard - OPM FATP)
SSF | SMT |  |  | 2026-04-15
SSF | FATP |  |  | 2026-04-22 |  |  |  | Lani Than
Snowball | SMT | [5 empty] | 2026-04-13
Snowball | FATP | [5 empty] | 2026-04-20 | Lani Than
AS3 | SMT | [6 empty] | thuptq@fih-foxconn.com
AS3 | FATP | [6 empty] | Thuy Thuy Windy
LD8 | SMT | [6 empty] | Hieu Nguyen Thi Thanh(DMS_SMT) <hieuntt@fih-foxconn.com>
LD8 | FATP |  |  |  |  | 2026-06-01 |  | Thao Vuong
BM2 | SMT | [5 empty] | 2026-06-29 | hauntt@fih-foxconn.com
BM2 | FATP | [5 empty] | 2026-05-21 | Thao Vuong
ML2 | SMT | [6 empty] | Hieu Nguyen Thi Thanh(DMS_SMT) <hieuntt@fih-foxconn.com>
ML2 | FATP |  |  |  |  | 2026-05-19 |  | Thao Vuong
AS4 | SMT |  |  |  | 2026-03-21 |  |  | Tracy
AS4 | FATP |  |  |  | 2026-03-30 |  |  | Tracy
IS1 | SMT
MA4 | FATP |  |  |  | 28/05/2026 | 28/05/2026 |  | Thuy Thuy Windy
MA4 | SMT | [6 empty] | Thuy Thuy Windy

## Pivot để check coi 2 worksheet (hidden)
| G Project |  |  | G Project |  |  | NonG Project | NonG Project
|  | counta | Column 1 | Column 3 | All Project | counta
1 | 4CS4 | 5 |  | 1 | 4CS4 | 43
2 | 4CS4 FATP | 1 |  | 2 | ASK5 | 11
3 | 4CS4 SMT | 1 |  | 3 | CGY4 | 38
4 | 4CS4 SVR line | 4 |  | 4 | KSH5 | 14
5 | AS3 | 4 |  | 5 | MCN5 | 9
6 | ASK5 FATP P1.0 | 1 | số lượng ko trùng | 6 | MCN6 | 1
7 | ASK5 SMT P1.0 | 2 | khác tên, số lượng | 7 | MCN7 | 1
8 | BM2 | 13 |  | 8 | MCN8 | 1
9 | BM2 | 3 |  | 9 | MCN9 | 1
10 | BM2 MP | 6 | bên kia ko có | 10 | MT5 | 2
11 | CGY4 | 6 |  | 11 | PKK4 | 24
12 | CGY4 FATP | 1 |  | 12 | WGO5 | 12
13 | CGY4 P26 demo line | 4 | SVR Line?? | 13 | AS3 | 4
14 | CGY4 SMT | 1 |  | 14 | BM2 | 22
15 | CGY4 SVR line | 4 | đủ | 15 | LD8 | 18
16 | KSH5 FATP P1.0 | 1 | bbênkia ko có? | 16 | MA4 | 11
17 | KSH5 SMT P1.0 | 2 |  | 17 | MH2 | 14
18 | LD8 | 12 |  | 18 | ML2 | 9
19 | MA4 | 4 |  | 19 | OR5 | 15
20 | MCN5 FATP Proto | 3 | ko trùng số lg | 20 | OR6 | 37
21 | MCN5 FATP Proto1 | 7 | kkotrungf số lg | 21 | SSF | 12
22 | MCN5 Proto | 1 |  |  | Sum (Total) | 299
23 | MH2 | 5
24 | MH2 | 9
25 | ML2 | 2
26 | ML2 PVT | 4 | -- check ts đây
27 | MP line 3 | 4
28 | MP line 3 | 6
29 | Mua bù 1x ENG1 | 2
30 | NB for MP P26 | 6
31 | OR5 bổ sung 2 line | 4
32 | OR5 DVT | 4
33 | OR5 UPH 230 to 300 | 4
34 | OR6 EVT | 15
35 | OR6 MP 4 line | 14
36 | OR6 MP 4 line Setup fixture test for FA area | 8
37 | OR6 MP 4 lineSetup fixture test for FA area | 1
38 | OR6 MP 4 lineSetup fixture test for FA area | 1
39 | Order for Q station on Line LD8-NPI | 3
40 | Order for test station on Line LD8-NPI | 3
41 | P1 for F27 / FATP | 1
42 | P1 for F27 / SMT | 1
43 | P1 for P27 | 3
44 | P25 service | 2
45 | P26 | 2
46 | P26 Demo Line | 6
47 | P26 FATP MP 4CS4 | 1
48 | P26 FATP MP 4CS4 Service line | 2
49 | P26 FATP MP CGY4 | 1
50 | P26 FATP MP CGY4Service line | 2
51 | P26 FATP MP PKK4Service line | 2
52 | P26 MP | 9
53 | P26 service | 1
54 | P26 SMT MP 4CS4 | 1
55 | P26 SMT MP CGY4 | 1
56 | P26 SMT service 4CS4 | 2
57 | P26 SMT service CGY4 | 2
58 | P26 SMT service PKK4 | 2
59 | P27 P1.0 | 9
60 | PC for Auto charging machine P26 | 9
61 | PKK4 | 4
62 | PKK4 SVR line | 4
63 | Proto (ASK5) | 5
64 | Proto (KSH5) | 5
65 | Proto (WGO5)) | 5
66 | Service MP 4CS4 | 3
67 | Service MP CGY4 | 3
68 | Service MP PKK4 | 3
69 | Set up OR5 MP 4 line | 3
70 | SSF | 4
71 | SSF EVT | 8
72 | Use for MA4 | 4
73 | Use for MA4 PVT | 3
74 | WGO5 FATP P1.0 | 1
75 | WGO5 SMT P1.0 | 2
76 | Sum (Total) | 297

## DRI input Rq
Gg Project | [5 empty] | Non Gg project
MFG | To Thi Phuong Anh | V1524505 | anhttp@fih-foxconn.com | 4327 |  | FAE | Vu Xuan Bach | V1521896 | bachvx@fih-foxconn.com |  | bachvx@fih-foxconn.com
QA | Ngô Thị Hoa | V1524668 | hoant3@fih-foxconn.com |  |  | WH | Le Thi Lich | V1525678 | lichlt@fih-foxconn.com | x
TE | Nguyen Trung Kien | V1524574 | kiennt1@fih-foxconn.com |  |  | ME | Nguyen Thi Hai | V1516000 | haint2@fih-foxconn.com | x
ENG3 | Nguyen Van Huynh | V1536667 | huynhnv2@fih-foxconn.com | 4500 | x | PQE | Nguyen Thi Phuong | V1544473 | phuongnt18@fih-foxconn.com | x
REL | Laymu Chen | 504000 | LaymuTHChen@fih-foxconn.com |  |  | TE | Nguyen Hai Yen | V1549748 | yennh@fih-foxconn.com | x
GG-WH | Nguyen Thi Viet | V1524536 | Vietnt@fih-foxconn.com | 4478 |  | MFG | Đặng Thị Ban | V1547168 | bandt1@fih-foxconn.com | x
ENG1 | Ngo Van Duong | v1523845 | duongnv2@fih-foxconn.com | 4328 |  | IQC | Nguyễn Thị Hiền | V1524357 | hiennt3@fih-foxconn.com | x
GG-PQE | Phạm Thị Bích | V1524485 | Bich_Kate IPQC | 3040 |  | PQE | Vũ Đăng Hoạch | V1546253 | hoachvd@fih-foxconn.com | x
TE | Nguyen Ngoc Huyen | V1549412 | huyennn1@fih-foxconn.com | 4440 | x | PQE | Nguyen Van Than | V1550929 | thannv@fih-foxconn.com | x
ENG2 | Đỗ Thị Xuân | V1536196 | xuandt99@fih-foxconn.com | 4347 |  | TE | Nguyen Duc Manh | V1536673 | manhnd6@fih-foxconn.com
ENG3 | Phạm Van Hùng | V1544999 | hungpv3@fih-foxconn.com | 4500 | x | TE | Le Thi Hong Nhung | V1552445 | nhunglth2@fih-foxconn.com | x
ENG1 | Nguyễn Đức Hưng | V1538465 | hungnd7@fih-foxconn.com |  | x | GG-PQE | Nguyen Anh Thai | V1544017 | thaina@fih-foxconn.com | x
REL | Đường Kim Quy | V1538557 | quydk@fih-foxconn.com | 4337 |  | TE | Lê Phi Yến | V1542548 | yenlp@fih-foxconn.com | x
GG-PQE(GTW) | Nguyen Anh Thai | V1544017 | thaina@fih-foxconn.com | 24422 |  | IQC | Nguyễn Văn Ngọc | V1540332 | ngocnv5@fih-foxconn.com | x
[6 empty] | FAE | Trần Ngọc Tiến | V1524847 | tientn@fih-foxconn.com | x
[6 empty] | ORT | Nguyen Van Thai | V1552266 | thainv3@fih-foxconn.com | x
[6 empty] | TE | Ngô Thị Anh | V1550422 | anhnt40@fih-foxconn.com | x
[6 empty] | TE | Vi Thị Phương Oanh | V1549294 | oanh.vi-thi.phuong1@fih-foxconn.com | x
[6 empty] | IQC | Nguyễn Thị Hiên | V1550665 | hiennt78@fih-foxconn.com | x
[6 empty] | ME | Nguyễn Thành Luân | V1546250 | luan_nguyen_thanh1@fih-foxconn.comx | x

## Pivot Table 1
Year Project | Project | Item | Department | Quantity | BG Done | PR Done | PO Done | Arrived
| 4CS4 | Barcode Printer ZEBRA | MFG | 20 | #NAME?
|  | Barcode Scanner SEUIC HS505DP, USB cable | MFG | 160
|  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | ENG1 | 1
|  |  | MFG | 6
|  |  | QA G -PQC | 26
|  | IPC+(updated) | ENG3 | 3
|  | IPC++(updated) | TE SMT | 38
|  |  | TE FATP | 65
|  | Mini PC (Assy) | MFG | 163
|  | Monitor 2 | QA G -PQC | 33
|  |  | MFG | 138
| CGY4 | Barcode Printer ZEBRA | MFG | 31
|  | Barcode Scanner SEUIC HS505DP, USB cable | MFG | 180
|  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | MFG | 7
|  | IPC+(updated) | ENG3 | 3
|  | IPC++(updated) | TE SMT | 36
|  |  | TE FATP | 76
|  | Mini PC (Assy) | MFG | 184
|  | Monitor (White)+ ARM | MFG | 149
|  | Monitor 2 | MFG | 35
| PKK4 | Barcode Printer ZEBRA | MFG | 21
|  | Barcode Scanner SEUIC HS505DP, USB cable | MFG | 31
|  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | ENG1 | 1
|  | IPC+(updated) | ENG3 | 3
|  | Mini PC (Assy) | MFG | 31
|  | Monitor 2 | MFG | 31
Total
F27 | MCN5 | Barcode Scanner SEUIC HS505DP, USB cable | GG-PQE | 10
|  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | IQC | 2
|  |  | FAE | 3
|  |  | TE | 12
|  | IPC+(updated) | GG-PQE | 5
|  | IPC++(updated) | TE | 2
|  |  | TE | 10
|  | Monitor 1 | GG-PQE | 5
F27 Total
P25 Service line |  | Barcode Printer ZEBRA | ENG1 | 7
|  | PDA CHAINWAY C61-4850 | ENG1 | 1
P25 Service line Total
P26 |  | IPC | REL | 2
|  | Monitor 2 | REL | 7
| 4CS4 | Barcode Printer ZEBRA | GG-WH | 2
|  | IPC(updated) | ENG1 | 1
|  |  | QA G -PQC | 33
|  | IPC+ | ENG3 | 5
|  | IPC+(updated) | GG-WH | 4
|  | Mini PC (Assy) | ENG2 | 12
|  | Mini PC ASUS NUC 14 Essential NUC14MNK150 (TE P26 MP ONLY) | TE | 1
|  |  | TE | 26
|  | Monitor 1 | GG-WH | 5
|  | Monitor 2 | ENG1 | 1
|  |  | ENG2 | 12
| CGY4 | Barcode Printer ZEBRA | GG-WH | 2
|  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | QA G -PQC | 31
|  | IPC(updated) | ENG1 | 1
|  |  | QA G -PQC | 38
|  | IPC+ | ENG3 | 5
|  | IPC+(updated) | GG-WH | 5
|  | Mini PC (Assy) | ENG2 | 12
|  | Mini PC ASUS NUC 14 Essential NUC14MNK150 (TE P26 MP ONLY) | TE | 1
|  |  | TE | 22
|  | Monitor 1 | GG-WH | 4
|  | Monitor 2 | ENG1 | 1
|  |  | ENG2 | 12
|  |  | QA G -PQC | 38
| PKK4 | Barcode Printer ZEBRA | GG-WH | 2
|  | IPC(updated) | ENG1 | 1
|  | IPC+ | ENG3 | 5
|  | IPC+(updated) | GG-WH | 3
|  | Monitor 2 | ENG1 | 1
P26 Total
P26 Demo Line | 4CS4 | Mini PC (Assy) | TE | 6
|  |  | QA | 23
|  |  | MFG | 49
|  | Monitor (White)+ ARM | QA | 23
|  |  | TE | 29
|  |  | MFG | 49
P26 Demo Line Total
P26 Service line |  | PDA CHAINWAY C61-4850 | ENG1 | 1
| 4CS4 | Barcode Scanner ZEBRA DS8178,USB cable | GG-WH | 1
|  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | TE | 2
|  |  | GG-PQE | 19
|  | IPC(updated) | GG-PQE | 21
|  | IPC+(updated) | GG-WH | 3
|  | IPC++(updated) | TE | 10
|  | Mini PC (Assy) | ENG2 | 1
|  | Monitor 1 | GG-WH | 3
|  | Monitor 2 | ENG2 | 1
|  |  | GG-PQE | 21
|  | PDA CHAINWAY C61-4850 | GG-WH | 1
| CGY4 | Barcode Scanner ZEBRA DS8178,USB cable | GG-WH | 1
|  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | TE | 2
|  | IPC+(updated) | GG-WH | 3
|  | IPC++(updated) | TE | 10
|  | Mini PC (Assy) | ENG2 | 1
|  | Monitor 1 | GG-WH | 3
|  | Monitor 2 | ENG2 | 1
|  | PDA CHAINWAY C61-4850 | GG-WH | 1
| PKK4 | Barcode Scanner ZEBRA DS8178,USB cable | GG-WH | 1
|  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | TE | 2
|  |  | GG-PQE | 20
|  | IPC(updated) | GG-PQE | 21
|  | IPC+(updated) | GG-WH | 3
|  | IPC++(updated) | TE | 10
|  | Mini PC (Assy) | ENG2 | 1
|  | Monitor 1 | GG-WH | 3
|  | Monitor 2 | ENG2 | 1
|  |  | GG-PQE | 21
|  | PDA CHAINWAY C61-4850 | GG-WH | 1
P26 Service line Total
P27 |  | IPC+(updated) | REL | 2
|  | Monitor 2 | REL | 4
|  | Monitor VA2432-MHD-3, 24 inch Full HD | REL | 3
| ASK5 | Barcode Printer ZEBRA | MFG | 18
|  | Barcode Scanner SEUIC HS505DP, USB cable | MFG | 75
|  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | MFG | 6
|  |  | TE | 7
|  | IPC++(updated) | TE | 67
|  | Mini PC (Assy) | MFG | 93
|  | Monitor 2 | MFG | 93
| KSH5 | Barcode Printer ZEBRA | MFG | 15
|  | Barcode Scanner SEUIC HS505DP, USB cable | MFG | 68
|  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | MFG | 6
|  |  | TE | 7
|  | IPC++(updated) | TE | 67
|  | Mini PC (Assy) | MFG | 93
|  | Monitor 2 | MFG | 93
| WGO5 | Barcode Printer ZEBRA | MFG | 18
|  | Barcode Scanner SEUIC HS505DP, USB cable | MFG | 72
|  | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | MFG | 6
|  |  | TE | 7
|  | IPC++(updated) | TE | 65
|  | Mini PC (Assy) | MFG | 92
|  | Monitor 2 | MFG | 92
P27 Total
Grand Total

## Sheet9
PO | Estimate ETA | Actual ETA | Quantity received
1FSHPB0065 |  |  | 4
1FSHPB0061 |  |  | 23
1FSHPB0062 |  |  | 7
1FSHPB0063 |  |  | 6
1FSHPB0087 1FSHPB0088 |  | Đã nhận 56x ( 6.01) | 56
1FSHPB0094 |  | Đã nhận hàng 17/1 | 145
VNPO202512020099 |  | đã nhận 22/12/2025 | 42
1FSHPB0112 |  | Đã nhận hàng 23/12/2025 | 18
1FSHPB0115 1FSHPB0114 |  | 1FSHPB0115 1/7/2026 1FSHPB0114 30/01/2026 | 815
VNPO202512020099 |  | đã nhận 22/12/2025 | 124
1FSHPB0149 1FSHPB0148 1FSHPB0145 1FSHPB0147 |  | Đã nhận 23-24 | 585
VNPO202512020018 |  | đã nhận 22/12/2025 | 510
1FSHPB0107 1FSHPB0106 |  | Đã nhận 23-24 | 224
VNPO202512020075 |  | đã nhận 27/12/2025 | 292
VNPO202511250247 |  | đã nhận 22/12/2025 | 5
1FSHPB0090 |  | Đã nhận 3/1/2026 | 352
VNPO202511280083 |  | Đã nhận 27/12/2025 | 50
1FSHPB0098 |  | Đã nhận 30.01.2026 | 10
VNPO202512020075 |  | đã nhận 27/12/2025 | 235
|  | đã nhận 22/12/2025 | 7
1FSHPB0091 |  | Đã nhận 23-24 | 130
1FSHPB0118 1FSHPB0119 |  | Đã nhận 25.02.2025 | 139
1FSHPB0117 |  | Đã nhận 15.01.2025 | 12
1FSHPB0113 |  | Đã nhận 23-24 | 10
VNPO202512020098 |  | đã nhận 22/12/2025 | 315
1FSHPB0129 1FSHPB0128 1FSHPB0130 |  | đã nhận hàng 19/1 | 163
VNPO202512100087 |  | Đã nhận 11.02.2026 | 20
VNPO202512100087 |  | Đã nhận 07.03.2026 | 12
1FSHPB0131 1FSHPB0132 1FSHPB0135 1FSHPB0133 1FSHPB0134 1FSHPB0137 |  | đã nhận hàng 19/1 | 331
190x VNPO202511280091 300x VNPO202511280107 300x VNPO202511280105 300x VNPO202511280106 |  | 190x VNPO202511280091 (đã nhận 06.1) 300x VNPO202511280107 (đã nhận 06.1) 300x VNPO202511280105 300x VNPO202511280106 ( 06.01 - 108pcs- tt nhận 104) | 1090
VNPO202512170063 |  | Đã nhận 11.02.2026 | 37
VNPO202512170063 |  | Đã nhận 07.03.2026 | 10
1FSHPB0124 |  | đã nhận 23.11.2025 | 3
VNPO202512020088 |  | đã nhận 27.11 | 20
VNPO202512110008 |  | Đã nhận 26.01.2026 | 2
1FSHPC0097 |  | Đã nhận 29.12.2025 | 3
VNPO202512220159 |  | Đã nhận 02.02.2026 | 92
VNPO202512220176 |  | Đã nhận 28.01.2026 | 58
VNPO202512220175 |  | Đã nhận 11.02.2026 | 5
1FSHPC0092 |  | Đã nhận 26.2.2026 | 18
VNPO202512220175 |  | Đã nhận 26.02.2026 | 87
1FSHPC0093 |  |  | 92
1FSHQ10080 |  | Đã nhận 11.03.2026 | 92
1FSHQ10078 |  | Đã nhận 20.04 | 23
1FSHQ10079 |  | Đã nhận 20.04 | 79
1FSHPC0118 |  | đã nhận 34x+60x 08.01.2026 | 34
VNPO202512230202 |  | Đã nhận 28.01.2026 | 2
1FSHQ10033 |  | Đã nhận 30.01.2026 | 3
1FSHQ10034 |  | Đã nhận 19.1 / OM keep in OM WH | 3
1FSHQ10040 |  | Đã nhận 26.2.2026 | 4
VNPO202601130267 |  | Đã nhận 22.01.2026 | 60
VNPO202601080117 |  | Đã nhận 15.1 | 10
VNPO202601080117 |  | Đã nhận 15.1 | 10
VNPO202601080117 |  | Đã nhận 15.1 | 10
1FSHQ10048 |  | Đã nhận 26.02.2026 / Mua bổ sung request cho TE làm spare | 4
VNPO202601130350 |  | Đã nhận 11.02.2026 / Mua bổ sung request cho FAE làm spare | 3
VNPO202601130349 |  | Đã nhận 27.01.2026 | 60
VNPO202602130022 |  | Đã nhận 13.3 | 2
1FSHQ10057 |  | Đã nhận | 4
VNPO202601150152 |  | Đã nhận 28.1 | 1
VNPO202601160039 |  | Đã nhận 28.1 | 1
VNPO202601160041 |  | Đã nhận 23.1 | 1
VNPO202601160041 |  | Đã nhận 23.1 | 1
VNPO202601160040 |  | Đã nhận 22.1 | 1
VNPO202601200226 |  | Đã nhận 26.01 | 3
1FSHQ10101 |  | Đã nhận 03.02.2026 | 80
1FSHQ10102 |  | Đã nhận 26.02.2026 | 80
VNPO202602110038 | Không nhận hàng => check xử lý với chị Thảo GI GR như thế nào (cần giấy tờ gì để GI/GR) |  | 1
VNPO202602130022 |  | Đã nhận 21.03.2026 | 1
VNPO202604070281 |  | Đã nhận 16.4 | 1
VNPO202604110050 | đã nhận hàng (test)
1FSHQ10133 |  | Đã nhận 03.02.2026 | 2
1FSHQ10134 |  | Đã nhận 12.02.2026 | 4
1FSHQ10132 |  | Đã nhận 11.02.2026 / EPR2602020007 | 2
1FSHQ10118 |  | Đã nhận 11.03.2026 | 78
1FSHQ20008 1FSHQ20010 1FSHQ20009 | còn1FSHQ20008 120 1FSHQ20010 40 | Đã nhận 1FSHQ20009 120x 1FSHQ20010 80x | 200
1FSHQ20012 (PO) 1FSHQ20011 (PO) 1FSHQ20015 (PO) 1FSHQ20013 (PO) |  | 1FSHQ20012 Đã nhận 26.02.2026 1FSHQ20011 Đã nhận 10.04.2026 (2x+ 88x =90) 1FSHQ20015 Đã nhận 10.04.2026: ok 1FSHQ20013 Đã nhận 10.04.2026:ok | 360
1FSHQ20007 |  | Đã nhận 02.04.2026 | 16
VNPO202602090105 |  | Đã nhận 26.02.2026 29x Đã nhận 27.03.2026 301x | 330
1FSHQ10126 |  | Đã nhận 11.02.2026 | 15
1FSHQ10131 |  | Đã nhận 8x - 11.03 72x - 21.04 | 80
1FSHQ20004 |  | Đã nhận 11.02.2026 | 4
1FSHQ20006 |  | Đã nhận 12.02.2026 | 4
1
1FSHQ20036 |  | Đã nhận 12.03.2026 | 4
VNPO202602110021 |  | Đã nhận 13.03.2026 | 27
VNPO202602110021 |  | Đã nhận 13.03.2026 | 3
1FSHQ20037 |  | Đã nhận 26.02.2026 | 3
1FSHQ20038 |  | Đã nhận 16.03.3026 | 32
1FSHQ20039 |  | Đã nhận 05.03.2026 | 8
1FSHQ20040 |  | Đã nhận 05.03.2026 | 1
1FSHQ20029 |  | Đã nhận 23.02.2026 | 27
VNPO202602110021 | Vendor báo 5/5 hàng về
VNPO202604150065 | 15-20 May 2026
1FSHQ20106 |  | Đã nhận 16.03.2026 | 18
1FSHQ20104 |  |  | 18
VNPO202603120086 |  | Đã nhận 19.03.2026 | 92
1FSHQ30023 |  | Đã nhận 16.03.2026 | 3
1FSHQ30070 | Dự kiến 29/4
1FSHQ30072 |  | Đã nhận 02.04.2026 | 4
1FSHQ30029 |  | Đã nhận 16.03.2026 | 6
VNPO202603260041
40x 1FSHQ30073 40x 1FSHQ30075 40x 1FSHQ30076 21x 1FSHQ30078 |  | 40x 1FSHQ30073 đã nhận 13.04 40x 1FSHQ30075 đã nhận 13.04 40x 1FSHQ30076 đã nhận 13.04 21x 1FSHQ30078 đã nhận 13.04 | 141
1FSHQ30093 |  | Đã nhận 23/04 | 9
1FSHQ30094
1FSHQ30095 |  | Đã nhận 26.03.2026 | 1
1FSHQ30084 | Dự kiến 29/4
1FSHQ30071
1FSHQ30085
1FSHQ30087
1FSHQ30096 | Dự kiến T5
100x 1FSHQ30097 63x 1FSHQ30098
1FSHQ30099
1FSHQ30102 | Dự kiến 29/4
100x 1FSHQ30103 84x 1FSHQ30108
20x 1FSHQ30106 11x 1FSHQ30107
1FSHQ30105 |  | Đã nhận 20.04 | 149
1FSHQ30127 |  | Đã nhận 26.03 | 3
1FSHQ30124 |  | Đã nhận 20.04 | 3
1FSHQ30128
VNPO202603200118 | Vendor báo 5/5 hàng về
1FSHQ30074 |  | Đã nhận 26.03 | 3
1FSHQ30077 |  | Đã nhận 20.04 | 3
VNPO202603160180 | Vendor báo 5/5 hàng về
1FSHQ30080 |  | Đã nhận 26.03 3 1FSHQ30100 3 VNPO202603160180 Vendor báo 5/5 hàng về 1FSHQ30101 1FSHQ30125 6 1FSHQ30119 3 1FSHQ30126 Đã nhận 23/04 3 VNPO202603190072 Đã nhận 25.04 2 VNPO202603230130 Đã nhận 25.04 2 VNPO202603230130 Đã nhận 25.04 3 1FSHQ30118 1FSHQ30116 Đã nhận 23/04 4 1FSHQ30117 Dự kiến 29/04 1FSHQ30133 Đã nhận 23/04 6 1FSHQ30134 Dự kiến 29/04 1FSHQ30201
1FSHQ30200" |  |  | 74
1FSHQ40038
1FSHQ40039
1FSHQ30273
1FSHQ30274 |  |  | 1
1FSHQ30275 |  |  | 1
1FSHQ30276 |  |  | 1
1FSHQ30277 |  |  | 1
1FSHQ30278 |  |  | 1
VNPO202603280076 |  | Đã nhận 25.04 | 18
VNPO202603280076 |  | Đã nhận 25.04 | 8
VNPO202603280076 |  | Đã nhận 25.04 | 32
VNPO202604100231 |  | Đã nhận 25.04 | 13
1FSHQ40023
VNPO202604070280 | Dự kiến 07/05 hàng về
1FSHQ40045
VNPO202604160163 | Dự kiến 25/05 hàng về
1FSHQ40046 |  |  | 33
1FSHQ40007 | Dự kiến 29/04
VNPO202604070280 | Dự kiến 07/05 hàng về
1FSHQ40009 |  |  | 38
VNPO202604160162 | Dự kiến 25/05 hàng về
VNPO202604160165 | Dự kiến 25/05 hàng về
VNPO202604160165 | Dự kiến 25/05 hàng về
VNPO202604160167 | Dự kiến 25/05 hàng về
VNPO202604160167 | Dự kiến 25/05 hàng về
1FSHQ40076 | Đã nhận 23/04 |  | 7
1FSHQ40077 | Dự kiến 29/04
VNPO202604110048 | Vendor báo 5/5 hàng về
VNPO202604110048
VNPO202604150301 | Dự kiến 25/05 hàng về
VNPO202604020122 | Dự kiến giữaT5
VNPO202604020122 | Dự kiến giữaT5
VNPO202604020128 | Dự kiến giữaT5
VNPO202604020128 | Dự kiến giữaT5
VNPO202604020123 | Dự kiến 24.04.2026
VNPO202604070280 | Dự kiến 07/05 hàng về
1FSHQ30271 |  |  | 26
1FSHQ30272 |  |  | 22
1FSHQ40064
VNPO202604150088 | Dự kiến 25/05 hàng về
1FSHQ40065 |  |  | 21
1FSHQ40066
VNPO202604150088 | Dự kiến 25/05 hàng về
1FSHQ40067 |  |  | 21
1FSHQ40069
VNPO202604150088 | Dự kiến 25/05 hàng về
1FSHQ40070 |  |  | 21
1FSHQ40025
1FSHQ40030
VNPO202604100259 |  | Đã nhận 25.04 | 51
VNPO202604100259 | Dự kiến 07/05 hàng về
1FSHQ40031
1FSHQ40027
1FSHQ40028
VNPO202604150301 | Dự kiến 25/05 hàng về
VNPO202604150301 | Dự kiến 25/05 hàng về
1FSHQ40029
1FSHQ40032
VNPO202604150301 | Dự kiến 25/05 hàng về
VNPO202604150301 | Dự kiến 25/05 hàng về
1FSHQ40034
1FSHQ40058 | Dự kiến 29/04
1FSHQ40057 | Đã nhận 23/04 |  | 3
VNPO202603310112 | Vendor báo 5/5 hàng về
VNPO202603310112 |  | Đã nhận 25.04 | 1
1FSHQ40061 | Dự kiến 29/04
1FSHQ40059 | Đã nhận 23/04 |  | 3
VNPO202603310112 | Vendor báo 5/5 hàng về
VNPO202603310112 |  | Đã nhận 25.04 | 1
1FSHQ40063 | Dự kiến 29/04
1FSHQ40062 | Đã nhận 23/04 |  | 3
VNPO202603310112 | Vendor báo 5/5 hàng về
VNPO202603310112 |  | Đã nhận 25.04 | 1
1FSHQ30255
1FSHQ30258
1FSHQ30253
1FSHQ30256
1FSHQ30252 |  |  | 1
1FSHQ30254 |  |  | 1
VNPO202604130136 | Dự kiến 07/05 hàng về
VNPO202604130136 | Dự kiến 07/05 hàng về
1FSHQ40011
1FSHQ40013 |  |  | 3
1FSHQ40014 |  |  | 10
1FSHQ40078 |  |  | 2
1FSHQ40047
1FSHQ40049
1FSHQ40052
1FSHQ40071 |  |  | 10
VNPO202604110046 | Dự kiến 07/05 hàng về
1FSHQ40072 |  |  | 10
VNPO202604110046 | Dự kiến 07/05 hàng về
1FSHQ40073 |  |  | 10
VNPO202604110046 | Dự kiến 07/05 hàng về
VNPO202604070282
VNPO202604070283
VNPO202604100289
VNPO202604100289
VNPO202604100289
VNPO202604100289
1FSHQ40120
VNPO202604150030 | Dự kiến 07/05 hàng về
VNPO202604150030 | Dự kiến 07/05 hàng về
1FSHQ40122
1FSHQ40123
VNPO202604150030 | Dự kiến 25/05 hàng về
VNPO202604150030 | Dự kiến 07/05 hàng về
1FSHQ40125
1FSHQ40126
VNPO202604150030 | Dự kiến 25/05 hàng về
VNPO202604150030 | Dự kiến 07/05 hàng về
1FSHQ40128
VNPO202604210080
1FSHQ40132 | Dự kiến 29/04
1FSHQ40133 |  | Đã nhận 23/04 | 4
1FSHQ40134 | Dự kiến 29/04
1FSHQ40135 |  | Đã nhận 23/04 | 5
1FSHQ40136 | Dự kiến 29/04
1FSHQ40137 |  | Đã nhận 23/04 | 3
1FSHQ40138 |  | Đã nhận 29/04 | 5
VNPO202604150301 | Dự kiến 25/05 hàng về
1FSHQ40139
1FSHQ40140
1FSHQ40168
VNPO202604200198
VNPO202604200198
1FSHQ40166
1FSHQ40167
25.0x 1FSHQ40227 40.0x 1FSHQ40226
VNPO202604240250
VNPO202604240250
VNPO202604240250

## Bidding list 26
[16 empty] | P27-P1.1-SMT (FBU) | P27-P1.1-FATP (FBU)
Big Cagetory | Small Category | CPU | RAM | SSD | Request No | Spec (Model name, dimension, accessory,...) | Vendor Name/ Vendor Code | Unit price (VND) | Bidding effective date | Bidding Expiry date | Department | Remark | Vendor's leadtime (days) | Leadtime process Budget/PR/PO | Total Leadtime | 2026-07-05 | 2026-07-13
[16 empty] | Request deadline | Request deadline
Monitor | Monitor HKC MB24V7-W |  |  |  | AIDB-I25121968793 / HIDP-I25122607765 | HKC MB24V7-W, 23.8 inch white display, IPS, 100Hz,3Yrs | VVN0010296 CÔNG TY TNHH HTC | 1550000 | 2026-01-16 | 2026-07-31 |  |  | 60 | 20 | 80 | 2026-04-16 | 2026-04-24
Monitor | Monitor MB24V7-W, 23.8 inch White, With Bracket Arm Warrior |  |  |  | AIDB-I25120962198 / HIDP-I25122708407 | MB24V7-W, 23.8 inch White, With Bracket Arm Warrior WA-MH0802 (White) | VVN0010296 CÔNG TY TNHH HTC | 1815000 | 2026-01-16 | 2026-07-31 |  |  | 60 | 20 | 80 | 2026-04-16 | 2026-04-24
Scanner | Barcode Scanner NEWLAND HH220-HD, USB cable |  |  |  | 0809001-0100041 | NEWLAND HH220-HD, USB cable | VVN0010378 CONG TY TNHH THUONG MAI VA DICH VU TONG HOP TAN HUNG HA | 2400000 | 2026-01-03 | 2026-07-31 |  | 2900000 | 15 | 20 | 35 | 2026-05-31 | 2026-06-08
Scanner | Barcode Scanner SEUIC HS505DP, USB cable |  |  |  | AIDB-I26020493841 / AIDB-I25111044470 | HS505DP, USB cable | VVN0011431 CÔNG TY TNHH CÔNG NGHỆ THÔNG MINH SHARETECH VIỆT NAM | 2300000 | 2026-03-10 | 2026-07-31 |  | 2500000 | 30 | 20 | 50 | 2026-05-16 | 2026-05-24
Scanner | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable |  |  |  | AIDB-I26020493841 / AIDB-I25110743647 | SEUIC HS505HDP-2530 ,USB cable | VVN0011431 CÔNG TY TNHH CÔNG NGHỆ THÔNG MINH SHARETECH VIỆT NAM | 3300000 | 2026-03-10 | 2026-07-31 |  | 3500000 | 30 | 20 | 50 | 2026-05-16 | 2026-05-24
Scanner | Barcode Scanner ZEBRA DS8178,USB cable |  |  |  | AIDB-I25111346919/ HIDP-I25111986293 | ZEBRA DS8178,USB cable PCS Wireless Scanner | VVN0011431 CÔNG TY TNHH CÔNG NGHỆ THÔNG MINH SHARETECH VIỆT NAM | 5800000 | 2026-01-03 | 2026-07-31 |  | 6300000 | 45 | 20 | 65 | 2026-05-01 | 2026-05-09
Printer | Barcode Printer ZEBRA |  |  |  | HIDP-I25070918630 | ZT610, 600dpi | VVN0011455 CÔNG TY TNHH KHOA HỌC ĐIỆN TỬ QUAN THỤY | 48800000 | 2026-01-03 | 2026-07-31 |  | 57500000 | 30 | 20 | 50 | 2026-05-16 | 2026-05-24
Printer | Barcode Printer ZEBRA (new) |  |  |  | HIDP-I26051976818 | ZT610, 600dpi | VVN0011455 CÔNG TY TNHH KHOA HỌC ĐIỆN TỬ QUAN THỤY | 52300000 | 2026-06-01 | 2026-07-31 |  | 57500000 | 30 | 20 | 50 | 2026-05-16 | 2026-05-24
Monitor + ARM | Monitor (White)+ ARM |  |  |  |  | HKC MB24V7-W, 23.8 inch White, With Bracket Arm Warrior WA-MH0802 (White) | VVN0010296 CÔNG TY TNHH HTC | 1815000 |  |  |  | 2815000 | 60 | 20 | 80 | 2026-04-16 | 2026-04-24
Monitor | Monitor (White) |  |  |  |  | HKC MB24V7-W, 23.8 inch White | VVN0010296 CÔNG TY TNHH HTC | 1550000 |  |  |  |  | 60 | 20 | 80 | 2026-04-16 | 2026-04-24
PC | Mini PC (Assy NUC series) |  |  |  |  | Mini PC ASUS RNUC14MNK9700000, Intel N100, Ram 16 GB DDR5 4800MHz , SSD 256GB, Wi-Fi and Bluetooth, 3Yrs Wty | [7 empty] | 20 | 20 | 2026-06-15 | 2026-06-23
Barcode Scanner CHAINWAY C61-4850 | PDA CHAINWAY C61-4850 |  |  |  | AIDB-I26010979473 / HIDP-I26012321093 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | VVN0011431 CÔNG TY TNHH CÔNG NGHỆ THÔNG MINH SHARETECH VIỆT NAM | 15500000 | 2026-02-02 | 2026-07-31 |  | 15500000 | 45 | 20 | 65 | 2026-05-01 | 2026-05-09
PC | IPC(updated) |  |  |  | HIDP-I26020929492 | Pro Tower QCT1250, Core i3-14100, Ram 8GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | VVN0010445 CÔNG TY CỔ PHẦN KỸ NGHỆ BANICO | 13888000 | 2026-03-02 |  |  |  | 30 | 20 | 50 | 2026-05-16
PC | IPC+(updated) |  |  |  | HIDP-I26020929512 | Pro Tower QCT1250, Ultra 5 235, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | VVN0010445 CÔNG TY CỔ PHẦN KỸ NGHỆ BANICO | 18717000 | 2026-03-02 | 2026-07-31 |  |  | 50 | 20 | 70 | 2026-04-26 | 2026-05-04
PC | IPC++(updated) |  |  |  | HIDP-I26020929517 | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | VVN0010445 CÔNG TY CỔ PHẦN KỸ NGHỆ BANICO | 26752000 | 2026-03-02 | 2026-07-31 |  |  | 50 | 20 | 70 | 2026-04-26 | 2026-05-04
PC | Mini PC ASUS NUC 15 (TE only) |  |  |  | XIDP-I26020690582 | NUC 15 PRO Tall/ U7-255H/16GB DDR5/512GB NVMe SSD, 3Yrs Wty | VVN0010445 CÔNG TY CỔ PHẦN KỸ NGHỆ BANICO | 20870000 |  | 2026-07-31 |  |  | 30 | 20 | 50 | 2026-05-16 | 2026-05-24
PC | Mini PC ASUS NUC 14 Essential NUC14MNK150 |  |  |  | AIDB-I26022598785 / HIDP-I26030535743 | NUC 14 Essential NUC14MNK150 Intel N150, Ram 16 GB DDR5,SSD 256GB, Wi-Fi and Bluetooth, NoOS, 3Yrs Wty | VVN0010445 CÔNG TY CỔ PHẦN KỸ NGHỆ BANICO | 9680000 |  | 2026-07-31 |  |  | 30 | 20 | 50 | 2026-05-16 | 2026-05-24
Monitor(REL) | Monitor VA2432-MHD-3, 24 inch Full HD |  |  |  | AIDB-I26020695559 / HIDP-I26031138325 | VIEWSONIC VA2432-MHD-3, 24 inch Full HD, 3Yrs | VVN0010296 CÔNG TY TNHH HTC | 1970000 | 2026-03-17 | 2026-07-31 |  |  | 30 | 20 | 50 | 2026-05-16 | 2026-05-24
Monitor | Monitor 1 |  |  |  | AIDB-I26040723335 // 0820001-0890058 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | VVN0010296 CÔNG TY TNHH HTC | 2020000 | 2026-04-17 | 2026-07-31 |  |  | 30 | 20 | 50 | 2026-05-16 | 2026-05-24
Monitor | Monitor 2 |  |  |  | AIDB-I26040723335 // 0820001-0890007 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | VVN0010296 CÔNG TY TNHH HTC | 1265000 | 2026-04-17 | 2026-07-31 |  |  | 30 | 20 | 50 | 2026-05-16 | 2026-05-24
Monitor | Monitor 3 |  |  |  | AIDB-I26031308370 | U2725QE 120HZ 27 inch, 4K/IPS/120HZ / Brand: Dell |  | 15150000 |  | 2026-07-31 |  |  |  | 20 | 20 | 2026-06-15 | 2026-06-23
Monitor | Monitor 4 |  |  |  | AIDB-I26031308370 | PA279CRV 27 inch, 4K/IPS/60Hz / Brand: ASUS |  | 11450000 |  | 2026-07-31 |  |  |  | 20 | 20 | 2026-06-15 | 2026-06-23
PC | Mini PC ASUS NUC 15 PRO Tall - APR 2026 |  |  |  | AIDB-I26040924948 | NUC 15 PRO Tall, U7- 255H, 16GB DDR5, 512GB NVMe SSD, 3Yrs Ｗty | VVN0010681 CÔNG TY CỔ PHẦN QUẢN LÝ HỆ THỐNG THÔNG TIN FLEXYS | 22750000 | 2026-04-21 | 2026-07-31 |  |  | 30 | 20 | 50 | 2026-05-16 | 2026-05-24
Printer | Printer GODEX |  |  |  | AIDB-I26040221434 / HIDP-I26041357386 | GODEX GX4600i pro, 600dpi | VVN0010454 CÔNG TY CỔ PHẦN CÔNG NGHỆ ITD | 31150000 | 2026-04-21 | 2026-07-31 |  |  | 28 | 20 | 48 | 2026-05-18 | 2026-05-26
PC | All-in-One SingPC M22Vi512H8M2-W |  |  |  | x` | SingPC M22Vi512H8M2-W , i5-12450H, Ram 8GB, SSD 256GB, 21.5inch Key-Mouse, WiFi, Bluetooth | VVN0010296 CÔNG TY TNHH HTC | 16280000 | 2026-06-03 21:07 | 2026-07-31 |  |  |  | 20 | 20
PC | All-in-One AOC (SSF) |  |  |  | AIDB-I2605204957 / HIDP-I26053084540 | All-in-One Desktop PC AOC A24A33-2FN2N8F/74 // CPU N95 ¦ Ram 8G ¦ SSD 256G ¦ IPS 23.8 inch FHD ¦ Color: Black Warranty: 03 Years | VVN0010445 CÔNG TY CỔ PHẦN KỸ NGHỆ BANICO | 13088000 | 2026-06-03 21:07 | 2026-07-31 |  |  |  | 20 | 20
Formulas:
Bidding Expiry date = [Bidding effective date]+60

## Bidding 2026 data base
Big Cagetory | Small Category | Spec (Model name, dimension, accessory,...) | PAS demand no | PAS result no | PAS material No | Vendor Name/ Vendor Code | Vendor code | Unit price | Currency | Bidding effective date (mmddyyyy) | Bidding Expiry date (mmddyyyy)
Barcode Scanner CHAINWAY C61-4850 | PDA CHAINWAY C61-4850 | C61-4850, Not including RFID module. Includes: 64GB 27-key Android 11, controller with battery, charging dock, charging adapter, glass screen protector | AIDB-I26010979473 | HIDP-I26012321093 |  | CÔNG TY TNHH CÔNG NGHỆ THÔNG MINH SHARETECH VIỆT NAM | VVN0011431 | 15500000 | VND | 2026-01-31 | 2026-07-31
Monitor | Monitor (White) | HKC MB24V7-W, 23.8 inch white display, IPS, 100Hz,3Yrs | AIDB-I25121968793 | HIDP-I25122607765 |  | CÔNG TY TNHH HTC | VVN0010296 | 1550000 | VND | 2026-01-07 | 2026-07-31
Monitor | Monitor 1 | DELL E2225HM, 21.5 inch HDMI cable, 3Yrs Wty | AIDB-I26040723335 |  | 0820001-0890058 | CÔNG TY TNHH HTC | VVN0010296 | 2020000 | VND | 2026-06-12 | 2026-07-31
Monitor | Monitor 2 | VA1903H-2, 19 inch, VGA cable + HDMI cable / Brand: VIEWSONIC | AIDB-I26040723335 |  | 0820001-0890007 | CÔNG TY TNHH HTC | VVN0010296 | 1265000 | VND | 2026-04-17 | 2026-07-31
Monitor + ARM | Monitor (White) | MB24V7-W, 23.8 inch White, With Bracket Arm Warrior WA-MH0802 (White) | AIDB-I25120962198 | HIDP-I25122708407 |  | CÔNG TY TNHH HTC | VVN0010296 | 1815000 | VND | 2026-01-07 | 2026-07-31
PC | IPC++(updated) | Pro Tower QCT1250, Ultra 7 265, Ram 16GB DDR5, SSD 512GB, Integrated graphics card, Power 180W, HDMI & DP Port, Keyboard and Mouse, 3Yrs Wty | get quotation by mail | HIDP-I26020929517 |  | CÔNG TY CỔ PHẦN KỸ NGHỆ BANICO | VVN0010445 | 26752000 | VND | 2026-02-09 | 2026-08-05
PC | Mini PC ASUS NUC 14 Essential NUC14MNK150 | NUC 14 Essential NUC14MNK150 Intel N150, Ram 16 GB DDR5,SSD 256GB, Wi-Fi and Bluetooth, NoOS, 3Yrs Wty | AIDB-I26022598785 | HIDP-I26030535743 |  | CÔNG TY CỔ PHẦN KỸ NGHỆ BANICO | VVN0010445 | 9680000 | VND | 2026-03-11 | 2026-07-31
PC | Mini PC ASUS NUC 15 PRO Tall - APR 2026 | NUC 15 PRO Tall, U7- 255H, 16GB DDR5, 512GB NVMe SSD, 3Yrs Ｗty | AIDB-I26040924948 | HIDP-I26041458147 |  | CÔNG TY CỔ PHẦN QUẢN LÝ HỆ THỐNG THÔNG TIN FLEXYS | VVN0010681 | 22750000 | VND | 2026-04-20 | 2026-07-31
PC | All-in-One SingPC M22Vi512H8M2-W | SingPC M22Vi512H8M2-W , i5-12450H, Ram 8GB, SSD 256GB, 21.5inch Key-Mouse, WiFi, Bluetooth | AIDB-I26052049572 | HIDP-I26053084537 |  | CÔNG TY TNHH HTC | VVN0010296 | 16280000 | VND | 2026-06-03 21:07 | 2026-07-31
PC | All-in-One AOC (SSF) | All-in-One Desktop PC AOC A24A33-2FN2N8F/74 // CPU N95 ¦ Ram 8G ¦ SSD 256G ¦ IPS 23.8 inch FHD ¦ Color: Black Warranty: 03 Years | AIDB-I2605204957 | HIDP-I26053084540 |  | CÔNG TY CỔ PHẦN KỸ NGHỆ BANICO | VVN0010445 | 13088000 | VND | 2026-06-03 21:07 | 2026-07-31
Printer | Barcode Printer ZEBRA (new) | ZT610, 600dpi | AIDB-I26053056461 | HIDP-I25121802930 |  | CÔNG TY TNHH KHOA HỌC ĐIỆN TỬ QUAN THỤY | VVN0011455 | 52300000 | VND | 2026-06-01 | 2026-07-31
Printer | Printer GODEX | GODEX GX4600i pro, 600dpi | AIDB-I26040221434 | HIDP-I26041357386 |  | CÔNG TY CỔ PHẦN CÔNG NGHỆ ITD | VVN0010454 | 31150000 | VND | 2026-04-21 | 2026-07-31
Scanner | Barcode Scanner SEUIC HS505DP, USB cable | HS505DP, USB cable | AIDB-I26020493841 |  | 0809001-0100032 | CÔNG TY TNHH CÔNG NGHỆ THÔNG MINH SHARETECH VIỆT NAM | VVN0011431 | 2300000 | VND | 2026-03-10 | 2026-07-31
Scanner | Barcode Scanner SEUIC HS505HDP-2530 ,USB cable | SEUIC HS505HDP-2530 ,USB cable | AIDB-I26020493841 |  | 0809001-0100026 | CÔNG TY TNHH CÔNG NGHỆ THÔNG MINH SHARETECH VIỆT NAM | VVN0011431 | 3300000 | VND | 2026-03-10 | 2026-07-31
Scanner | Barcode Scanner ZEBRA DS8178,USB cable | ZEBRA DS8178,USB cable PCS Wireless Scanner | AIDB-I26022397821 | HIDP-I26030434700 |  | CÔNG TY TNHH CÔNG NGHỆ THÔNG MINH SHARETECH VIỆT NAM | VVN0011431 | 5800000 | VND | 2026-03-07 | 2026-07-31

## NonG Project Timeline (hidden)
Rule: MVA EQ in-house date will be 2weeks earlier than each stage Date of each stage = OPM release
| Brand | 1st stage | 2nd stage | 3rd stage | 4th stage | 5th stage | 6th stage
| NONE-G | P1.0 | P1.1 | EVT | DVT | PVT | MP
Project Year | Project | Date | Date | Date | Date | Date | Date | OPM mail
| LS1 |  |  |  |  | 2026-05-05
LS2
LS3
MS1
JP1
LD1
LD3
ML1
MH2
| OC1 | [7 empty] | Project | LD1
| OC2 | [7 empty] | Stage | PVT
OR4
| OR5 | [6 empty] | Mary Hạnh Nguyễn - OPM
| OR6 | [6 empty] | Trung Hoàng (Howard - OPM FATP) | Line Open Date
| HSA | [7 empty] | EQ Arrival Date | -14 | line open date - 14 days
| SSF | [6 empty] | Lani Than
AS3
Formulas:
LD1 = [LD1, row above]-14

## Purchase RQ template (hidden)
Date of Request | Department | Requester name | Requester employee ID | Email | Phone | Item | Request equipment spec | Price | Quantity | Total Cost | Purpose | Project | Stage | Required Delivery Date(line open date - 14 days) | Given LT (days) | Action | Remark | Budget Status | Budget # | PR Status | PR # | PO Status | PO # | AIH | #PUR request No
[7 empty] | #N/A |  |  |  |  | PKK4 | PVT | #N/A
[7 empty] | #N/A |  |  |  |  | 4CS4 | PVT | #N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A